## Sheet1
Tab Status | Works | File No | Category | PO No | Item Code | Item Cateogry | Item Name | Specs/Standard | Dia. - mm | Length - mm | Job No | MO No | Customer | Qty. | UOM | Wt./Pc T | Total Wt. Ton | Demand Dt. | Protocol Approval Date | Req. Dt. | Lead Time | Supplier | Country | City | Payment Ref No | Batch No | Payment Ref Date | Bank | Payment Mode | Ret Dt. | Unit Price | Currency | Exchange Rate | Total Value(FC) Batch_Wise | Total Value(FC) | Total Value(PKR) Batch_Wise | Total Value(PKR) | Docs Status | Account Approval | Bank Approval | H.S. Code | EFS | S/Terms | QE S/Agent | Target Vessel | S. Line | Local Agent | Mode of Shipment | B/L # | Free Days | POL | POD | Rediness Dt. | ETD | 1st ETA | 2nd ETA | 3rd ETA | 4th ETA | ETA | Transit Time | C/Agent | GD File | GD No | Clearance Mode | Gate-out | Last Free Day | Clearance Time | ETA Works | Actual Lead Time | Protocol Approval Variance with IDM | Total Variance | Adv Pay Dt. | Value | Adv Payment Status | Retire. Dt. | Value2 | LC Payment Status | T&D Payment Date | Value3 | T&D Payment Status | Ex. Rate | Invoice Value | Imp Value | Tariff | Clearance | GIN Status | GIN Date | ELC Amount/Unit | UOM2 | ALC Amount/Unit2 | ALC Status | ALC Date | ALC Lead Time | QFL Charges | C/A Bill Status | C/A Bill Received Date | Bill Submission Date to A/C | Current Status | Remarks | supplier_id | clearing_agent_id | pod_id | pol_id | works_id
Arrived | QE |  |  |  | TMPNL0001 |  | Old Rolls -TPC 06 Pcs | [6 empty] | 6 | Pcs | [5 empty] | 0 | TPC | Tanzania |  | Exp-2316 |  |  |  | Exp |  |  | $ |  | 0 |  | 0 | [11 empty] | By Sea | MEDUTZ352179 | FCL |  | Karachi |  | 2025-12-09 | 2026-01-09 | 2026-01-13 | 2026-01-30 | 2026-02-04 | 2026-02-04 | 57 | EFS | 2026-02-04 | KAPS-TI-134916 |  | 2026-02-13 |  | 9 | 2026-02-20 | 0 | 0 | 0 |  | 0 | Unpaid |  |  |  | 2026-02-04 | 1200000 | Paid | 0 | 0 | 0 | [5 empty] | Pcs | [8 empty] | Arrived at Works | F.I Approval Pending | 1 | 1 | 1 |  | 1
Arrived | QE |  | Refurb. |  | TMPNL0002 |  | Old Rolls | As per PO. |  |  | 2258, 2259, 2262 |  | Simunye, Mhlume, UCL | 3 | Pcs |  | 55.4 |  |  |  | 0 | SONKOR | SA | Durban | Exp. 2280 |  |  | HMB | FOC | [5 empty] | 39450 |  | 0 |  |  |  | 8438.901 | No | CFR |  | 2025-04-22 | Hapag-Lloyd | Ceva Log. - KHI | 1 x 20' OT | MEDUFI430663 | Pending | Durban | Karachi-port | 2025-04-10 | [8 empty] | 2025-08-13 | KAPS-TI-26638 |  |  |  |  | 2025-08-25 | 0 | 0 | 0 | [17 empty] | Pcs | [8 empty] | Arrived at Works | On time | 2 |  | 2 | 1 | 1
Arrived | QE |  | Refurb. |  | TMPNL0003 |  | Old Rolls | As per PO. |  |  | 2258, 2259, 2262 |  | Simunye, Mhlume, UCL | 9 | Pcs. | [5 empty] | 0 | SONKOR | SA | Durban | Exp. 2258, 2259,2262 |  |  | HMB | FOC | [5 empty] | 80259 |  | 0 |  |  |  | 8438.901 | No | CFR |  | 2025-04-22 | Hapag-Lloyd | Ceva Log. - KHI | 1 x 20' OT | MEDUFI384175 | Pending | Durban | Karachi-port | 2025-04-10 | [8 empty] | 2025-07-11 | KAPS-TI-7136 |  |  |  |  | 2025-07-22 | 0 | 0 | 0 | [17 empty] | Pcs. | [8 empty] | Arrived at Works | On time | 2 |  | 2 | 1 | 1
Arrived | QE |  |  |  | TMPNL0004 |  | Old Rolls | As per PO. |  |  | 2258 |  | Simunye | 4 | Pc | [5 empty] | 0 |  |  |  | Exp. 2258 | [9 empty] | 50400 |  | 0 | [11 empty] | DBA0372837 | [12 empty] | 2025-06-20 | KAPS-TI-205449 |  |  |  |  | 2025-07-01 | 0 | 0 | 0 | [17 empty] | Pc | [8 empty] | Arrived at Works | On time |  |  |  |  | 1
Arrived | QE |  | Refurb. |  | TMPNL0005 |  | Old Rolls | As per PO. | [5 empty] | 2 | Pcs. | [5 empty] | 0 | SONKOR | SA | Durban | Exp. 2200 |  |  | HMB | FOC | [5 empty] | 26026 |  | 0 |  |  |  | 8438.901 | No | CFR |  | 2025-02-25 | CMA CGM | CMA CGM - KHI | 2 x 20' OT | DBA0366148 / DUR250078975 | 6 | Durban | Karachi-port | 2025-02-24 | 2025-02-25 | 2025-03-21 |  |  |  |  | 3.4286 | Eastern | 2025-03-24 |  | Green | 2025-03-28 | 2025-03-26 | 7 | 2025-04-03 | 0 | 0 | 0 | [17 empty] | Pcs. | [8 empty] | Arrived at Works | On time | 2 | 2 | 2 | 1 | 1
Arrived | QE |  | Refurb. |  | TMPNL0006 |  | Old Rolls | As per PO. | [5 empty] | 1 | Pc. | [5 empty] | 0 | SONKOR | SA | Durban | Exp. 2178 |  |  | HMB | FOC | [5 empty] | 15795 |  | 0 |  |  |  | 8438.901 | No | CFR |  | 2025-02-05 | CMA CGM | Ceva - KHI | 1 x 40' OT | DBA0365115 | 6 | Durban | Karachi-port | 2025-02-05 | 2025-02-05 | 2025-03-15 |  |  |  |  | 5.4286 | Eastern | 2025-03-17 |  | Green |  | 2025-03-20 |  | 2025-03-27 | 0 | 0 | 0 | [17 empty] | Pc. | [8 empty] | Arrived at Works | On time | 2 | 2 | 2 | 1 | 1
Arrived | QE |  | Refurb. |  | TMPNL0007 |  | Old Rolls | As per PO. | [5 empty] | 4 | Pcs. | [5 empty] | 0 | SONKOR | SA | Durban | Exp. 2178 |  |  | HMB | FOC | [5 empty] | 64700 |  | 0 |  |  |  | 8438.901 | No | CFR |  | 2024-12-27 | CMA CGM | CMA CGM - KHI | 2 x 20' + 2 x 40' OT | DBA0362352 | 7 | Durban | Karachi-port | 2024-12-27 | 2024-12-27 | 2025-02-02 |  |  |  |  | 5.2857 | Eastern | 2025-02-03 |  | Green | 2025-02-11 | 2025-02-07 | 8 | 2025-02-15 | 0 | 0 | 0 | [17 empty] | Pcs. | [8 empty] | Arrived at Works | On time | 2 | 2 | 2 | 1 | 1
Arrived | QE |  | Refurb. |  | TMPNL0008 |  | Old Rolls | As per PO. | [5 empty] | 3 | Pcs. | [5 empty] | 0 | SONKOR | SA | Durban | Exp. 2120, 2178 |  |  | HMB | FOC | [5 empty] | 47459 |  | 0 |  |  |  | 8438.901 | No | CFR |  | 2025-01-21 | CMA CGM | Ceva - KHI | 3 x 20' OT | DBA0364007 | 7 | Durban | Karachi-port | 2025-01-21 | 2025-01-22 | 2025-02-21 |  |  |  |  | 4.2857 | Eastern | 2025-02-21 |  | Green | 2025-03-01 | 2025-02-27 | 8 | 2025-03-05 | 0 | 0 | 0 | [17 empty] | Pcs. | [8 empty] | Arrived at Works | On time | 2 | 2 | 2 | 1 | 1
Arrived | QE |  | Refurb. |  | TMPNL0009 |  | Old Rolls | As per PO. | [5 empty] | 1 | Pc. | [5 empty] | 0 | SONKOR | SA | Durban | Exp. 2111 |  |  | HMB | FOC | [5 empty] | 4868 | 0 | 0 |  |  |  | 8438.901 | No | CFR |  | 2024-12-22 | CMA CGM | Pending | 1 x 20' O/T | ABQ0115597 | 7 | Beira | Karachi-port | 2024-12-24 | 2024-12-22 | 2025-01-23 |  |  |  |  | 4.5714 | Eastern | 2025-01-24 |  | Green | 2025-01-31 | 2025-01-30 | 8 | 2025-02-03 | 0 | 0 | 0 | [17 empty] | Pc. | [8 empty] | Arrived at Works | On time | 2 | 2 | 2 | 2 | 1
Shafts/Ongoing/Import Status/Import Rem | QCL | Foundry Material | Store |  | 26487-60 |  | Zircon Coating | CK780/RISA-5100 | [5 empty] | 13.2 | Ton |  |  | 2026-02-24 |  | 2026-05-24 | 12.7143 | SQ | China |  | DP |  | 2026-04-21 | BAH | CAD |  | 1920 | $ | 279.25 | 30230.7 | 25344 | 1364610.975 |  |  |  |  | 3824.1 |  | CFR Karachi |  |  |  |  | Sea |  |  |  | Karachi |  | 2026-06-25 | 2026-07-17 |  |  |  | 2026-07-17 | 22 | [6 empty] | 0 | 2026-07-27 | 21.8571 | 0 | -64 |  |  |  | 2026-07-30 |  | Unpaid | 2026-04-30 |  | Unpaid | 279.25 |  |  | 0.23 | 0.065 |  |  | 575 | Kg | [8 empty] | Ready Awaiting Sailing | 3 Ton for QBL-II, 10.2 Ton for QCL/Shipment ETD was 09-05-2026, China customs hold the shipment due to sudden new policy changes on DG material and custom required Analysis certificate to got approval for export, this procedure will be completed by end of May afterwards CIQ Inspection will conducted and shipment will be planned to sail accordingly. | 3 |  | 1 |  | 2
Shafts/Ongoing/Import Status/Import Rem | QCL | Foundry Material | Store |  | 26486-60 |  | Intensifier | Reflak-212/Risa-5107 | [5 empty] | 5.46 | Ton |  |  | 2026-02-24 |  | 2026-05-24 | 12.7143 | SQ | China |  | DP |  | 2026-04-21 | BAH | CAD |  | 895 | $ | 279.25 |  | 4886.7 |  | 1364610.975 |  |  |  | 3824.1 |  | CFR Karachi |  |  |  |  | Sea |  |  |  | Karachi |  | 2026-06-25 | 2026-07-17 |  |  |  | 2026-07-17 | 22 | [6 empty] | 0 | 2026-07-27 | 21.8571 | 0 | -64 |  |  |  | 2026-07-30 | 1364610.975 | Unpaid | 2026-04-30 | 406585.84 | Unpaid | 279.25 | 1364610.975 | 1378257.0847 | 0.23 | 0.065 |  |  | 264 | Kg | [8 empty] | Ready Awaiting Sailing | QCL Only /Shipment ETD was 09-05-2026, China customs hold the shipment due to sudden new policy changes on DG material and custom required Analysis certificate to got approval for export, this procedure will be completed by end of May afterwards CIQ Inspection will conducted and shipment will be planned to sail accordingly. | 3 |  | 1 |  | 2
Arrived | QCL |  |  |  | 19969-60 |  | SCRAP OF CAST IRON | [6 empty] | 244.818 | Tons | [5 empty] | 0 |  |  |  | CAD 38043 |  | 2025-05-30 | [5 empty] | 282.5 |  | 91806.75 |  | 25935406.875 | [11 empty] | HLCUBSC2504CWGR0 | [12 empty] | 2025-07-07 | KPPI-HC-1131 |  | 2025-07-08 |  |  | 2025-07-11 | 0 | 0 | 0 | [17 empty] | Tons | [8 empty] | Arrived at Works | On time |  |  |  |  | 2
Shafts/Ongoing/Import Status/Import Rem | QCL |  | Store |  | 21824-60 |  | Anode Butt | 100-700mm | [5 empty] | 150 | Ton |  |  | 2025-10-23 |  | 2026-01-23 | 13.1429 | Pakmin Trading | UAE | Sharjah | CAD |  |  |  | CAD |  | 365 | $ | 282 | 54750 | 54750 | 15439500 | 15439500 |  |  |  | 3801.9 |  | CFR Karachi |  |  |  |  | Sea |  |  | Damam | Karachi |  | 2026-07-25 | 2026-07-31 |  |  |  | 2026-07-31 | 6 | EFS | [5 empty] | 0 | 2026-08-10 | 41.5714 | 0 | -199 | 2025-11-19 | 15439500 | Unpaid |  |  |  |  | 5068015.875 | Unpaid | 282 | 15439500 | 15593895 | 0.26 | 0.065 |  |  | 126 | Kg | [8 empty] | Ready Awaiting Sailing | Vessel struck at Jebel Ali seaport, UAE since 05-03-2026 due to closure of strait of Hermuz. | 4 | 1 | 1 | 3 | 2
[5 empty] | TMPNL0010 | [19 empty] | abc-2121 | [8 empty] | 0 |  | 0 | [30 empty] | 0 |  |  | 0 | 0 | [17 empty] | 0
Arrived | QE |  |  |  | TMPNL0011 |  | Old Rolls - (S) Simunye | [6 empty] | 1 | Pcs | [5 empty] | 0 | Sonkor | SA | [8 empty] | $ | 284 | 12600 | 12600 | 3578400 | 3578400 |  |  |  |  | NO | OLB |  |  |  |  | By Sea |  | FCL |  | 0 |  | 2025-07-21 | 2025-08-19 |  |  |  | 2025-08-19 | 29 | EFS | [5 empty] | 0 | 2025-08-29 | 0 | 0 | 0 |  | 0 | Unpaid |  |  | Unpaid | 2025-08-19 | 234921.96 | Paid | 284 | 3578400 | 3614184 |  | 0.065 |  |  |  | Pcs | [8 empty] | Arrived at Works |  | 2 | 1 |  |  | 1
Arrived | QEN |  | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 4140 | 618 | 5285 | SE25-LAGE-0008 |  | Ingenio LA Garcia | 1 | Ton | 12.464 | 12.464 | 2025-12-11 |  | 2026-03-05 | 12 | Qilu | China | Jining | 90035 | B2 | 2025-12-26 | BAH | LC |  | 8300 | ¥ | 40 |  | 103451.2 |  | 4138048 |  |  |  | 7228.4 |  | FOB Shanghai |  | Interasia Amplify |  | Broco | Sea | SHZS60000800 |  | Shanghai | Karachi | 2026-01-21 | 2026-02-22 | 2026-03-17 | 2026-03-19 | 2026-03-21 |  | 2026-03-21 | 27 | EFS | 2026-03-24 | KAPS-FS-162511 |  | 2026-03-26 |  | 2 | 2026-04-02 | 16 | 0 | -28 |  |  |  | 2026-02-05 | 4138048 | Paid | 2026-03-21 | 355251.4208 | Paid | 40 | 4138048 | 4179428.48 | 0.02 | 0.065 |  |  | 386 | Kg | 367 |  | 2026-06-12 | 52 |  |  |  |  | Arrived at Works | Vessel Rollover from ETD: 25-01-26 to 09-02-2026 & 17-02-26 & 22-02-2026 due to shipper export license issue and vessel rollover. | 5 | 1 | 1 | 4 | 3
Arrived | QEN |  | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 4140 | 537 | 4592 | SE25-LAGE-0009 |  | Ingenio LA Garcia | 1 | Ton | 8.177 | 8.177 | 2025-12-11 |  | 2026-03-05 | 12 | Qilu | China | Jining | 90035 | B2 | 2025-12-26 | BAH | LC |  | 8300 | ¥ | 40 |  | 67869.1 |  | 2714764 |  |  |  | 7228.4 |  | FOB Shanghai |  | Interasia Amplify |  | Broco | Sea | SHZS60000800 |  | Shanghai | Karachi | 2026-01-21 | 2026-02-22 | 2026-03-17 | 2026-03-19 | 2026-03-21 |  | 2026-03-21 | 27 | EFS | 2026-03-24 | KAPS-FS-162511 |  | 2026-03-26 |  | 2 | 2026-04-02 | 16 | 0 | -28 |  |  |  | 2026-02-05 | 2714764 | Paid | 2026-03-21 | 233062.4894 | Paid | 40 | 2714764 | 2741911.64 | 0.02 | 0.065 |  |  | 386 | Kg | 367 |  | 2026-06-12 | 52 |  |  |  |  | Arrived at Works | Vessel Rollover from ETD: 25-01-26 to 09-02-2026 & 17-02-26 due to shipper export license issue and vessel rollover. | 5 | 1 | 1 | 4 | 3
Arrived | QEN |  | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 4140 | 537 | 4287 | SE25-LAGE-0010 |  | Ingenio LA Garcia | 1 | Ton | 7.634 | 7.634 | 2025-12-11 |  | 2026-03-05 | 12 | Qilu | China | Jining | 90035 | B2 | 2025-12-26 | BAH | LC |  | 8300 | ¥ | 40 |  | 63362.2 |  | 2534488 |  |  |  | 7228.4 |  | FOB Shanghai |  | Interasia Amplify |  | Broco | Sea | SHZS60000800 |  | Shanghai | Karachi | 2026-01-21 | 2026-02-22 | 2026-03-17 | 2026-03-19 | 2026-03-21 |  | 2026-03-21 | 27 | EFS | 2026-03-24 | KAPS-FS-162511 |  | 2026-03-26 |  | 2 | 2026-04-02 | 16 | 0 | -28 |  |  |  | 2026-02-05 | 2534488 | Paid | 2026-03-21 | 217585.7948 | Paid | 40 | 2534488 | 2559832.88 | 0.02 | 0.065 |  |  | 386 | Kg | 367 |  | 2026-06-12 | 52 |  |  |  |  | Arrived at Works | Vessel Rollover from ETD: 25-01-26 to 09-02-2026 & 17-02-26 due to shipper export license issue and vessel rollover. | 5 | 1 | 1 | 4 | 3
Arrived | QEN |  | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 4140 | 589 | 5243 | SE25-LAGE-0011 |  | Ingenio LA Garcia | 1 | Ton | 11.232 | 11.232 | 2025-12-11 |  | 2026-03-05 | 12 | Qilu | China | Jining | 90035 | B2 | 2025-12-26 | BAH | LC |  | 8300 | ¥ | 40 |  | 93225.6 |  | 3729024 |  |  |  | 7228.4 |  | FOB Shanghai |  | Interasia Amplify |  | Broco | Sea | SHZS60000800 |  | Shanghai | Karachi | 2026-01-21 | 2026-02-22 | 2026-03-17 | 2026-03-19 | 2026-03-21 |  | 2026-03-21 | 27 | EFS | 2026-03-24 | KAPS-FS-162511 |  | 2026-03-26 |  | 2 | 2026-04-02 | 16 | 0 | -28 |  |  |  | 2026-02-05 | 3729024 | Paid | 2026-03-21 | 320136.7104 | Paid | 40 | 3729024 | 3766314.24 | 0.02 | 0.065 |  |  | 386 | Kg | 367 |  | 2026-06-12 | 52 |  |  |  |  | Arrived at Works | Vessel Rollover from ETD: 25-01-26 to 09-02-2026 & 17-02-26 due to shipper export license issue and vessel rollover. | 5 | 1 | 1 | 4 | 3
Arrived | QEN |  | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 4140 | 587 | 4938 | SE25-LAGE-0012 |  | Ingenio LA Garcia | 1 | Ton | 10.507 | 10.507 | 2025-12-11 |  | 2026-03-05 | 12 | Qilu | China | Jining | 90035 | B2 | 2025-12-26 | BAH | LC |  | 8300 | ¥ | 40 |  | 87208.1 |  | 3488324 |  |  |  | 7228.4 |  | FOB Shanghai |  | Interasia Amplify |  | Broco | Sea | SHZS60000800 |  | Shanghai | Karachi | 2026-01-21 | 2026-02-22 | 2026-03-17 | 2026-03-19 | 2026-03-21 |  | 2026-03-21 | 27 | EFS | 2026-03-24 | KAPS-FS-162511 |  | 2026-03-26 |  | 2 | 2026-04-02 | 16 | 0 | -28 |  |  |  | 2026-02-05 | 3488324 | Paid | 2026-03-21 | 299472.6154 | Paid | 40 | 3488324 | 3523207.24 | 0.02 | 0.065 |  |  | 386 | Kg | 367 |  | 2026-06-12 | 52 |  |  |  |  | Arrived at Works | Vessel Rollover from ETD: 25-01-26 to 09-02-2026 & 17-02-26 due to shipper export license issue and vessel rollover. | 5 | 1 | 1 | 4 | 3
Arrived | QEN |  | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 1045 | 403 | 4045 | SE25-LAGE-0013 |  | Ingenio LA Garcia | 1 | Ton | 4.057 | 4.057 | 2025-12-11 |  | 2026-03-05 | 12 | Qilu | China | Jining | 90035 | B1 | 2025-12-26 | BAH | LC |  | 7700 | ¥ | 40 | 193785.9 | 31238.9 | 7751436 | 1249556 |  |  |  | 7214.109 |  | FOB Shanghai |  | Zhong GU XI AN |  | Broco | Sea | 757610069636 |  | Shanghai | Karachi | 2026-01-21 | 2026-02-17 | 2026-03-13 |  |  |  | 2026-03-13 | 24 | EFS | 2026-03-17 | KAPS-FS-007937 |  | 2026-03-18 |  | 1 | 2026-03-30 | 15.5714 | 0 | -25 |  |  |  | 2026-02-05 | 1249556 | Paid | 2026-03-13 | 107274.3826 | Paid | 40 | 1249556 | 1262051.56 | 0.02 | 0.065 |  |  | 361 | Kg | 343 |  | 2026-06-12 | 55 |  |  |  |  | Arrived at Works | Vessel Rollover from ETD: 25-01-26 to 09-02-2026 & 17-02-26 due to shipper export license issue and vessel rollover. | 5 | 1 | 1 | 4 | 3
Arrived | QEN |  | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 1045 | 558 | 5490 | SE25-SARI-0004 |  | Sonkor(SARI) | 2 | Ton | 10.555 | 21.11 | 2025-12-11 |  | 2026-03-05 | 12 | Qilu | China | Jining | 90035 | B1 | 2025-12-26 | BAH | LC |  | 7700 | ¥ | 40 |  | 162547 |  | 6501880 |  |  |  | 7214.109 |  | FOB Shanghai |  | Zhong GU XI AN |  | Broco | Sea | 757610069636 |  | Shanghai | Karachi | 2026-01-21 | 2026-02-17 | 2026-03-13 |  |  |  | 2026-03-13 | 24 | EFS | 2026-03-17 | KAPS-FS-007937 |  | 2026-03-18 |  | 1 | 2026-03-30 | 15.5714 | 0 | -25 |  |  |  | 2026-02-05 | 6501880 | Paid | 2026-03-13 | 558186.398 | Paid | 40 | 6501880 | 6566898.8 | 0.02 | 0.065 |  |  | 361 | Kg | 343 |  | 2026-06-12 | 55 |  |  |  |  | Arrived at Works | Vessel Rollover from ETD: 25-01-26 to 09-02-2026 & 17-02-26 due to shipper export license issue and vessel rollover. | 5 | 1 | 1 | 4 | 3
Shafts/Ongoing/Import Status/Import Rem | QEN |  | Engg. |  | TMPNL0019 |  | Double Column Vertical Lathe Machine | CK5231B | [5 empty] | 1 | Pcs | 45 | [5 empty] | Ruitai | China |  | 87578 |  | 2025-12-10 | BAH | LC |  | 136666 | $ | 278.7 | 136666 | 136666 | 38088814.2 | 38088814.2 |  |  |  | 8458.99 |  | CFR-FCL |  | Ever Utile |  |  | By Sea | 144600157406 |  | Dalian | Karachi | 2026-02-28 | 2026-06-08 | 2026-07-26 |  |  |  | 2026-07-26 | 48 | EFS | [5 empty] | 0 | 2026-08-05 | 0 | 0 | 0 |  |  |  | 2026-06-22 | 38088814.2 | Paid | 2026-07-26 | 3269924.6991 | Unpaid | 278.7 | 38088814.2 | 38469702.342 | 0.02 | 0.065 |  |  |  | Pcs | [8 empty] | In Transit | Vessel Booking received from supplier as ETD: 08-06-2026, ETA:03-08-26, Now received new ETA: 26-07-26 | 6 | 1 | 1 | 5 | 3
Arrived | QCL |  | Store |  | 19969-60 |  | Cast Iron Scrap | [6 empty] | 178.36 | Ton | [5 empty] | 0 | Prime Commodities Fze | UAE |  | 87234 |  | 2025-12-03 | BAH | LC |  | 355 | $ | 280.45 | 63317.8 | 63317.8 | 17757477.01 | 17757477.01 |  |  |  | 7204.109 | No | CFR Karachi |  | MSC Linzie | MSC | MSC Pakistan | By Sea | MEDUYK516787 |  | Gdynia, Poland | Karachi | 2025-12-30 | 2025-11-15 | 2025-12-30 | 2025-12-31 | 2026-01-01 |  | 2026-01-01 | 47 | MHQ | 2026-01-02 | KPPI-HC-38901 |  | 2026-01-03 |  | 1 | 2026-01-09 | 0 | 0 | 0 |  |  |  | 2025-12-23 | 17757477.01 | Paid | 2025-12-25 | 6187592.8641 | Paid | 280.45 | 17757477.01 | 17935051.7801 | 0.28 | 0.065 |  |  | 129 | Kg | [8 empty] | Arrived at Works |  | 7 | 3 | 1 | 6 | 2
Arrived | QBL-II |  | Store |  | 26287-60 |  | Resin | APR-103D | [5 empty] | 15.6 | Ton |  |  | 2025-10-27 |  | 2026-01-28 | 13.2857 | SQ | China | Jinancity | 86686 |  | 2025-11-25 | BAH | LC |  | 790 | $ | 280.4 |  | 12324 |  | 3455649.6 |  |  |  | 3824.1 | EFS | CFR-FCL |  | ESL Dachan Bay | TS Lines | Sharaf Shipping | By Sea | 799510774012 |  | Qingdao | Karachi | 2025-12-20 | 2025-12-19 | 2026-01-11 | 2026-01-14 |  |  | 2026-01-14 | 26 | EFS | 2026-01-14 | KAPS-FS-121254 |  | 2026-01-17 |  | 3 | 2026-01-24 |  | 0 | 4 |  |  |  | 2026-01-08 | 3455649.6 | Paid |  | 1029610.7983 | Paid | 280.4 | 3455649.6 | 3490206.096 | 0.23 | 0.065 |  |  | 257 | Kgs | 256 | [7 empty] | Arrived at Works | Vessel booking received from Cukurova ETD:17-12-2025, Vessel rollover ETD:30-12-25 | 3 | 1 | 1 | 7 | 4
Arrived | QBL-II |  | Store |  | 26382-60 |  | Hardener | HQ-G60 | [5 empty] | 5 | Ton |  |  | 2025-10-27 |  | 2026-01-28 | 13.2857 | SQ | China | Jinancity | 86686 |  | 2025-11-25 | BAH | LC |  | 1510 | $ | 280.4 |  | 7550 |  | 2117020 |  |  |  | 3824.1 | EFS | CFR-FCL |  | ESL Dachan Bay | TS Lines | Sharaf Shipping | By Sea | 799510774012 |  | Qingdao | Karachi | 2025-12-20 | 2025-12-19 | 2026-01-11 | 2026-01-14 |  |  | 2026-01-14 | 26 | EFS | 2026-01-14 | KAPS-FS-121254 |  | 2026-01-17 |  | 3 | 2026-01-24 |  | 0 | 4 |  |  |  | 2026-01-08 | 2117020 | Paid |  | 630766.109 | Paid | 280.4 | 2117020 | 2138190.2 | 0.23 | 0.065 |  |  | 474 | Kgs | 463 | [7 empty] | Arrived at Works | Vessel booking received from Cukurova ETD:17-12-2025, Vessel rollover ETD:30-12-25 | 3 | 1 | 1 | 7 | 4
Arrived | QCL |  | Store |  | 19969-60 |  | Cast Iron Scrap | Oversized | [5 empty] | 83.47 | Ton | [5 empty] | 0 | KE Metal | USA |  | 74518 |  | 2025-07-21 | BAH | LC | 2025-08-19 | 385 | $ | 282.5 |  | 32135.95 |  | 9078405.875 |  |  |  | 7204.109 | EFS | CFR - FCL |  | MSC UNIFIC | MSC | MSC Pakistan | By Sea | MEDUJZ306948 | FCL | New York | Karachi |  | 2025-07-19 | 2025-09-02 | 2025-09-09 | 2025-09-13 | 2025-09-20 | 2025-09-20 | 63 | MHQ | 2025-09-25 | KPPI-HC-17648 | Green | 2025-09-26 |  | 1 | 2025-09-30 | 0 | 0 | 0 |  |  | Unpaid | 2025-08-19 | 9078405.875 | Paid | 2025-09-25 | 779381.1444 | Paid | 282.5 | 9078405.875 | 9169189.9337 | 0.02 | 0.065 |  |  |  | Ton | [8 empty] | Arrived at Works | On-time ( ETA changed from 02-Sep to 09-Sep, 13 Sep & 20 Sep) | 8 | 3 | 1 | 8 | 2
Arrived | QCL |  |  |  | 19969-60 |  | SCRAP OF CAST IRON | [6 empty] | 145.181 | Ton | [5 empty] | 0 |  |  |  | 72056 |  | 2025-06-30 | [5 empty] | 283.8 |  | 54442.875 |  | 15450887.925 | [11 empty] | HLCUBSC2506BKWN7 | [12 empty] | 2025-08-19 | KPPI-HC-9615 |  | 2025-08-22 |  |  | 2025-08-26 | 0 | 0 | 0 | [17 empty] | Ton | [8 empty] | Arrived at Works | On time |  |  |  |  | 2
Arrived | QCL |  |  |  | 19969-60 |  | SCRAP OF CAST IRON | [6 empty] | 62.568 | Ton | [5 empty] | 0 |  |  |  | 72056 |  | 2025-06-30 | [5 empty] | 283.8 |  | 23463 |  | 6658799.4 | [11 empty] | HLCUBSC2506ASWB7 | [12 empty] | 2025-08-15 | KPPI-HC-8861 |  | 2025-08-17 |  |  | 2025-08-19 | 0 | 0 | 0 | [17 empty] | Ton | [8 empty] | Arrived at Works | On time |  |  |  |  | 2
Arrived | QCL |  | Store |  | 19969-60 |  | Cast Iron Scrap | Oversized | [5 empty] | 62.568 | Ton | [5 empty] | 0 | KE Metal | USA |  | 72056 | B1 | 2025-06-30 | BAH | LC | 2025-07-31 | 375 | $ | 283.8 | 23463 | 23463 | 6658799.4 | 6658799.4 |  |  |  | 7204.109 | NO | CFR - FCL |  | Nagoya Express | Hapag | Happag-Lloyd Pakistan | By Sea | HLCUBSC2506SWB7 | FCL | New York | Karachi |  | 2025-06-24 | 2025-08-13 |  |  |  | 2025-08-13 | 50 | MHQ | 2025-08-15 | KPPI-HC-8861 |  | 2025-08-17 |  | 2 | 2025-08-19 | 0 | 0 | 0 |  |  | Unpaid |  |  | Unpaid | 2025-08-13 | 2522020.2728 | Paid | 283.8 | 6658799.4 | 6725387.394 | 0.31 | 0.065 |  |  |  | Ton | [8 empty] | Arrived at Works |  | 8 | 3 | 1 | 8 | 2
Arrived | QCL |  | Store |  | 19969-60 |  | Cast Iron Scrap | Oversized | [5 empty] | 145.181 | Ton | [5 empty] | 0 | KE Metal | USA |  | 72056 | B2 | 2025-06-30 | BAH | LC | 2025-07-31 | 375 | $ | 283.8 | 54442.875 | 54442.875 | 15450887.925 | 15450887.925 |  |  |  | 7204.109 | NO | CFR - FCL |  | KOTA MANZANELLO | Hapag |  | By Sea | HUBSC2506BKWN7 | FCL | New York | Karachi |  | 2025-06-24 | 2025-08-18 |  |  |  | 2025-08-18 | 55 | MHQ | 2025-08-19 | KPPI-HC-9615 |  | 2025-08-22 |  | 3 | 2025-09-05 | 0 | 0 | 0 |  |  | Unpaid | 2025-07-31 | 15450887.925 | Paid | 2025-08-19 | 5852023.8016 | Paid | 283.8 | 15450887.925 | 15605396.8043 | 0.31 | 0.065 |  |  |  | Ton | [8 empty] | Arrived at Works |  | 8 | 3 | 1 | 8 | 2
Arrived | QCL |  | Store |  | 19969-60 |  | Cast Iron Scrap | Oversized | [5 empty] | 162.06 | Ton | [5 empty] | 0 | KE Metal | USA |  | 72056 | B3 | 2025-06-30 | BAH | LC |  | 375 | $ | 284 | 60772.5 | 60772.5 | 17259390 | 17259390 |  |  |  | 7204.109 | NO | CFR - FCL |  | KOTA MANZANELLO | Maersk |  | By Sea | 255762668 | FCL | New York | Karachi |  | 2025-07-19 | 2025-08-27 |  |  |  | 2025-08-27 | 39 | MHQ | 2025-08-28 | KPPI-HC-11661 |  | 2025-09-04 |  | 7 | 2025-09-06 | 0 | 0 | 0 |  |  | Unpaid |  |  | Unpaid | 2025-08-27 | 6536993.9625 | Paid | 282.5 | 17259390 | 17431983.9 | 0.31 | 0.065 |  |  |  | Ton | [8 empty] | Arrived at Works |  | 8 | 3 | 1 | 8 | 2
Arrived | QCL |  | Store |  | 19969-60 |  | Cast Iron Scrap | Oversized | [5 empty] | 40.481 | Ton | [5 empty] | 0 | KE Metal | USA |  | 72056 | B4 | 2025-06-30 | BAH | LC | 2025-08-19 | 375 | $ | 284 | 15180.375 | 15180.375 | 4311226.5 | 4311226.5 |  |  |  | 7204.109 | NO | CFR - FCL |  | KOTA MANZANELLO | Maersk |  | By Sea | 257047097 | FCL | New York | Karachi |  | 2025-07-27 | 2025-09-10 |  |  |  | 2025-09-10 | 45 | MHQ | 2025-09-11 | KPPI-HC-14396 |  | 2025-09-14 |  | 3 | 2025-09-16 | 0 | 0 | 0 |  |  | Unpaid | 2025-08-19 | 4354338.765 | Paid | 2025-09-10 | 1632877.0369 | Paid | 282.5 | 4311226.5 | 4354338.765 | 0.31 | 0.065 |  |  |  | Ton | [8 empty] | Arrived at Works |  | 8 | 3 | 1 | 8 | 2
Arrived | QBL-II |  | Store |  | 16784-60 |  | T Pipe brick | Dia60 | [5 empty] | 1400 | Pcs |  |  | 2025-11-06 |  | 2026-02-06 | 13.1429 | One Piece | China | Shanghai | 70664 |  |  | BAH | CAD |  | 4.74 | ¥ | 39.95 | 90020.4 | 6636 | 3596314.98 | 265108.2 |  |  |  | 6903.901 |  | CFR Karachi |  | OOCL NAGOYA |  |  | By Sea | YMJAS237020022 |  | Shanghai | Karachi | 2025-11-20 | 2025-12-01 | 2025-12-19 | 2025-12-22 | 2025-12-29 |  | 2025-12-29 | 28 | EFS | 2025-12-22 | KAPW-HC-113784 | Green | 2025-12-23 |  | 1 | 2025-12-31 | 7.8571 | 0 | 37 |  |  |  | 2025-12-19 | 265108.2 | Paid | 2025-12-22 | 87021.7667 | Paid | 39.95 | 265108.2 | 267759.282 | 0.26 | 0.065 |  |  |  | Pcs | [8 empty] | Arrived at Works | Material is ready, Vessel booking received ETD: 01-12-25 | 9 | 1 | 1 | 4 | 4
Arrived | QBL-II |  | Store |  | 16781-60 |  | Straight Pipe | Dia60,L300 | [5 empty] | 3857 | Pcs |  |  | 2025-10-27 |  | 2026-01-26 | 13 | One Piece | China | Shanghai | 70664 |  |  | BAH | CAD |  | 5.7 | ¥ | 39.95 |  | 21984.9 |  | 878296.755 |  |  |  | 6903.901 |  | CFR Karachi |  | OOCL NAGOYA |  |  | By Sea | YMJAS237020022 |  | Shanghai | Karachi | 2025-11-20 | 2025-12-01 | 2025-12-19 | 2025-12-22 | 2025-12-29 |  | 2025-12-29 | 28 | EFS | 2025-12-22 | KAPW-HC-113784 | Green | 2025-12-23 |  | 1 | 2025-12-31 | 9.2857 | 0 | 26 |  |  |  | 2025-12-19 | 878296.755 | Paid | 2025-12-22 | 288300.9098 | Paid | 39.95 | 878296.755 | 887079.7226 | 0.26 | 0.065 |  |  |  | Pcs | [8 empty] | Arrived at Works | Material is ready, Vessel booking received ETD: 01-12-25 | 9 | 1 | 1 | 4 | 4
Arrived | QBL-II |  | Store |  | 16878-60 |  | Straight Pipe | Dia80,L300 | [5 empty] | 630 | Pcs |  |  | 2025-11-06 |  | 2026-02-06 | 13.1429 | One Piece | China | Shanghai | 70664 |  |  | BAH | CAD |  | 8.65 | ¥ | 39.95 |  | 5449.5 |  | 217707.525 |  |  |  | 6903.901 |  | CFR Karachi |  | OOCL NAGOYA |  |  | By Sea | YMJAS237020022 |  | Shanghai | Karachi | 2025-11-20 | 2025-12-01 | 2025-12-19 | 2025-12-22 | 2025-12-29 |  | 2025-12-29 | 28 | EFS | 2025-12-22 | KAPW-HC-113784 | Green | 2025-12-23 |  | 1 | 2025-12-31 | 7.8571 | 0 | 37 |  |  |  | 2025-12-19 | 217707.525 | Paid | 2025-12-22 | 71462.4951 | Paid | 39.95 | 217707.525 | 219884.6002 | 0.26 | 0.065 |  |  |  | Pcs | [8 empty] | Arrived at Works | Material is ready, Vessel booking received ETD: 01-12-25 | 9 | 1 | 1 | 4 | 4
Arrived | QBL-II |  | Store |  | 25655-60 |  | Fire Slab-Straight | 250*250*20 | [5 empty] | 3000 | Pcs |  |  | 2025-11-06 |  | 2026-02-06 | 13.1429 | One Piece | China | Shanghai | 70664 |  |  | BAH | CAD |  | 10.76 | ¥ | 39.95 |  | 32280 |  | 1289586 |  |  |  | 6903.901 |  | CFR Karachi |  | OOCL NAGOYA |  |  | By Sea | YMJAS237020022 |  | Shanghai | Karachi | 2025-11-20 | 2025-12-01 | 2025-12-19 | 2025-12-22 | 2025-12-29 |  | 2025-12-29 | 28 | EFS | 2025-12-22 | KAPW-HC-113784 | Green | 2025-12-23 |  | 1 | 2025-12-31 | 7.8571 | 0 | 37 |  |  |  | 2025-12-19 | 1289586 | Paid | 2025-12-22 | 423306.6045 | Paid | 39.95 | 1289586 | 1302481.86 | 0.26 | 0.065 |  |  |  | Pcs | [8 empty] | Arrived at Works | Material is ready, Vessel booking received ETD: 01-12-25 | 9 | 1 | 1 | 4 | 4
Arrived | QBL-II |  | Store |  | 25656-60 |  | Fire Slab-Straight | 375*125*20 | [5 empty] | 3000 | Pcs |  |  | 2025-11-06 |  | 2026-02-06 | 13.1429 | One Piece | China | Shanghai | 70664 |  |  | BAH | CAD |  | 7.89 | ¥ | 39.95 |  | 23670 |  | 945616.5 |  |  |  | 6903.901 |  | CFR Karachi |  | OOCL NAGOYA |  |  | By Sea | YMJAS237020022 |  | Shanghai | Karachi | 2025-11-20 | 2025-12-01 | 2025-12-19 | 2025-12-22 | 2025-12-29 |  | 2025-12-29 | 28 | EFS | 2025-12-22 | KAPW-HC-113784 | Green | 2025-12-23 |  | 1 | 2025-12-31 | 7.8571 | 0 | 37 |  |  |  | 2025-12-19 | 945616.5 | Paid | 2025-12-22 | 310398.6161 | Paid | 39.95 | 945616.5 | 955072.665 | 0.26 | 0.065 |  |  |  | Pcs | [8 empty] | Arrived at Works | Material is ready, Vessel booking received ETD: 01-12-25 | 9 | 1 | 1 | 4 | 4
Arrived | QBL-II |  | Store |  | 19969-60 |  | SCRAP OF CAST IRON | [6 empty] | 202.741 | Ton | [5 empty] | 0 |  |  |  | 67937 |  | 2025-05-13 | [5 empty] | 283.8 |  | 75014.17 |  | 21289021.446 | [11 empty] | HLCUBSC2505BDWG2 | [12 empty] | 2025-07-15 | KPPI-HC-2859 |  |  |  |  | 2025-07-24 | 0 | 0 | 0 | [17 empty] | Ton | [8 empty] | Arrived at Works | On time |  |  |  |  | 4
Arrived | QBL-II |  | Store |  | 19969-60 |  | IRON AND STEEL REMELTABLE (SCRAP OF CAST IRON) | [6 empty] | 41.389 | Ton | [5 empty] | 0 |  |  |  | 67937 |  | 2025-05-13 | [5 empty] | 283.8 |  | 15313.93 | 25635114.78 | 4346093.334 | [11 empty] | HLCUBSC2505CEME0 | [12 empty] | 2025-07-22 | KPPI-HC-4147 |  |  |  |  | 2025-07-28 | 0 | 0 | 0 | [17 empty] | Ton | [8 empty] | Arrived at Works | On time |  |  |  |  | 4
Shafts/Ongoing/Import Status/Import Rem | QEN | Shafts | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 1045 | 638 | 5510 | SL26-CHYS-0046 |  | Chaudry | 1 | Pcs | 13.832 | 13.832 | 2026-05-21 |  | 2026-08-13 | 12 | Qilu | China |  | 67792 |  | 2026-06-02 | BAH | LC |  | 7650 | ¥ | 41 | 253068.73 | 105814.8 | 10375817.93 | 4338406.8 |  |  |  | 7214.109 | YES | FOB |  |  |  |  | Sea |  |  |  | Karachi | 2026-06-25 | 2026-07-10 | 2026-08-07 |  |  |  | 2026-08-07 | 28 | EFS | [5 empty] | 0 | 2026-08-13 | 12 | 0 | 0 |  |  |  | 2026-07-25 | 4338406.8 | Unpaid | 2026-07-10 | 200000 | Unpaid | 41 | 4338406.8 | 4381790.868 | 0.02 | 0.065 |  |  |  | Kg | [8 empty] | Under Production | Production is about to complete. Forwarder nomination is awaited from Logistics. | 5 | 1 | 1 |  | 3
Shafts/Ongoing/Import Status/Import Rem | QEN | Shafts | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 1045 | 603 | 5040 | SE26-ALMA-0080 |  | ALMA | 1 | Pcs | 11.3022 | 11.3022 | 2026-05-21 |  | 2026-08-13 | 12 | Qilu | China |  | 67792 |  | 2026-06-02 | BAH | LC |  | 7650 | ¥ | 41 |  | 86461.83 |  | 3544935.03 |  |  |  | 7214.109 | YES | FOB |  |  |  |  | Sea |  |  |  | Karachi | 2026-06-25 | 2026-07-10 | 2026-08-07 |  |  |  | 2026-08-07 | 28 | EFS | [5 empty] | 0 | 2026-08-13 | 12 | 0 | 0 |  |  |  | 2026-07-25 | 3544935.03 | Unpaid | 2026-07-10 | 200000 | Unpaid | 41 | 3544935.03 | 3580384.3803 | 0.02 | 0.065 |  |  |  | Pcs | [8 empty] | Under Production | Production is about to complete. Forwarder nomination is awaited from Logistics. | 5 | 1 | 1 |  | 3
Shafts/Ongoing/Import Status/Import Rem | QEN | Shafts | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 1045 | 543 | 4424 | SE26-ALMA-0079 |  | ALMA | 1 | Pcs | 8.044 | 8.044 | 2026-05-21 |  | 2026-08-13 | 12 | Qilu | China |  | 67792 |  | 2026-06-02 | BAH | LC |  | 7150 | ¥ | 41 |  | 57514.6 |  | 2358098.6 |  |  |  | 7214.109 | YES | FOB |  |  |  |  | Sea |  |  |  | Karachi | 2026-06-25 | 2026-07-10 | 2026-08-07 |  |  |  | 2026-08-07 | 28 | EFS | [5 empty] | 0 | 2026-08-13 | 12 | 0 | 0 |  |  |  | 2026-07-25 | 2358098.6 | Unpaid | 2026-07-10 | 200000 | Unpaid | 41 | 2358098.6 | 2381679.586 | 0.02 | 0.065 |  |  |  | Pcs | [8 empty] | Under Production | Production is about to complete. Forwarder nomination is awaited from Logistics. | 5 | 1 | 1 |  | 3
Shafts/Ongoing/Import Status/Import Rem | QEN | Shafts | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 42CrMoA(QT) | 60 | 2620 | CE26-TSLU-0007 | CE26-MO-0162 | Lindemann | 5 | Pcs | 0.056 | 0.28 | 2026-05-21 |  | 2026-08-13 | 12 | Qilu | China |  | 67792 |  | 2026-06-02 | BAH | LC |  | 9500 | ¥ | 41 |  | 2660 |  | 109060 |  |  |  | 7228.4 | YES | FOB |  |  |  |  | Sea |  |  |  | Karachi | 2026-07-05 | 2026-07-10 | 2026-08-07 |  |  |  | 2026-08-07 | 28 | EFS | [5 empty] | 0 | 2026-08-13 | 12 | 0 | 0 |  |  |  | 2026-07-25 | 109060 | Unpaid | 2026-07-10 | 200000 | Unpaid | 41 | 109060 | 110150.6 | 0.02 | 0.065 |  |  |  | Pcs | [8 empty] | Under Production | Production is about to complete. Forwarder nomination is awaited from Logistics. | 5 | 1 | 1 |  | 3
Shafts/Ongoing/Import Status/Import Rem | QEN | Shafts | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 42CrMoA(QT) | 60 | 300 | CE26-TSLU-0007 | CE26-MO-0162 | Lindemann | 1 | Pcs | 0.065 | 0.065 | 2026-05-21 |  | 2026-08-13 | 12 | Qilu | China |  | 67792 |  | 2026-06-02 | BAH | LC |  | 9500 | ¥ | 41 |  | 617.5 |  | 25317.5 |  |  |  | 7228.4 | YES | FOB |  |  |  |  | Sea |  |  |  | Karachi | 2026-07-05 | 2026-07-10 | 2026-08-07 |  |  |  | 2026-08-07 | 28 | EFS | [5 empty] | 0 | 2026-08-13 | 12 | 0 | 0 |  |  |  | 2026-07-25 | 25317.5 | Unpaid | 2026-07-10 | 200000 | Unpaid | 41 | 25317.5 | 25570.675 | 0.02 | 0.065 |  |  |  | Pcs | [8 empty] | Under Production | Production is about to complete. Forwarder nomination is awaited from Logistics. | 5 | 1 | 1 |  | 3
Shafts/Ongoing/Import Status/Import Rem | QEN | Shafts | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 1045 | 638 | 5513 | SE25-RPLA-0014 |  | Riopaila | 2 | Pcs | 13.84 | 27.68 | 2026-05-15 |  | 2026-08-07 | 12 | Dajin | China |  | 67519 |  | 2026-05-22 | BAH | LC |  | 7600 | ¥ | 41 | 370538.47 | 210368 | 15192077.27 | 8625088 |  |  |  | 7214.109 | YES | FOB |  |  |  |  | Sea |  |  |  | Karachi | 2026-06-26 | 2026-07-09 | 2026-07-30 |  |  |  | 2026-07-30 | 21 | EFS | [5 empty] | 0 | 2026-08-07 | 12 | 0 | 0 |  |  |  | 2026-07-25 | 8625088 | Unpaid | 2026-07-10 | 200000 | Unpaid | 41 | 8625088 | 8711338.88 | 0.02 | 0.065 |  |  |  | Pcs | [8 empty] | Ready Awaiting Sailing | Cargo is ready, Vessel Bookin received ETD: 09-07-2026 | 10 | 1 | 1 |  | 3
Shafts/Ongoing/Import Status/Import Rem | QEN | Shafts | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 4140 QT | 733 | 670 | SL26-SAKS-0106 |  | Sakrand | 2 | Pcs | 1.633 | 3.266 | 2026-05-15 |  | 2026-08-07 | 12 | Dajin | China |  | 67519 |  | 2026-05-22 | BAH | LC |  | 10500 | ¥ | 41 |  | 34293 |  | 1406013 |  |  |  | 7228.8 | YES | FOB |  |  |  |  | Sea |  |  |  | Karachi | 2026-06-26 | 2026-07-09 | 2026-07-30 |  |  |  | 2026-07-30 | 21 | EFS | [5 empty] | 0 | 2026-08-07 | 12 | 0 | 0 |  |  |  | 2026-07-25 | 1406013 | Unpaid | 2026-07-10 | 200000 | Unpaid | 41 | 1406013 | 1420073.13 | 0.02 | 0.065 |  |  |  | Pcs | [8 empty] | Ready Awaiting Sailing | Cargo is ready, Vessel Bookin received ETD: 09-07-2026 | 10 | 1 | 1 |  | 3
Shafts/Ongoing/Import Status/Import Rem | QEN | Shafts | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 4140 QT | 963 | 580 | SL26-SAKS-0108 |  | Sakrand | 2 | Pcs | 2.808 | 5.616 | 2026-05-15 |  | 2026-08-07 | 12 | Dajin | China |  | 67519 |  | 2026-05-22 | BAH | LC |  | 10500 | ¥ | 41 |  | 58968 |  | 2417688 |  |  |  | 7228.8 | YES | FOB |  |  |  |  | Sea |  |  |  | Karachi | 2026-06-26 | 2026-07-09 | 2026-07-30 |  |  |  | 2026-07-30 | 21 | EFS | [5 empty] | 0 | 2026-08-07 | 12 | 0 | 0 |  |  |  | 2026-07-25 | 2417688 | Unpaid | 2026-07-10 | 200000 | Unpaid | 41 | 2417688 | 2441864.88 | 0.02 | 0.065 |  |  |  | Pcs | [8 empty] | Ready Awaiting Sailing | Cargo is ready, Vessel Bookin received ETD: 09-07-2026 | 10 | 1 | 1 |  | 3
Shafts/Ongoing/Import Status/Import Rem | QEN | Shafts | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 4340 Stepped QT | 283*386*283 | 735*460*895 | SL26-SAKS-0107 |  | Sakrand | 1 | Pcs | 1.227 | 1.227 | 2026-05-18 |  | 2026-08-10 | 12 | Dajin | China |  | 67519 |  | 2026-05-22 | BAH | LC |  | 12510 | ¥ | 41 |  | 15349.77 |  | 629340.57 |  |  |  | 7228.8 | YES | FOB |  |  |  |  | Sea |  |  |  | Karachi | 2026-06-26 | 2026-07-09 | 2026-07-30 |  |  |  | 2026-07-30 | 21 | EFS | [5 empty] | 0 | 2026-08-07 | 11.5714 | 0 | 3 |  |  |  | 2026-07-25 | 629340.57 | Unpaid | 2026-07-10 | 200000 | Unpaid | 41 | 629340.57 | 635633.9757 | 0.02 | 0.065 |  |  | 637 | Kg | [8 empty] | Ready Awaiting Sailing | Cargo is ready, Vessel Bookin received ETD: 09-07-2026 | 10 | 1 | 1 |  | 3
Shafts/Ongoing/Import Status/Import Rem | QEN | Shafts | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 4140 Stepped QT | 283*386*283 | 735*460*895 | SL26-HUDS-0046 |  | Seven Star | 1 | Pcs | 1.227 | 1.227 | 2026-05-18 |  | 2026-08-10 | 12 | Dajin | China |  | 67519 |  | 2026-05-22 | BAH | LC |  | 10900 | ¥ | 41 |  | 13374.3 |  | 548346.3 |  |  |  | 7228.8 | YES | FOB |  |  |  |  | Sea |  |  |  | Karachi | 2026-06-26 | 2026-07-09 | 2026-07-30 |  |  |  | 2026-07-30 | 21 | EFS | [5 empty] | 0 | 2026-08-07 | 11.5714 | 0 | 3 |  |  |  | 2026-07-25 | 548346.3 | Unpaid | 2026-07-10 | 200000 | Unpaid | 41 | 548346.3 | 553829.763 | 0.02 | 0.065 |  |  | 637 | Kg | [8 empty] | Ready Awaiting Sailing | Cargo is ready, Vessel Bookin received ETD: 09-07-2026 | 10 | 1 | 1 |  | 3
Shafts/Ongoing/Import Status/Import Rem | QEN | Shafts | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 42CrMo4 QT | 383 | 5640 | CL25-DCLH-0071 |  | DEWAN © | 1 | Pcs | 5.105 | 5.105 | 2026-05-19 |  | 2026-08-12 | 12.1429 | Dajin | China |  | 67519 |  | 2026-05-22 | BAH | LC |  | 7480 | ¥ | 41 |  | 38185.4 |  | 1565601.4 |  |  |  | 7228.8 | YES | FOB |  |  |  |  | Sea |  |  |  | Karachi | 2026-06-26 | 2026-07-09 | 2026-07-30 |  |  |  | 2026-07-30 | 21 | EFS | [5 empty] | 0 | 2026-08-07 | 11.4286 | 0 | 5 |  |  |  | 2026-07-25 | 1565601.4 | Unpaid | 2026-07-10 | 200000 | Unpaid | 41 | 1565601.4 | 1581257.414 | 0.02 | 0.065 |  |  |  | Kg | [8 empty] | Ready Awaiting Sailing | Cargo is ready, Vessel Bookin received ETD: 09-07-2026 | 10 | 1 | 1 |  | 3
Shafts/Ongoing/Import Status/Import Rem | QEN | Shafts | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 1045 | 383 | 4570 | SE26-SUCL-0053 |  | Sonkor(UCL) | 1 | Pcs | 4.134 | 4.134 | 2026-05-07 |  | 2026-07-30 | 12 | Qilu | China |  | 66744 |  | 2026-05-13 | BAH | LC |  | 7100 | ¥ | 41 |  | 29351.4 |  | 1203407.4 |  |  |  | 7214.109 |  | FOB |  |  |  |  | Sea |  |  |  | Karachi | 2026-06-17 | 2026-07-10 | 2026-08-01 |  |  |  | 2026-08-01 | 22 | EFS | [5 empty] | 0 | 2026-08-07 | 13.1429 | 0 | -8 |  |  |  | 2026-07-25 | 1203407.4 | Unpaid | 2026-07-10 | 200000 | Unpaid | 41 | 1203407.4 | 1215441.474 | 0.02 | 0.065 |  |  |  | Pcs | [8 empty] | Under Production | Production is about to complete. Forwarder nomination is awaited from Logistics. | 5 | 1 | 1 |  | 3
Shafts/Ongoing/Import Status/Import Rem | QEN | Shafts | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 4140 | OD835*ID407 | 780 | SL26-ESML-0166 |  | Etihad | 1 | Pcs | 2.558 | 2.558 | 2026-05-11 |  | 2026-08-03 | 12 | Qilu | China |  | 66744 |  | 2026-05-13 | BAH | LC |  | 10046.91 | ¥ | 41 |  | 25699.9958 |  | 1053699.827 |  |  |  | 7228.8 |  | FOB |  |  |  |  | Sea |  |  |  | Karachi | 2026-06-17 | 2026-07-10 | 2026-08-01 |  |  |  | 2026-08-01 | 22 | EFS | [5 empty] | 0 | 2026-08-07 | 12.5714 | 0 | -4 |  |  |  | 2026-07-25 | 1053699.827 | Unpaid | 2026-07-10 | 200000 | Unpaid | 41 | 1053699.827 | 1064236.8252 | 0.02 | 0.065 |  |  | 495 | Kg | [8 empty] | Under Production | Production is about to complete. Forwarder nomination is awaited from Logistics. | 5 | 1 | 1 |  | 3
Shafts/Ongoing/Import Status/Import Rem | QEN | Shafts | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 1045 | 621 | 5985 | SL26-HABL-0271 |  | Habib Sugar | 1 | Pcs | 14.234 | 14.234 | 2026-05-14 |  | 2026-08-08 | 12.2857 | Qilu | China |  | 66744 |  | 2026-05-13 | BAH | LC |  | 7650 | ¥ | 41 |  | 108890.1 |  | 4464494.1 |  |  |  | 7214.109 |  | FOB |  |  |  |  | Sea |  |  |  | Karachi | 2026-06-17 | 2026-07-10 | 2026-08-01 |  |  |  | 2026-08-01 | 22 | EFS | [5 empty] | 0 | 2026-08-07 | 12.1429 | 0 | 1 |  |  |  | 2026-07-25 | 4464494.1 | Unpaid | 2026-07-10 | 200000 | Unpaid | 41 | 4464494.1 | 4509139.041 | 0.02 | 0.065 |  |  | 368 | Kg | [8 empty] | Under Production | Production is about to complete. Forwarder nomination is awaited from Logistics. | 5 | 1 | 1 |  | 3
Shafts/Ongoing/Import Status/Import Rem | QEN | Shafts | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 1045 | 613 | 5390 | SL26-ASMZ-0063 |  | Alliance | 1 | Pcs | 12.491 | 12.491 | 2026-05-14 |  | 2026-08-08 | 12.2857 | Qilu | China |  | 66744 |  | 2026-05-13 | BAH | LC |  | 7650 | ¥ | 41 |  | 95556.15 |  | 3917802.15 |  |  |  | 7214.109 |  | FOB |  |  |  |  | Sea |  |  |  | Karachi | 2026-06-17 | 2026-07-10 | 2026-08-01 |  |  |  | 2026-08-01 | 22 | EFS | [5 empty] | 0 | 2026-08-07 | 12.1429 | 0 | 1 |  |  |  | 2026-07-25 | 3917802.15 | Unpaid | 2026-07-10 | 200000 | Unpaid | 41 | 3917802.15 | 3956980.1715 | 0.02 | 0.065 |  |  | 368 | Kg | [8 empty] | Under Production | Production is about to complete. Forwarder nomination is awaited from Logistics. | 5 | 1 | 1 |  | 3
Shafts/Ongoing/Import Status/Import Rem | QEN | Shafts | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 1045 | 613 | 5390 | QG26-QESS-0048 |  | Qadbros | 2 | Pcs | 12.491 | 24.982 | 2026-05-15 |  | 2026-08-07 | 12 | Qilu | China |  | 66744 |  | 2026-05-13 | BAH | LC |  | 7650 | ¥ | 41 |  | 191112.3 |  | 7835604.3 |  |  |  | 7214.109 |  | FOB |  |  |  |  | Sea |  |  |  | Karachi | 2026-06-17 | 2026-07-10 | 2026-08-01 |  |  |  | 2026-08-01 | 22 | EFS | [5 empty] | 0 | 2026-08-07 | 12 | 0 | 0 |  |  |  | 2026-07-25 | 7835604.3 | Unpaid | 2026-07-10 | 200000 | Unpaid | 41 | 7835604.3 | 7913960.343 | 0.02 | 0.065 |  |  | 368 | Kg | [8 empty] | Under Production | Finished forging but 2pcs failed UT test,repreparing raw material,expected to start forged this week,Production is about to complete. Forwarder nomination is awaited from Logistics. | 5 | 1 | 1 |  | 3
Shafts/Ongoing/Import Status/Import Rem | QEN | Shafts | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 1045 | 513 | 4550 | SL26-HAMS-0273 |  | Hamza Sugar | 1 | Pcs | 7.38 | 7.38 | 2026-04-28 |  | 2026-07-21 | 12 | Dajin | China |  | 65981 |  | 2026-05-06 | BAH | LC |  | 7100 | ¥ | 41 |  | 52398 |  | 2148318 |  |  |  | 7214.109 |  | FOB |  | VARANYA BHUM 012W |  | Portlink | Sea | HOSE26060372 |  | Shanghai | Karachi | 2026-06-10 | 2026-06-21 | 2026-07-15 |  |  |  | 2026-07-15 | 24 | EFS | [5 empty] | 0 | 2026-07-23 | 12.2857 | 0 | -2 |  |  |  | 2026-07-10 | 2148318 | Unpaid | 2026-07-10 | 200000 | Unpaid | 41 | 2148318 | 2169801.18 | 0.02 | 0.065 |  |  |  | Pcs | [8 empty] | In Transit | Vessel rollover from ETD: 18-06-2026 to 21-06-2026. | 10 | 1 | 1 | 4 | 3
Shafts/Ongoing/Import Status/Import Rem | QEN | Shafts | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 1045 | 558 | 4870 | SL26-CHMS-0170 |  | Chashma | 3 | Pcs | 9.35 | 28.05 | 2026-04-28 |  | 2026-07-21 | 12 | Dajin | China |  | 65981 |  | 2026-05-06 | BAH | LC |  | 7100 | ¥ | 41 |  | 199155 |  | 8165355 |  |  |  | 7214.109 |  | FOB |  | VARANYA BHUM 012W |  | Portlink | Sea | HOSE26060372 |  | Shanghai | Karachi | 2026-06-10 | 2026-06-21 | 2026-07-15 |  |  |  | 2026-07-15 | 24 | EFS | [5 empty] | 0 | 2026-07-23 | 12.2857 | 0 | -2 |  |  |  | 2026-07-10 | 8165355 | Unpaid | 2026-07-10 | 200000 | Unpaid | 41 | 8165355 | 8247008.55 | 0.02 | 0.065 |  |  |  | Pcs | [8 empty] | In Transit | Vessel rollover from ETD: 18-06-2026 to 21-06-2026. | 10 | 1 | 1 | 4 | 3
Shafts/Ongoing/Import Status/Import Rem | QEN | Shafts | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 1045 | 493 | 4255 | SL26-RANP-0041 |  | Ranipur | 1 | Pcs | 6.378 | 6.378 | 2026-05-04 |  | 2026-07-28 | 12.1429 | Dajin | China |  | 65981 |  | 2026-05-06 | BAH | LC |  | 7100 | ¥ | 41 |  | 45283.8 |  | 1856635.8 |  |  |  | 7214.109 |  | FOB |  | VARANYA BHUM 012W |  | Portlink | Sea | HOSE26060372 |  | Shanghai | Karachi | 2026-06-10 | 2026-06-21 | 2026-07-15 |  |  |  | 2026-07-15 | 24 | EFS | [5 empty] | 0 | 2026-07-23 | 11.4286 | 0 | 5 |  |  |  | 2026-07-10 | 1856635.8 | Unpaid | 2026-07-10 | 200000 | Unpaid | 41 | 1856635.8 | 1875202.158 | 0.02 | 0.065 |  |  |  | Pcs | [8 empty] | In Transit | Vessel rollover from ETD: 18-06-2026 to 21-06-2026. | 10 | 1 | 1 | 4 | 3
Shafts/Ongoing/Import Status/Import Rem | QEN | Shafts | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 1045 | 493 | 4255 | SL26-RANP-0043 |  | Ranipur | 1 | Pcs | 6.378 | 6.378 | 2026-05-04 |  | 2026-07-28 | 12.1429 | Dajin | China |  | 65981 |  | 2026-05-06 | BAH | LC |  | 7100 | ¥ | 41 |  | 45283.8 |  | 1856635.8 |  |  |  | 7214.109 |  | FOB |  | VARANYA BHUM 012W |  | Portlink | Sea | HOSE26060372 |  | Shanghai | Karachi | 2026-06-10 | 2026-06-21 | 2026-07-15 |  |  |  | 2026-07-15 | 24 | EFS | [5 empty] | 0 | 2026-07-23 | 11.4286 | 0 | 5 |  |  |  | 2026-07-10 | 1856635.8 | Unpaid | 2026-07-10 | 200000 | Unpaid | 41 | 1856635.8 | 1875202.158 | 0.02 | 0.065 |  |  |  | Pcs | [8 empty] | In Transit | Vessel rollover from ETD: 18-06-2026 to 21-06-2026. | 10 | 1 | 1 | 4 | 3
Shafts/Ongoing/Import Status/Import Rem | QEN | Shafts | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 1045 | 481 | 4389 | SL26-SANS-0068 |  | Sanghar | 1 | Pcs | 6.264 | 6.264 | 2026-04-24 |  | 2026-07-17 | 12 | Qilu | China |  | 65704 | B2 | 2026-05-05 | BAH | LC |  | 7150 | ¥ | 41 | 219031.35 | 44787.6 | 8980285.35 | 1836291.6 |  |  |  | 7214.109 |  | FOB |  |  |  |  | Sea |  |  |  | Karachi | 2026-06-16 | 2026-07-01 | 2026-07-23 |  |  |  | 2026-07-23 | 22 | [6 empty] | 0 | 2026-07-30 | 13.8571 | 0 | -13 |  |  |  | 2026-07-05 | 1836291.6 | Unpaid | 2026-07-10 | 200000 | Unpaid | 41 | 1836291.6 | 1854654.516 | 0.02 | 0.065 |  |  |  | Pcs | [8 empty] | In Transit | Shafts will be ready by 10th June, Vessel rollover from ETD: 21-06-26 to 25-06-26 & now 01-07-2026 | 5 |  | 1 |  | 3
Shafts/Ongoing/Import Status/Import Rem | QEN | Shafts | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 1045 | 538 | 4640 | SL26-AABM-0196 |  | AL Abbas | 2 | Pcs | 8.283 | 16.566 | 2026-04-24 |  | 2026-07-17 | 12 | Qilu | China |  | 65704 | B2 | 2026-05-05 | BAH | LC |  | 7150 | ¥ | 41 |  | 118446.9 |  | 4856322.9 |  |  |  | 7214.109 |  | FOB |  |  |  |  | Sea |  |  |  | Karachi | 2026-06-16 | 2026-07-01 | 2026-07-23 |  |  |  | 2026-07-23 | 22 | [6 empty] | 0 | 2026-07-30 | 13.8571 | 0 | -13 |  |  |  | 2026-07-05 | 4856322.9 | Unpaid | 2026-07-10 | 200000 | Unpaid | 41 | 4856322.9 | 4904886.129 | 0.02 | 0.065 |  |  |  | Pcs | [8 empty] | In Transit | Shafts will be ready by 10th June, Vessel rollover from ETD: 21-06-26 to 25-06-26 & now 01-07-2026 | 5 |  | 1 |  | 3
Shafts/Ongoing/Import Status/Import Rem | QEN | Shafts | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 1045 | 163 | 3950 | SE26-SNAK-0113 |  | Sonkor(Nakambala) | 2 | Pcs | 0.6472 | 1.2945 | 2026-04-24 |  | 2026-07-17 | 12 | Qilu | China |  | 65704 | B1 | 2026-05-05 | BAH | LC |  | 7150 | ¥ | 41 | 37308.7 | 9255.675 | 1529656.7 | 379482.675 |  |  |  | 7214.109 |  | FOB |  |  |  |  | Sea | HSHKHI2602501A |  | Shanghai | Karachi | 2026-06-09 | 2026-06-21 | 2026-07-15 |  |  |  | 2026-07-15 | 24 | [6 empty] | 0 | 2026-07-22 | 12.7143 | 0 | -5 |  |  |  | 2026-07-05 | 379482.675 | Unpaid | 2026-07-10 | 200000 | Unpaid | 41 | 379482.675 | 383277.5017 | 0.02 | 0.065 |  |  |  | Pcs | [8 empty] | In Transit | Vessel rollover from ETD: 17-06-2026 to 21-06-2026. | 5 |  | 1 | 4 | 3
Shafts/Ongoing/Import Status/Import Rem | QEN | Shafts | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 1045 | 163 | 4071 | SE26-SUBO-0063 |  | Sonkor(UBOMBO) | 2 | Pcs | 0.6671 | 1.3342 | 2026-04-24 |  | 2026-07-17 | 12 | Qilu | China |  | 65704 | B1 | 2026-05-05 | BAH | LC |  | 7150 | ¥ | 41 |  | 9539.53 |  | 391120.73 |  |  |  | 7214.109 |  | FOB |  |  |  |  | Sea | HSHKHI2602501A |  | Shanghai | Karachi | 2026-06-09 | 2026-06-21 | 2026-07-15 |  |  |  | 2026-07-15 | 24 | [6 empty] | 0 | 2026-07-22 | 12.7143 | 0 | -5 |  |  |  | 2026-07-05 | 391120.73 | Unpaid | 2026-07-10 | 200000 | Unpaid | 41 | 391120.73 | 395031.9373 | 0.02 | 0.065 |  |  |  | Pcs | [8 empty] | In Transit | Vessel rollover from ETD: 17-06-2026 to 21-06-2026. | 5 |  | 1 | 4 | 3
Shafts/Ongoing/Import Status/Import Rem | QEN | Shafts | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 1045 | 156 | 4510 | SL26-FATD-0460 |  | Fatima | 2 | Pcs | 0.6769 | 1.3538 | 2026-04-24 |  | 2026-07-17 | 12 | Qilu | China |  | 65704 | B1 | 2026-05-05 | BAH | LC |  | 7150 | ¥ | 41 |  | 9679.67 |  | 396866.47 |  |  |  | 7214.109 |  | FOB |  |  |  |  | Sea | HSHKHI2602501A |  | Shanghai | Karachi | 2026-06-09 | 2026-06-21 | 2026-07-15 |  |  |  | 2026-07-15 | 24 | [6 empty] | 0 | 2026-07-22 | 12.7143 | 0 | -5 |  |  |  | 2026-07-05 | 396866.47 | Unpaid | 2026-07-10 | 200000 | Unpaid | 41 | 396866.47 | 400835.1347 | 0.02 | 0.065 |  |  |  | Pcs | [8 empty] | In Transit | Vessel rollover from ETD: 17-06-2026 to 21-06-2026. | 5 |  | 1 | 4 | 3
Shafts/Ongoing/Import Status/Import Rem | QEN | Shafts | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 1045 | 163 | 3770 | SE26-SNAK-0113 |  | Sonkor(Nakambala) | 2 | Pcs | 0.6112 | 1.2355 | 2026-04-24 |  | 2026-07-17 | 12 | Qilu | China |  | 65704 | B1 | 2026-05-05 | BAH | LC |  | 7150 | ¥ | 41 |  | 8833.825 |  | 362186.825 |  |  |  | 7214.109 |  | FOB |  |  |  |  | Sea | HSHKHI2602501A |  | Shanghai | Karachi | 2026-06-09 | 2026-06-21 | 2026-07-15 |  |  |  | 2026-07-15 | 24 | [6 empty] | 0 | 2026-07-22 | 12.7143 | 0 | -5 |  |  |  | 2026-07-05 | 362186.825 | Unpaid | 2026-07-10 | 200000 | Unpaid | 41 | 362186.825 | 365808.6933 | 0.02 | 0.065 |  |  |  | Pcs | [8 empty] | In Transit | Vessel rollover from ETD: 17-06-2026 to 21-06-2026. | 5 |  | 1 | 4 | 3
Shafts/Ongoing/Import Status/Import Rem | QEN | Shafts | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 4340(QT) | 410 | 4680 | CE26-TSLU-0001 | CE26-MO-0162 | Texas Shredder | 1 | Pcs | 4.8519 | 4.8519 | 2026-04-27 |  | 2026-07-20 | 12 | Qilu | China |  | 65704 | B2 | 2026-05-05 | BAH | LC |  | 11500 | ¥ | 41 | 219031.35 | 55796.85 | 8980285.35 | 2287670.85 |  |  |  | 7228.4 | YES | FOB |  |  |  |  | Sea |  |  |  | Karachi | 2026-06-16 | 2026-07-01 | 2026-07-23 |  |  |  | 2026-07-23 | 22 | [6 empty] | 0 | 2026-07-30 | 13.4286 | 0 | -10 |  |  |  | 2026-07-05 | 2287670.85 | Unpaid | 2026-07-10 | 200000 | Unpaid | 41 | 2287670.85 | 2310547.5585 | 0.02 | 0.065 |  |  |  | Pcs | [8 empty] | In Transit | Shafts will be ready by 10th June, Vessel rollover from ETD: 21-06-26 to 25-06-26 & now 01-07-2026 | 5 |  | 1 |  | 3
Shafts/Ongoing/Import Status/Import Rem | QBL-II | Scraps | Store |  | 19969-60 |  | Cast Iron Scrap | Oversized | [5 empty] | 81.098 | Ton | [6 empty] | Prime Commodities Fze | UAE |  | 65543 | B2 | 2026-05-05 | BAH | LC |  | 440 | $ | 278.4 | 35683.12 | 35683.12 | 9934180.608 | 9934180.608 |  |  |  | 7204.109 | NO | CFR Karachi |  |  |  |  | Sea |  |  |  | Karachi |  | 2026-05-15 | 2026-07-13 |  |  |  | 2026-07-13 | 59 | MHQ | [5 empty] | 0 | 2026-07-23 | 0 | 0 | 0 |  |  |  | 2026-06-18 | 9934180.608 | Paid | 2026-02-05 | 3762570.9053 | Unpaid | 278.4 | 9934180.608 | 10033522.4141 | 0.31 | 0.065 |  |  | 152 | Kg | [8 empty] | In Transit |  | 7 | 3 | 1 |  | 4
Shafts/Ongoing/Import Status/Import Rem | QBL-II | Scraps | Store |  | 19969-60 |  | Cast Iron Scrap | Oversized | [5 empty] | 68.83 | Ton | [6 empty] | Prime Commodities Fze | UAE |  | 65543 | B1 | 2026-05-05 | BAH | LC |  | 440 | $ | 279.35 | 30285.2 | 30285.2 | 8460170.62 | 8460170.62 |  |  |  | 7204.109 | NO | CFR Karachi |  |  |  |  | Sea |  |  |  | Karachi |  | 2026-05-26 | 2026-07-09 | 2026-07-11 |  |  | 2026-07-11 | 46 | MHQ | [5 empty] | 0 | 2026-07-21 | 0 | 0 | 0 |  |  |  | 2026-06-23 | 8460170.62 | Paid | 2026-02-05 | 3204289.6223 | Unpaid | 279.35 | 8460170.62 | 8544772.3262 | 0.31 | 0.065 |  |  | 152 | Kg | [8 empty] | In Transit |  | 7 | 3 | 1 |  | 4
Shafts/Ongoing/Import Status/Import Rem | QBL-II | Scraps | Store |  | 19969-60 |  | Cast Iron Scrap | Oversized | [5 empty] | 20.717 | Ton | [6 empty] | Prime Commodities Fze | UAE |  | 65543 | B3 | 2026-05-05 | BAH | LC |  | 440 | $ | 282 | 9115.48 | 9115.48 | 2570565.36 | 2570565.36 |  |  |  | 7204.109 | NO | CFR Karachi |  |  |  |  | Sea |  |  |  | Karachi |  | 2026-06-29 | 2026-08-25 |  |  |  | 2026-08-25 | 57 | MHQ | [5 empty] | 0 | 2026-09-04 | 0 | 0 | 0 |  |  |  | 2026-05-30 | 2570565.36 | Unpaid | 2026-02-05 | 973601.6301 | Unpaid | 282 | 2570565.36 | 2596271.0136 | 0.31 | 0.065 |  |  | 152 | Kg | [8 empty] | In Transit |  | 7 | 3 | 1 |  | 4
Shafts/Ongoing/Import Status/Import Rem | QEN | Engineering Item | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 1045 | 663 | 5860 | SL26-SWSM-0121 |  | SW Sugar | 1 | Pcs | 15.893 | 15.893 | 2026-04-14 |  | 2026-07-07 | 12 | Dajin | China |  | 64670 |  | 2026-04-17 | BAH | LC |  | 7600 | ¥ | 41 | 372163.7 | 120786.8 | 15258711.6984 | 4952258.8 |  |  |  | 7214.109 | YES | FOB |  | OOCL LE HARVE | OOCL | MIYAM SHIPPING | Sea | KXSE28060100002 |  | Shanghai | Karachi | 2026-05-22 | 2026-06-15 | 2026-07-02 | 2026-07-03 |  |  | 2026-07-03 | 18 | [6 empty] | 0 | 2026-07-10 | 12.4286 | 0 | -3 |  |  |  | 2026-05-30 | 4952258.8 | Unpaid | 2026-05-30 | 200000 | Unpaid | 41 | 4952258.8 | 5001781.388 | 0.02 | 0.065 |  |  |  | Pcs | [8 empty] | In Transit | Vessel rollover from ETD: 01-06-2026 to 07-06-2026 and now 13-06-2026 and now 15-06-2026. | 10 |  | 1 | 4 | 3
Shafts/Ongoing/Import Status/Import Rem | QEN | Engineering Item | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 1045 | 631 | 6150 | SE26-MAGZ-0046 |  | MAYAGUEZ S.A | 1 | Pcs | 15.11 | 15.11 | 2026-04-14 |  | 2026-07-07 | 12 | Dajin | China |  | 64670 |  | 2026-04-17 | BAH | LC |  | 7600 | ¥ | 41 |  | 114836 |  | 4708276 |  |  |  | 7214.109 | YES | FOB |  | OOCL LE HARVE | OOCL | MIYAM SHIPPING | Sea | KXSE28060100002 |  | Shanghai | Karachi | 2026-05-22 | 2026-06-15 | 2026-07-02 | 2026-07-03 |  |  | 2026-07-03 | 18 | [6 empty] | 0 | 2026-07-10 | 12.4286 | 0 | -3 |  |  |  | 2026-05-30 | 4708276 | Unpaid | 2026-05-30 | 200000 | Unpaid | 41 | 4708276 | 4755358.76 | 0.02 | 0.065 |  |  |  | Pcs | [8 empty] | In Transit | Vessel rollover from ETD: 01-06-2026 to 07-06-2026 and now 13-06-2026 and now 15-06-2026. | 10 |  | 1 | 4 | 3
Shafts/Ongoing/Import Status/Import Rem | QEN | Engineering Item | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 1045 | 533 | 4693 | SE26-MAGZ-0047 |  | MAYAGUEZ S.A | 1 | Pcs | 8.226 | 8.226 | 2026-04-14 |  | 2026-07-07 | 12 | Dajin | China |  | 64670 |  | 2026-04-17 | BAH | LC |  | 7100 | ¥ | 41 |  | 58404.6 |  | 2394588.6 |  |  |  | 7214.109 | YES | FOB |  | OOCL LE HARVE | OOCL | MIYAM SHIPPING | Sea | KXSE28060100002 |  | Shanghai | Karachi | 2026-05-22 | 2026-06-15 | 2026-07-02 | 2026-07-03 |  |  | 2026-07-03 | 18 | [6 empty] | 0 | 2026-07-10 | 12.4286 | 0 | -3 |  |  |  | 2026-05-30 | 2394588.6 | Unpaid | 2026-05-30 | 200000 | Unpaid | 41 | 2394588.6 | 2418534.486 | 0.02 | 0.065 |  |  |  | Pcs | [8 empty] | In Transit | Vessel rollover from ETD: 01-06-2026 to 07-06-2026 and now 13-06-2026 and now 15-06-2026. | 10 |  | 1 | 4 | 3
Shafts/Ongoing/Import Status/Import Rem | QEN | Engineering Item | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 1045 | 560 | 4287 | SE26-LULS-0269 |  | Lula Sugar | 1 | Pcs | 8.295 | 8.295 | 2026-04-17 |  | 2026-07-10 | 12 | Dajin | China |  | 64670 |  | 2026-04-17 | BAH | LC |  | 7100 | ¥ | 41 |  | 58894.5 |  | 2414674.5 |  |  |  | 7214.109 | YES | FOB |  | OOCL LE HARVE | OOCL | MIYAM SHIPPING | Sea | KXSE28060100002 |  | Shanghai | Karachi | 2026-05-22 | 2026-06-15 | 2026-07-02 | 2026-07-03 |  |  | 2026-07-03 | 18 | [6 empty] | 0 | 2026-07-10 | 12 | 0 | 0 |  |  |  | 2026-05-30 | 2414674.5 | Unpaid | 2026-05-30 | 200000 | Unpaid | 41 | 2414674.5 | 2438821.245 | 0.02 | 0.065 |  |  |  | Pcs | [8 empty] | In Transit | Vessel rollover from ETD: 01-06-2026 to 07-06-2026 and now 13-06-2026 and now 15-06-2026. | 10 |  | 1 | 4 | 3
Shafts/Ongoing/Import Status/Import Rem | QEN | Engineering Item | Engg. |  | TMPNL0051 |  | Forged Steel Hollow Drill Bars | EN24 | OD 653, ID 283 | 680 | CE26-AFVP-0002 | CE26-MO-0160 | AFRISAM | 1 | Pcs | 1.452 | 1.452 | 2026-04-10 |  | 2026-07-05 | 12.2857 | Dajin | China |  | 64670 |  | 2026-04-17 | BAH | LC |  | 12150 | ¥ | 41 |  | 17641.8 |  | 723313.8 |  |  |  | 7228.8 | YES | FOB |  | OOCL LE HARVE | OOCL | MIYAM SHIPPING | Sea | KXSE28060100002 |  | Shanghai | Karachi | 2026-05-22 | 2026-06-15 | 2026-07-02 | 2026-07-03 |  |  | 2026-07-03 | 18 | [6 empty] | 0 | 2026-07-10 | 13 | 0 | -5 |  |  |  | 2026-05-30 | 723313.8 | Unpaid | 2026-05-30 | 200000 | Unpaid | 41 | 723313.8 | 730546.938 | 0.02 | 0.065 |  |  | 647 | Kgs | [8 empty] | In Transit | Vessel rollover from ETD: 01-06-2026 to 07-06-2026 and now 13-06-2026 and now 15-06-2026. | 10 |  | 1 | 4 | 3
Shafts/Ongoing/Import Status/Import Rem | QEN | Engineering Item | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | EN24 | 150*150 | 150 | CE26-AFVP-0002 | CE26-MO-0160 | AFRISAM | 1 | Pcs | 0.026 | 0.026 | 2026-04-10 |  | 2026-07-05 | 12.2857 | Dajin | China |  | 64670 |  | 2026-04-17 | BAH | LC |  | 61538.46 | ¥ | 41 |  | 1600 |  | 65599.9984 |  |  |  | 7228.4 | YES | FOB |  | OOCL LE HARVE | OOCL | MIYAM SHIPPING | Sea | KXSE28060100002 |  | Shanghai | Karachi | 2026-05-22 | 2026-06-15 | 2026-07-02 | 2026-07-03 |  |  | 2026-07-03 | 18 | [6 empty] | 0 | 2026-07-10 | 13 | 0 | -5 |  |  |  | 2026-05-30 | 65599.9984 | Unpaid | 2026-05-30 | 200000 | Unpaid | 41 | 65599.9984 | 66255.9983 | 0.02 | 0.065 |  |  |  | Pcs | [8 empty] | In Transit | Vessel rollover from ETD: 01-06-2026 to 07-06-2026 and now 13-06-2026 and now 15-06-2026. | 10 |  | 1 | 4 | 3
Arrived | QBL-II |  | Store |  | TMPNL0053 |  | SCRAP OF STAINLESS STEEL. (MAGNETIC) | [6 empty] | 105.933 | Ton | [5 empty] | 0 |  |  |  | 64195 |  | 2025-04-07 | [5 empty] | 283.8 |  | 84746.4 |  | 24051028.32 | [11 empty] | 252402049 | [12 empty] | 2025-07-09 | KPPI-HC-1760 |  |  |  |  | 2025-07-22 | 0 | 0 | 0 | [17 empty] | Ton | [8 empty] | Arrived at Works | On time |  |  |  |  | 4
Shafts/Ongoing/Import Status/Import Rem | QCL | Foundry Material | Store |  | 26287-60 |  | Resin | A-85 | [5 empty] | 48000 | Kgs |  |  | 2026-03-25 |  | 2026-06-25 | 13.1429 | Cukurova | Turkey |  | 2715 |  | 2026-04-15 | HMB | LC |  | 0.645 | € | 325.45 | 30960 | 30960 | 10075932 | 10075932 |  |  |  | 3824.1 |  | CFR Karachi |  | NAVIOS AZURE | CMA CGM | CMA CGM - KHI | Sea | ISB1962187 |  | Aliaga | Karachi |  | 2026-05-09 | 2026-07-15 | 2026-07-27 | 2026-07-29 |  | 2026-07-29 | 81 | EFS | [5 empty] | 0 | 2026-08-08 |  | 0 | -44 |  |  |  | 2026-05-25 | 10075932 | Unpaid | 2026-04-30 | 3002123.9394 | Unpaid | 325.45 | 10075932 | 10176691.32 | 0.23 | 0.065 |  |  | 235 | Kgs | [8 empty] | In Transit | Shipment booking has been received with ETD 09-05-26. However, the shipment has been unexpectedly delayed due to the current Red Sea issue, which has increased the transit time from 45 days to approximately 70 days. Additionally, the booking was received by the supplier from the shipping line after a delay of 18 days. | 11 | 1 | 1 | 9 | 2
Shafts/Ongoing/Import Status/Import Rem | QEN | Shafts | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 4140 | 418 | 5000 | SL26-FATD-0462 |  | FATIMA SUGAR | 1 | Ton | 5.388 | 5.388 | 2026-04-03 |  | 2026-06-30 | 12.5714 | Qilu | China |  | 63751 | B2 | 2026-04-10 | BAH | LC |  | 7900 | ¥ | 40 |  | 42565.2 |  | 1702608 |  |  |  | 7228.4 |  | FOB Shanghai |  |  |  |  | Sea | HSHKHI2602501B |  | Shanghai | Karachi | 2026-06-10 | 2026-06-21 | 2026-07-15 |  |  |  | 2026-07-15 | 24 | EFS | [5 empty] | 0 | 2026-07-25 | 16.1429 | 0 | -25 |  |  |  | 2026-06-05 | 1702608 | Unpaid | 2026-07-14 | 146168.8968 | Unpaid | 40 | 1702608 | 1719634.08 | 0.02 | 0.065 |  |  |  | Kg | [8 empty] | In Transit | 1st production finish date was 15-05-2026, Reproduction, Preparing Raw Material, Vessel booking received Vessel rollover from ETD: 17-06-2026 to 21-06-2026. | 5 | 1 | 1 | 4 | 3
Shafts/Ongoing/Import Status/Import Rem | QEN | Shafts | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 4140 | 363 | 4590 | SL26-FATD-0463 |  | FATIMA SUGAR | 1 | Ton | 3.73 | 3.73 | 2026-04-03 |  | 2026-06-30 | 12.5714 | Qilu | China |  | 63751 | B2 | 2026-04-10 | BAH | LC |  | 7900 | ¥ | 40 |  | 29467 |  | 1178680 |  |  |  | 7228.4 |  | FOB Shanghai |  |  |  |  | Sea | HSHKHI2602501B |  | Shanghai | Karachi | 2026-06-10 | 2026-06-21 | 2026-07-15 |  |  |  | 2026-07-15 | 24 | EFS | [5 empty] | 0 | 2026-07-25 | 16.1429 | 0 | -25 |  |  |  | 2026-06-05 | 1178680 | Unpaid | 2026-07-14 | 101189.678 | Unpaid | 40 | 1178680 | 1190466.8 | 0.02 | 0.065 |  |  |  | Kg | [8 empty] | In Transit | 1st production finish date was 15-05-2026, Reproduction, Preparing Raw Material, Vessel booking received Vessel rollover from ETD: 17-06-2026 to 21-06-2026. | 5 | 1 | 1 | 4 | 3
Shafts/Ongoing/Import Status/Import Rem | QEN | Shafts | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 1045 | 743 | 6500 | SL26-JKS2-0419 |  | JK-II | 3 | Ton | 22.1303 | 66.391 | 2026-04-03 |  | 2026-06-30 | 12.5714 | Qilu | China |  | 63751 | B1 | 2026-04-10 | BAH | LC |  | 7650 | ¥ | 40 | 1114888.05 | 507891.15 | 44595522 | 20315646 |  |  |  | 7214.109 | YES | FOB Shanghai |  |  |  |  | Sea |  |  |  | Karachi | 2026-05-20 | 2026-06-08 | 2026-07-03 | 2026-07-05 | 2026-07-08 |  | 2026-07-08 | 30 | EFS | [5 empty] | 0 | 2026-07-18 | 15.1429 | 0 | -18 |  |  |  | 2026-06-05 | 20315646 | Unpaid | 2026-07-05 | 1744098.2091 | Unpaid | 40 | 20315646 | 20518802.46 | 0.02 | 0.065 |  |  |  | Kg | [8 empty] | In Transit | Production Completed, vessel booked ETD 30-05-26 rollover to 08-06-2026, ETA = 02-07-2026 rollover to05-07-2026 and now 08-07-2026 | 5 | 1 | 1 |  | 3
Shafts/Ongoing/Import Status/Import Rem | QEN | Shafts | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 1045 | 553 | 5705 | SL26-JKS2-0419 |  | JK-II | 1 | Ton | 10.76 | 10.76 | 2026-04-03 |  | 2026-06-30 | 12.5714 | Qilu | China |  | 63751 | B1 | 2026-04-10 | BAH | LC |  | 7150 | ¥ | 40 |  | 76934 |  | 3077360 |  |  |  | 7214.109 | YES | FOB Shanghai |  |  |  |  | Sea |  |  |  | Karachi | 2026-05-20 | 2026-06-08 | 2026-07-03 | 2026-07-05 | 2026-07-08 |  | 2026-07-08 | 30 | EFS | [5 empty] | 0 | 2026-07-18 | 15.1429 | 0 | -18 |  |  |  | 2026-06-05 | 3077360 | Unpaid | 2026-07-05 | 264191.356 | Unpaid | 40 | 3077360 | 3108133.6 | 0.02 | 0.065 |  |  |  | Kg | [8 empty] | In Transit | Production Completed, vessel booked ETD 30-05-26 rollover to 08-06-2026, ETA = 02-07-2026 rollover to05-07-2026 and now 08-07-2026 | 5 | 1 | 1 |  | 3
Shafts/Ongoing/Import Status/Import Rem | QEN | Shafts | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 1045 | 733 | 6370 | SL26-FATD-0460 |  | FATIMA SUGAR | 3 | Ton | 21.11 | 63.33 | 2026-04-03 |  | 2026-06-30 | 12.5714 | Qilu | China |  | 63751 | B1 | 2026-04-10 | BAH | LC |  | 7650 | ¥ | 40 |  | 484474.5 |  | 19378980 |  |  |  | 7214.109 | YES | FOB Shanghai |  |  |  |  | Sea |  |  |  | Karachi | 2026-05-20 | 2026-06-08 | 2026-07-03 | 2026-07-05 | 2026-07-08 |  | 2026-07-08 | 30 | EFS | [5 empty] | 0 | 2026-07-18 | 15.1429 | 0 | -18 |  |  |  | 2026-06-05 | 19378980 | Unpaid | 2026-07-05 | 1663685.433 | Unpaid | 40 | 19378980 | 19572769.8 | 0.02 | 0.065 |  |  |  | Kg | [8 empty] | In Transit | Production Completed, vessel booked ETD 30-05-26 rollover to 08-06-2026, ETA = 02-07-2026 rollover to05-07-2026 and now 08-07-2026 | 5 | 1 | 1 |  | 3
Shafts/Ongoing/Import Status/Import Rem | QEN | Shafts | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 1045 | 453 | 5030 | SL26-FATD-0460 |  | FATIMA SUGAR | 1 | Ton | 6.376 | 6.376 | 2026-04-03 |  | 2026-06-30 | 12.5714 | Qilu | China |  | 63751 | B1 | 2026-04-10 | BAH | LC |  | 7150 | ¥ | 40 |  | 45588.4 |  | 1823536 |  |  |  | 7214.109 | YES | FOB Shanghai |  |  |  |  | Sea |  |  |  | Karachi | 2026-05-20 | 2026-06-08 | 2026-07-03 | 2026-07-05 | 2026-07-08 |  | 2026-07-08 | 30 | EFS | [5 empty] | 0 | 2026-07-18 | 15.1429 | 0 | -18 |  |  |  | 2026-06-05 | 1823536 | Unpaid | 2026-07-05 | 156550.5656 | Unpaid | 40 | 1823536 | 1841771.36 | 0.02 | 0.065 |  |  |  | Kg | [8 empty] | In Transit | Production Completed, vessel booked ETD 30-05-26 rollover to 08-06-2026, ETA = 02-07-2026 rollover to05-07-2026 and now 08-07-2026 | 5 | 1 | 1 |  | 3
Arrived | QCL |  |  |  | TMPNL0060 |  | MANGANESE STEEL SCRAP IRON AND STEEL RE ROLLABLE SCRAP | [6 empty] | 105.868 | Tons | [5 empty] | 0 |  |  |  | 63189 |  | 2025-03-20 | [5 empty] | 281.3 |  | 50464.32 |  | 14195613.216 | [11 empty] | MEDUVC775735 | [12 empty] | 2025-07-16 | KPPI-HC-3035 |  | 2025-07-19 |  |  | 2025-07-21 | 0 | 0 | 0 | [17 empty] | Tons | [8 empty] | Arrived at Works | On time |  |  |  |  | 2
Shafts/Ongoing/Import Status/Import Rem | QCL | Foundry Material | Store |  | 26487-60 |  | Resin | A-85 | [5 empty] | 4800 | Kgs |  |  | 2026-03-25 |  | 2026-07-25 | 17.4286 | Cukurova | Turkey |  | 2716 |  | 2026-04-15 | HMB | LC |  | 0.645 | € | 322 | 26694 | 3096 | 8595468 | 996912 |  |  |  | 3824.1 |  | CFR Karachi |  | NAVIOS AZURE | CMA CGM | CMA CGM - KHI | Sea | ISB1974090 |  | Aliaga | Karachi |  | 2026-05-09 | 2026-07-15 | 2026-07-27 | 2026-07-29 |  | 2026-07-29 | 81 | EFS | [5 empty] | 0 | 2026-08-08 |  | 0 | -14 |  |  |  | 2026-05-25 | 996912 | Unpaid | 2026-04-30 | 297029.9304 | Unpaid | 322 | 996912 | 1006881.12 | 0.23 | 0.065 |  |  | 235 | Kgs | [8 empty] | In Transit | Shipment booking has been received with ETD 09-05-26. However, the shipment has been unexpectedly delayed due to the current Red Sea issue, which has increased the transit time from 45 days to approximately 70 days. Additionally, the booking was received by the supplier from the shipping line after a delay of 18 days. | 11 | 1 | 1 | 9 | 2
Shafts/Ongoing/Import Status/Import Rem | QBL-II | Foundry Material | Store |  | 26382-60 |  | Hardner | AKS-1075/HQG-60 | [5 empty] | 3000 | Kgs |  |  | 2026-02-25 |  | 2026-05-25 | 12.7143 | Cukurova | Turkey |  | 2716 |  | 2026-04-15 | HMB | LC |  | 1.42 | € | 322 |  | 4260 |  | 1371720 |  |  |  | 3824.1 |  | CFR Karachi |  | NAVIOS AZURE | CMA CGM | CMA CGM - KHI | Sea | ISB1974090 |  | Aliaga | Karachi |  | 2026-05-09 | 2026-07-15 | 2026-07-27 | 2026-07-29 |  | 2026-07-29 | 81 | EFS | [5 empty] | 0 | 2026-08-08 |  | 0 | -75 |  |  |  | 2026-05-25 | 1371720 | Unpaid | 2026-04-30 | 408703.974 | Unpaid | 322 | 1371720 | 1385437.2 | 0.23 | 0.065 |  |  | 499 | Kgs | [8 empty] | In Transit | Shipment booking has been received with ETD 09-05-26. However, the shipment has been unexpectedly delayed due to the current Red Sea issue, which has increased the transit time from 45 days to approximately 70 days. Additionally, the booking was received by the supplier from the shipping line after a delay of 18 days. | 11 | 1 | 1 | 9 | 4
Shafts/Ongoing/Import Status/Import Rem | QCL | Foundry Material | Store |  | 26382-60 |  | Hardner | AKS-1075/HQG-60 | [5 empty] | 3900 | Kgs |  |  | 2026-03-25 |  | 2026-06-25 | 13.1429 | Cukurova | Turkey |  | 2716 |  | 2026-04-15 | HMB | LC |  | 1.42 | € | 322 |  | 5538 |  | 1783236 |  |  |  | 3824.1 |  | CFR Karachi |  | NAVIOS AZURE | CMA CGM | CMA CGM - KHI | Sea | ISB1974090 |  | Aliaga | Karachi |  | 2026-05-09 | 2026-07-15 | 2026-07-27 | 2026-07-29 |  | 2026-07-29 | 81 | EFS | [5 empty] | 0 | 2026-08-08 |  | 0 | -44 |  |  |  | 2026-05-25 | 1783236 | Unpaid | 2026-04-30 | 531315.1662 | Unpaid | 322 | 1783236 | 1801068.36 | 0.23 | 0.065 |  |  | 499 | Kgs | [8 empty] | In Transit | Shipment booking has been received with ETD 09-05-26. However, the shipment has been unexpectedly delayed due to the current Red Sea issue, which has increased the transit time from 45 days to approximately 70 days. Additionally, the booking was received by the supplier from the shipping line after a delay of 18 days. | 11 | 1 | 1 | 9 | 2
Shafts/Ongoing/Import Status/Import Rem | QCL | Foundry Material | Store |  | 26838-60 |  | Hardner | AS-09/HQG-20 | [5 empty] | 11500 | Kgs |  |  | 2026-03-25 |  | 2026-06-25 | 13.1429 | Cukurova | Turkey |  | 2716 |  | 2026-04-15 | HMB | LC |  | 1.2 | € | 322 |  | 13800 |  | 4443600 |  |  |  | 3824.1 |  | CFR Karachi |  | NAVIOS AZURE | CMA CGM | CMA CGM - KHI | Sea | ISB1974090 |  | Aliaga | Karachi |  | 2026-05-09 | 2026-07-15 | 2026-07-27 | 2026-07-29 |  | 2026-07-29 | 81 | EFS | [5 empty] | 0 | 2026-08-08 |  | 0 | -44 |  |  |  | 2026-05-25 | 4443600 | Unpaid | 2026-04-30 | 1323970.62 | Unpaid | 322 | 4443600 | 4488036 | 0.23 | 0.065 |  |  | 423 | Kgs | [8 empty] | In Transit | Shipment booking has been received with ETD 09-05-26. However, the shipment has been unexpectedly delayed due to the current Red Sea issue, which has increased the transit time from 45 days to approximately 70 days. Additionally, the booking was received by the supplier from the shipping line after a delay of 18 days. | 11 | 1 | 1 | 9 | 2
Arrived | QBl-II | Foundry Material | Store |  | 26487-60 |  | Zircon Coating | CK-780/RISA-5100 | [5 empty] | 3240 | Kg |  |  | 2026-06-12 |  | 2026-07-06 |  | Cukurova | Turkey |  | 4041 |  | 2026-06-16 | HMB | Advance |  | 1.95 | € | 322.4 |  | 6318 |  | 2036923.2 |  |  |  | 3824.1 |  | FCA |  |  |  |  | Air |  |  |  | Lahore |  | 2026-06-19 | 2026-06-21 |  |  |  | 2026-06-21 | 2 | EFS | [5 empty] | 0 | 2026-06-22 |  | 0 | 14 | 2026-06-16 | 2036923.2 | Paid |  |  |  | 2026-06-22 | 200000 | Paid | 322.4 | 2036923.2 | 2057292.432 | 0.23 | 0.065 |  |  |  | Kg | [8 empty] | Arrived at Works | Material is ready, Forwarder nomination is awaited. | 11 | 1 | 3 |  | 4
Shafts/Ongoing/Import Status/Import Rem | QBL-II | Foundry Material | Store |  | 2847-60 |  | Slag Remover | [6 empty] | 5000 | Kg |  |  | 2026-05-20 |  | 2026-08-20 |  | Cukurova | Turkey |  | 4047 |  | 2026-06-16 | HMB | Advance |  | 0.17 | € | 322.4 | 850 | 850 | 274040 | 274040 |  |  |  | 2530.1 |  | FOB |  |  |  |  | Sea |  |  |  | Karachi | [14 empty] | 0 |  |  | 0 | 0 | 2026-06-16 | 274040 | Paid |  |  |  |  | 81650.218 | Unpaid | 322.4 | 274040 | 276780.4 | 0.23 | 0.065 |  |  | 211 | Kg | [8 empty] | Ready Awaiting Sailing | Material is ready, Forwarder nomination is awaited. | 11 |  | 1 |  | 4
Shafts/Ongoing/Import Status/Import Rem | QEN | Shafts | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 1045 | 536 | 4815 | SE26-NSEA-0051 |  | Ingenio San Antonio | 1 | Ton | 8.54 | 8.54 | 2026-03-19 |  | 2026-06-11 | 12 | Dajin | China | Jining | 62767 |  | 2026-03-31 | BAH | LC |  | 7100 | ¥ | 40 | 396918 | 60634 | 15876720 | 2425360 |  |  |  | 7214.109 | YES | FOB Shanghai |  | OOCL LE HARVE | OOCL | MIYAM SHIPPING | Sea | KXSE2606010003 |  |  | Karachi | 2026-05-17 | 2026-06-15 | 2026-07-02 | 2026-07-03 |  |  | 2026-07-03 | 18 | [6 empty] | 0 | 2026-07-10 | 16.1429 | 0 | -29 |  |  |  | 2026-06-05 | 2425360 | Unpaid | 2026-07-02 | 208217.156 | Unpaid | 40 | 2425360 | 2449613.6 | 0.02 | 0.065 |  |  | 361 | Kg | [8 empty] | In Transit | Vessel rollover from ETD: 01-06-2026 to 07-06-2026 and now 13-06-2026 and now 15-06-2026. | 10 |  | 1 |  | 3
Shafts/Ongoing/Import Status/Import Rem | QEN | Shafts | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 1045 | 638 | 5510 | SE26-SUBO-0063 |  | Sonkor(UBOMBO) | 3 | Ton | 13.84 | 41.52 | 2026-04-03 |  | 2026-06-30 | 12.5714 | Dajin | China | Jining | 62767 |  | 2026-03-31 | BAH | LC |  | 7600 | ¥ | 40 |  | 315552 |  | 12622080 |  |  |  | 7214.109 | YES | FOB Shanghai |  | OOCL LE HARVE | OOCL | MIYAM SHIPPING | Sea | KXSE2606010003 |  |  | Karachi | 2026-05-17 | 2026-06-15 | 2026-07-02 | 2026-07-03 |  |  | 2026-07-03 | 18 | [6 empty] | 0 | 2026-07-10 | 14 | 0 | -10 |  |  |  | 2026-06-05 | 12622080 | Unpaid | 2026-07-02 | 1083605.568 | Unpaid | 40 | 12622080 | 12748300.8 | 0.02 | 0.065 |  |  | 361 | Kg | [8 empty] | In Transit | Vessel rollover from ETD: 01-06-2026 to 07-06-2026 and now 13-06-2026 and now 15-06-2026. | 10 |  | 1 |  | 3
Shafts/Ongoing/Import Status/Import Rem | QEN | Shafts | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 1045 | 333 | 4260 | SE26-SUBO-0063 |  | Sonkor(UBOMBO) | 1 | Ton | 2.92 | 2.92 | 2026-04-03 |  | 2026-06-30 | 12.5714 | Dajin | China | Jining | 62767 |  | 2026-03-31 | BAH | LC |  | 7100 | ¥ | 40 |  | 20732 |  | 829280 |  |  |  | 7214.109 | YES | FOB Shanghai |  | OOCL LE HARVE | OOCL | MIYAM SHIPPING | Sea | KXSE2606010003 |  |  | Karachi | 2026-05-17 | 2026-06-15 | 2026-07-02 | 2026-07-03 |  |  | 2026-07-03 | 18 | [6 empty] | 0 | 2026-07-10 | 14 | 0 | -10 |  |  |  | 2026-06-05 | 829280 | Unpaid | 2026-07-02 | 71193.688 | Unpaid | 40 | 829280 | 837572.8 | 0.02 | 0.065 |  |  | 361 | Kg | [8 empty] | In Transit | Vessel rollover from ETD: 01-06-2026 to 07-06-2026 and now 13-06-2026 and now 15-06-2026. | 10 |  | 1 |  | 3
Arrived | QCL |  |  |  | 19969-60 |  | SCRAP OF CAST IRON | [6 empty] | 122.469 | Tons | [5 empty] | 0 |  |  |  | 61712 |  | 2025-03-24 |  | 100%LC |  |  |  | 281.1 |  | 47762.91 |  | 13426154.001 | [11 empty] | HLCUBSC2503AVLB8 | [12 empty] | 2025-05-30 | KPPI-HC-65310 |  | 2025-05-31 |  |  | 2025-06-05 | 0 | 0 | 0 | [17 empty] | Tons | [8 empty] | Arrived at Works | On time |  |  |  |  | 2
Arrived | QCL |  |  |  | 19969-60 |  | SCRAP OF CAST IRON | [6 empty] | 21.25 | Tons | [5 empty] | 0 |  |  |  | 61712 |  | 2025-03-24 |  | 100%LC |  |  |  | 282.3 |  | 8288.28 |  | 2339781.444 | [11 empty] | HLCUBSC2504CHOF1 | [12 empty] | 2025-06-18 | KPPI-HC-68263 |  | 2025-06-19 |  |  | 2025-06-17 | 0 | 0 | 0 | [17 empty] | Tons | [8 empty] | Arrived at Works | On time |  |  |  |  | 2
Arrived | QCL |  |  |  | 19969-60 |  | SCRAP OF CAST IRON | [6 empty] | 81.116 | Tons | [5 empty] | 0 |  |  |  | 61712 |  | 2025-03-24 |  | 100%LC |  |  |  | 282.3 |  | 31635.24 |  | 8930628.252 | [11 empty] | HLCUBSC2504CHLF5 | [12 empty] | 2025-06-19 | KPPI-HC-68429 |  | 2025-06-21 |  |  | 2025-06-23 | 0 | 0 | 0 | [17 empty] | Tons | [8 empty] | Arrived at Works | On time |  |  |  |  | 2
Arrived | QCL |  |  |  | 19969-60 |  | SCRAP OF CAST IRON | [6 empty] | 20.481 | Tons | [5 empty] | 0 |  |  |  | 61712 |  | 2025-03-24 |  | 100%LC |  |  |  | 282.7 |  | 7988 |  | 2258207.6 | [11 empty] | HLCUBSC2503CEKB4 | [12 empty] | 2025-06-12 | KPPI-HC-67185 |  | 2025-06-14 |  |  | 2025-06-24 | 0 | 0 | 0 | [17 empty] | Tons | [8 empty] | Arrived at Works | On time |  |  |  |  | 2
Arrived | QCL |  |  |  | 19969-60 |  | SCRAP OF CAST IRON | [6 empty] | 124.38 | Tons | [5 empty] | 0 |  |  |  | 61712 |  | 2025-03-24 |  | 100%LC |  |  |  | 282.7 |  | 48509.37 |  | 13713598.899 | [11 empty] | HLCUBSC2504AZHI6 | [12 empty] | 2025-06-12 | KPPI-HC-67186 |  | 2025-06-14 |  |  | 2025-06-17 | 0 | 0 | 0 | [17 empty] | Tons | [8 empty] | Arrived at Works | On time |  |  |  |  | 2
Arrived | QCL | Scraps | Store |  | 23562-60 |  | Manganese Steel Scrap | [6 empty] | 53.48 | Ton | [6 empty] | Prime Commodities Fze | UAE |  | 59933 |  | 2026-02-26 | BAH | LC |  | 490 | $ | 280 |  | 26205.2 |  | 7337456 |  |  |  | 7204.29 |  | CFR Karachi |  |  |  |  | Sea |  |  |  | Karachi |  | 2026-02-10 | 2026-04-25 | 2026-04-29 | 2026-05-04 |  | 2026-05-04 | 83 | [6 empty] | 0 | 2026-05-18 |  | 0 | 0 |  |  |  | 2026-05-06 | 7337456 | Paid | 2026-05-06 | 750000 | Paid | 280 | 7337456 | 7410830.56 | 0.27 | 0.065 |  |  | 168 | Kg | [8 empty] | Arrived at Works | Shipment will be reach at QCL on Monday dt: 12-05-2026 | 7 |  | 1 |  | 2
Arrived | QEN | Shafts | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 4140 | 404 | 4370 | SE25-CASA-0037 |  | CASA | 1 | Ton | 4.404 | 4.404 | 2026-01-29 |  | 2026-05-20 | 15.8571 | Dajin | China | Jining | 59764 | B1 | 2026-02-20 | BAH | LC |  | 8200 | ¥ | 40 | 36112.8 | 36112.8 | 1444512 | 1444512 |  |  |  | 7214.109 |  | FOB Shanghai |  |  | CNC Line |  | Sea | HTHC26033195-02 |  | Qingdao | Karachi |  | 2026-04-07 | 2026-05-02 | 2026-05-05 |  |  | 2026-05-05 | 28 | EFS | 2026-05-06 | KAPS-HC-189186 |  | 2026-05-07 |  | 1 | 2026-05-12 | 14.7143 | 0 | 8 |  |  |  | 2026-04-24 | 1444512 | Paid | 2026-05-06 | 124011.3552 | Paid | 40 | 1444512 | 1458957.12 | 0.02 | 0.065 |  |  | 401 | Kg | [7 empty] | . | Arrived at Works | Material will be ready on dt: 27-03-2026, Shipment booking has been received ETD:07-04-2026, Shipment will reach at QEN on Monday dt: 12-05-2026 | 10 | 1 | 1 | 7 | 3
Arrived | QEN | Shafts | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 1045 | 558 | 4830 | SE26-SARI-0005 |  | Sonkor(SARI) | 1 | Ton | 9.287 | 9.287 | 2026-02-04 |  | 2026-05-26 | 15.8571 | Dajin | China | Jining | 59764 | B2 | 2026-02-20 | BAH | LC |  | 6900 | ¥ | 40 | 193006.9 | 64080.3 | 7720276 | 2563212 |  |  |  | 7214.109 |  | FOB Shanghai |  | ZHONG GU HANG ZHOU V.2602W |  |  | Sea | CNSHAFGD1085 |  | Shanghai | Karachi | 2026-03-11 | 2026-04-24 | 2026-05-16 | 2026-05-17 | 2026-05-20 | 2026-05-23 | 2026-05-23 | 29 | EFS | [5 empty] | 0 | 2026-06-07 | 17.5714 | 0 | -12 |  |  |  | 2026-05-13 | 2563212 | Paid | 2026-03-30 | 220051.7502 | Paid | 40 | 2563212 | 2588844.12 | 0.02 | 0.065 |  |  | 346 | Kg | [8 empty] | Arrived at Works | Vessel bookin received ETD: 18-04-2026, Vessel Rollover from ETD 18-04-26 to 22-04-2026 & 24-04-26. Vessel Rollover ETA 17-05-2026 to 20-05-2026 then 23-05-2026 | 10 | 1 | 1 | 4 | 3
Arrived | QEN | Shafts | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 4140 | 404 | 4160 | SE25-CASA-0038 |  | CASA | 1 | Ton | 4.193 | 4.193 | 2026-01-29 |  | 2026-05-20 | 15.8571 | Dajin | China | Jining | 59764 | B2 | 2026-02-20 | BAH | LC |  | 8200 | ¥ | 40 |  | 34382.6 |  | 1375304 |  |  |  | 7214.109 |  | FOB Shanghai |  | ZHONG GU HANG ZHOU V.2602W |  |  | Sea | CNSHAFGD1085 |  | Shanghai | Karachi | 2026-03-05 | 2026-04-24 | 2026-05-16 | 2026-05-17 | 2026-05-20 | 2026-05-23 | 2026-05-23 | 29 | EFS | [5 empty] | 0 | 2026-06-07 | 18.4286 | 0 | -18 |  |  |  | 2026-05-13 | 1375304 | Paid | 2026-03-30 | 118069.8484 | Paid | 40 | 1375304 | 1389057.04 | 0.02 | 0.065 |  |  | 401 | Kg | [8 empty] | Arrived at Works | Vessel bookin received ETD: 18-04-2026, Vessel Rollover from ETD 18-04-26 to 22-04-2026 & 24-04-26. Vessel Rollover ETA 17-05-2026 to 20-05-2026 then 23-05-2026 | 10 | 1 | 1 | 4 | 3
Arrived | QEN | Shafts | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 1045 | 607 | 5472 | SE26-SUCA-0010 |  | Sucaf | 1 | Ton | 12.44 | 12.44 | 2026-02-19 |  | 2026-06-06 | 15.2857 | Dajin | China | Jining | 59764 | B2 | 2026-02-20 | BAH | LC |  | 7600 | ¥ | 40 |  | 94544 |  | 3781760 |  |  |  | 7214.109 |  | FOB Shanghai |  | ZHONG GU HANG ZHOU V.2602W |  |  | Sea | CNSHAFGD1085 |  | Shanghai | Karachi | 2026-03-26 | 2026-04-24 | 2026-05-16 | 2026-05-17 | 2026-05-20 | 2026-05-23 | 2026-05-23 | 29 | EFS | [5 empty] | 0 | 2026-06-07 | 15.4286 | 0 | -1 |  |  |  | 2026-05-13 | 3781760 | Paid | 2026-03-30 | 324664.096 | Paid | 40 | 3781760 | 3819577.6 | 0.02 | 0.065 |  |  | 382 | Kg | [8 empty] | Arrived at Works | Vessel bookin received ETD: 18-04-2026, Vessel Rollover from ETD 18-04-26 to 22-04-2026 & 24-04-26. Vessel Rollover ETA 17-05-2026 to 20-05-2026 then 23-05-2026 | 10 | 1 | 1 | 4 | 3
Arrived | QCL |  | Trading |  | TMPNL0068 |  | Anode Butt | [6 empty] | 149 | Ton | [6 empty] | Dynamic Commodities | UAE | Dubai | 59198 |  | 2025-10-03 | BAH | CAD | 2025-10-03 | 319.3 | $ | 281.4 | 47575.7 | 47575.7 | 13387801.98 | 13387801.98 |  |  |  | 3801.9 |  | CFR Karachi |  | Hema Bhum | Interasia | Rahmat Shipping | By Sea | A56FX32273 | 21 | Shnaghai | Karachi | 2025-09-17 | 2025-09-24 | 2025-09-29 |  |  |  | 2025-09-29 | 5 | AS Corp | [5 empty] | 0 | 2025-10-09 |  | 0 | 0 | 2025-10-03 | 13387801.98 | Paid |  |  |  | 2025-09-29 | 4259329.1999 | Paid | 281.4 | 13387801.98 | 13521679.9998 | 0.25 | 0.065 |  |  |  | Ton | [8 empty] | Arrived at Works | (Trading Shipment)/Arrived at Trader Warehouse. | 12 | 4 | 1 | 10 | 2
Arrived | QCL | Foundry Material | Store |  | 24612-60 |  | Resin | A-85 | [5 empty] | 12000 | Kgs |  |  | 2026-01-13 |  | 2026-04-13 | 12.8571 | Cukurova | Turkey |  | 58601 |  | 2026-02-10 | BAH | LC |  | 0.64 | € | 324.85 |  | 7680 |  | 2494848 |  |  |  | 3824.1 | YES | CFR Karachi |  | CMA CGM CENDRILLON |  |  | Sea | ISB1925996 |  | Aliaga | Karachi |  | 2026-03-05 | 2026-04-16 | 2026-04-23 | 2026-04-29 |  | 2026-04-29 | 55 | EFS | 2026-04-30 | KAPS-FS-186493 |  | 2026-05-04 |  | 4 | 2026-05-07 | 0 | 0 | -24 |  |  |  | 2026-03-25 | 2494848 | Paid | 2026-04-30 | 718141.9968 | Paid | 324.85 | 2494848 | 2519796.48 | 0.22 | 0.065 |  |  | 242 | Kgs | [8 empty] | Arrived at Works | Container is still at Colombo port since 09-04-2026 due port congestion and ETA Karachi rollover multiple times from 16-04-26 to 23-04-2026 and now ETA Karachi is 27-04-2026. | 11 | 1 | 1 | 9 | 2
Arrived | QCL | Foundry Material | Store |  | TMPNL0069 |  | Hardener | AS-09 | [5 empty] | 6600 | Kgs |  |  | 2026-01-13 |  | 2026-04-13 | 12.8571 | Cukurova | Turkey |  | 58601 |  | 2026-02-10 | BAH | LC |  | 1.2 | € | 324.85 |  | 7920 |  | 2572812 |  |  |  | 3824.1 | YES | CFR Karachi |  | CMA CGM CENDRILLON |  |  | Sea | ISB1925996 |  | Aliaga | Karachi |  | 2026-03-05 | 2026-04-16 | 2026-04-23 | 2026-04-29 |  | 2026-04-29 | 55 | EFS | 2026-04-30 | KAPS-FS-186493 |  | 2026-05-04 |  | 4 | 2026-05-07 | 0 | 0 | -24 |  |  |  | 2026-03-25 | 2572812 | Paid | 2026-04-30 | 740583.9342 | Paid | 324.85 | 2572812 | 2598540.12 | 0.22 | 0.065 |  |  | 440 | Kgs | [8 empty] | Arrived at Works | Container is still at Colombo port since 09-04-2026 due port congestion and ETA Karachi rollover multiple times from 16-04-26 to 23-04-2026 and now ETA Karachi is 27-04-2026. | 11 | 1 | 1 | 9 | 2
Arrived | QCL | Foundry Material | Store |  | TMPNL0070 |  | Coating | Reflak-212 | [5 empty] | 2025 | Kgs |  |  | 2026-01-13 |  | 2026-04-13 | 12.8571 | Cukurova | Turkey |  | 58601 |  | 2026-02-10 | BAH | LC |  | 0.64 | € | 324.85 |  | 1296 |  | 421005.6 |  |  |  | 3824.1 | YES | CFR Karachi |  | CMA CGM CENDRILLON |  |  | Sea | ISB1925996 |  | Aliaga | Karachi |  | 2026-03-05 | 2026-04-16 | 2026-04-23 | 2026-04-29 |  | 2026-04-29 | 55 | EFS | 2026-04-30 | KAPS-FS-186493 |  | 2026-05-04 |  | 4 | 2026-05-07 | 0 | 0 | -24 |  |  |  | 2026-03-25 | 421005.6 | Paid | 2026-04-30 | 121186.462 | Paid | 324.85 | 421005.6 | 425215.656 | 0.22 | 0.065 |  |  | 246 | Kgs | [8 empty] | Arrived at Works | Container is still at Colombo port since 09-04-2026 due port congestion and ETA Karachi rollover multiple times from 16-04-26 to 23-04-2026 and now ETA Karachi is 27-04-2026. | 11 | 1 | 1 | 9 | 2
Arrived | QCL | Foundry Material | Store |  | TMPNL0071 |  | Coating | CK-980 | [5 empty] | 1990 | Kgs |  |  | 2026-01-27 |  | 2026-04-27 | 12.8571 | Cukurova | Turkey |  | 58601 |  | 2026-02-10 | BAH | LC |  | 1.58 | € | 324.85 |  | 3144.2 |  | 1021393.37 |  |  |  | 3824.1 | YES | CFR Karachi |  | CMA CGM CENDRILLON |  |  | Sea | ISB1925996 |  | Aliaga | Karachi |  | 2026-03-05 | 2026-04-16 | 2026-04-23 | 2026-04-29 |  | 2026-04-29 | 55 | EFS | 2026-04-30 | KAPS-FS-186493 |  | 2026-05-04 |  | 4 | 2026-05-07 | 0 | 0 | -10 |  |  |  | 2026-03-25 | 1021393.37 | Paid | 2026-04-30 | 294008.0816 | Paid | 324.85 | 1021393.37 | 1031607.3037 | 0.22 | 0.065 |  |  | 576 | Kgs | [8 empty] | Arrived at Works | Container is still at Colombo port since 09-04-2026 due port congestion and ETA Karachi rollover multiple times from 16-04-26 to 23-04-2026 and now ETA Karachi is 27-04-2026. | 11 | 1 | 1 | 9 | 2
Arrived | QCL | Foundry Material | Store |  | TMPNL0072 |  | Coating | FL-69000 | [5 empty] | 300 | Kgs | [5 empty] | 0 | Cukurova | Turkey |  | 58601 |  | 2026-02-10 | BAH | LC |  | 1.65 | € | 324.85 |  | 495 |  | 160800.75 |  |  |  | 3824.1 | YES | CFR Karachi |  | CMA CGM CENDRILLON |  |  | Sea | ISB1925996 |  | Aliaga | Karachi |  | 2026-03-05 | 2026-04-16 | 2026-04-23 | 2026-04-29 |  | 2026-04-29 | 55 | EFS | 2026-04-30 | KAPS-FS-186493 |  | 2026-05-04 |  | 4 | 2026-05-07 | 0 | 0 | 0 |  |  |  | 2026-03-25 | 160800.75 | Paid | 2026-04-30 | 46286.4959 | Paid | 324.85 | 160800.75 | 162408.7575 | 0.22 | 0.065 |  |  |  | Kgs | [8 empty] | Arrived at Works | Container is still at Colombo port since 09-04-2026 due port congestion and ETA Karachi rollover multiple times from 16-04-26 to 23-04-2026 and now ETA Karachi is 27-04-2026. | 11 | 1 | 1 | 9 | 2
Shafts/Ongoing/Import Status/Import Rem | QBL-II | Scraps | Store |  | 19969-60 |  | Cast Iron Scrap | Oversized | [5 empty] | 206.352 | Ton | [6 empty] | Prime Commodities Fze | UAE |  | 57625 |  | 2026-01-30 | BAH | LC |  | 377 | $ | 278.4 |  | 77794.704 |  | 21658045.5936 |  |  |  | 7204.109 | NO | CFR Karachi |  |  | MSC Shipping | MSC Pakistan | Sea |  |  | New York | Karachi |  | 2026-04-29 | 2026-06-08 | 2026-06-15 | 2026-07-01 |  | 2026-07-01 | 63 | MHQ | [5 empty] | 0 | 2026-07-11 | 0 | 0 | 0 |  |  |  | 2026-06-18 | 21658045.5936 | Paid | 2026-02-05 | 8202984.7686 | Paid | 278.4 | 21658045.5936 | 21874626.0495 | 0.31 | 0.065 |  |  | 133 | Kg | [8 empty] | Under Custom Clearance |  | 7 | 3 | 1 | 8 | 4
Arrived | QCL |  | Store |  | 19969-60 |  | Cast Iron Scrap | Oversized | [5 empty] | 80.781 | Ton | [6 empty] | Prime Commodities Fze | UAE |  | 57582 | B1 | 2026-01-28 | BAH | LC |  | 377 | $ | 282 | 30454.437 | 30454.437 | 8588151.234 | 8588151.234 |  |  |  | 7204.109 |  | CFR Karachi |  |  | MSC Shipping | MSC Pakistan | Sea |  |  |  | Karachi |  | 2026-01-22 | 2026-03-14 |  |  |  | 2026-03-14 | 51 | MHQ | 2026-03-16 | KPPI-HC-54589 |  | 2026-03-17 |  | 1 | 2026-03-24 |  | 0 | 0 |  |  |  | 2026-03-01 | 8588151.234 | Paid | 2026-02-05 | 3252762.2799 | Paid | 282 | 8588151.234 | 8674032.7463 | 0.31 | 0.065 |  |  | 133 | Kg | [8 empty] | Arrived at Works |  | 7 | 3 | 1 |  | 2
Arrived | QCL | Scraps | Store |  | 19969-60 |  | Cast Iron Scrap | Oversized | [5 empty] | 62.867 | Ton | [6 empty] | Prime Commodities Fze | UAE |  | 57582 | B2 | 2026-01-28 | BAH | LC |  | 377 | $ | 279.4 | 23700.859 | 23700.859 | 6622020.0046 | 6622020.0046 |  |  |  | 7204.109 |  | CFR Karachi |  |  | MSC Shipping | MSC Pakistan | Sea | MEDUWN651759 |  | New York | Karachi |  | 2026-03-24 | 2026-04-20 | 2026-04-27 | 2026-04-28 |  | 2026-04-28 | 35 | MHQ | [5 empty] | 0 | 2026-05-05 | 0 | 0 | 0 |  |  |  | 2026-04-13 | 6622020.0046 | Paid | 2026-04-29 | 2508090.0767 | Unpaid | 279.4 | 6622020.0046 | 6688240.2046 | 0.31 | 0.065 |  |  | 133 | Kg | [8 empty] | Arrived at Works |  | 7 | 3 | 1 | 8 | 2
Arrived | QCL | Scraps | Store |  | 19969-60 |  | Cast Iron Scrap | Oversized | [5 empty] | 40.636 | Ton | [6 empty] | Prime Commodities Fze | UAE |  | 57582 | B4 | 2026-01-28 | BAH | LC |  | 377 | $ | 282 | 15319.772 | 15319.772 | 4320175.704 | 4320175.704 |  |  |  | 7204.109 |  | CFR Karachi |  |  | MSC Shipping | MSC Pakistan | Sea |  |  |  | Karachi |  | 2026-03-29 | 2026-05-02 | 2026-05-07 | 2026-05-09 | 2026-05-10 | 2026-05-10 | 42 | MHQ | [5 empty] | 0 | 2026-05-19 |  | 0 | 0 |  |  |  | 2026-03-01 | 4320175.704 | Paid | 2026-02-05 | 1636266.5479 | Paid | 282 | 4320175.704 | 4363377.461 | 0.31 | 0.065 |  |  | 133 | Kg | [8 empty] | Arrived at Works |  | 7 | 3 | 1 |  | 2
Arrived | QCL |  | Store |  | 19969-60 |  | Cast Iron Scrap | Oversized | [5 empty] | 98.6 | Ton | [6 empty] | Prime Commodities Fze | UAE |  | 57582 | B3 | 2026-01-28 | BAH | LC |  | 377 | $ | 282 | 37172.2 | 37172.2 | 10482560.4 | 10482560.4 |  |  |  | 7204.109 |  | CFR Karachi |  |  | MSC Shipping | MSC Pakistan | Sea | MEDUYK696472 |  | Gdynia, Poland | Karachi |  | 2026-03-24 | 2026-05-05 | 2026-05-19 | 2026-05-23 | 2026-05-24 | 2026-05-24 | 61 | MHQ | [5 empty] | 0 | 2026-06-06 |  | 0 | 0 |  |  |  | 2026-03-01 | 10482560.4 | Paid | 2026-02-05 | 3970269.7515 | Paid | 282 | 10482560.4 | 10587386.004 | 0.31 | 0.065 |  |  | 133 | Kg | [8 empty] | Arrived at Works |  | 7 | 3 | 1 | 6 | 2
Arrived | QCL | Foundry Material | Store |  | TMPNL0073 |  | Ferro Chrome H/C | C 6-8%, Cr 60%, Si 4% Max, S 0.05%, P 0.05% | [5 empty] | 10 | Ton |  |  | 2025-11-21 |  | 2026-02-21 | 13.1429 | JC Resources | South Korea | Seoul | 56399 |  | 2026-01-14 | BAH | LC |  | 1560 | $ | 282 | 15600 | 15600 | 4399200 | 4399200 |  |  |  | 7202.41 |  | CFR Karachi |  |  |  |  | Sea |  |  |  | Karachi | [7 empty] | 0 | EFS | [5 empty] | 0 |  |  | 0 | [17 empty] | 491 | kg | [8 empty] | Order Cancelled | order Cancelled | 13 | 1 | 1 |  | 2
Arrived | QCL |  | Store |  | 26287-60 |  | Resin | APR-103D | [5 empty] | 21.6 | Ton |  | 21.6 | 2025-10-23 |  | 2026-01-23 | 13.1429 | SQ | China | Jinancity | 55714 |  | 2026-01-12 | BAH | LC |  | 770 | $ | 279.8 | 16632 | 16632 | 4653633.6 | 4653633.6 |  |  |  | 3824.1 |  | CFR Karachi |  |  |  |  | Sea |  |  |  | Karachi |  | 2026-01-25 | 2026-02-21 |  |  |  | 2026-02-21 |  | EFS | 2026-02-23 | KAPS-HC-146576 |  | 2026-02-24 |  | 1 | 2026-02-27 |  | 0 | -35 |  |  |  | 2026-02-12 | 4653633.6 | Paid | 2026-02-21 | 1386550.1311 | Paid | 279.8 | 4653633.6 | 4700169.936 | 0.23 | 0.065 |  |  | 247 | Kg | 241 |  | 2026-06-12 | 76 |  |  |  |  | Arrived at Works |  | 3 | 1 | 1 |  | 2
Arrived | QEN | Engineering Item | Engg. |  | TMPNL0074 |  | Stainless Steel Flat Bar(60MM) | SS41500(ASTM A959-2004) | 65*180*160 |  | SE25-FCGL-0618 |  | FIVES(FCB) | 4 | Kgs | 107.5 | 430 | 2025-11-11 |  | 2026-02-05 | 12.2857 | Jiangsu Gangzhicheng Metal | China |  | 51011 |  | 2025-12-23 | BAH | Advance |  | 3.971 | $ | 280.6 |  | 1707.53 |  | 479132.918 |  |  |  | 7222.4 |  | FOB Shanghai |  |  |  |  | Sea | JHN26030189 |  | Shanghai | Karachi |  | 2026-04-01 | 2026-04-18 | 2026-04-20 |  |  | 2026-04-20 | 19 | EFS | 2026-04-20 | KAPE-HC-65052 |  | 2026-04-24 |  | 4 | 2026-04-30 | 18.4286 | 0 | -84 | 2025-12-20 | 479132.918 | Paid |  |  |  | 2026-04-20 | 157275.3803 | Paid | 280.6 | 479132.918 | 483924.2472 | 0.26 | 0.065 |  |  | 1308 | Kgs | [8 empty] | Arrived at Works | The demand was re-routed from Procurement to Import on 16-12-2025. A new supplier was arranged in China on 22-12-2025, and the advance T/T was transferred on 23-12-2025. The material was ready on 12-01-2026. However, as per the provided MTC, CPPC requested modifications in the specifications of the flat bar. Due to this requirement, the supplier had to reproduce the flat bar, resulting in additional reproduction costs of RMB 3,570, along with RMB 2,000 incurred due to newly imposed taxes by the Chinese government. These charges were negotiated and paid in China on 10-03-2026. The forwarder was nominated on 12-03-2026, and booking confirmation was received from the logistics provider with an ETD of 01-04-2026./Shipment under de-stuffing | 14 | 1 | 1 | 4 | 3
Arrived | QE |  | Capital |  | TMPNL0075 |  | Numerical Controlled Boring Machine(EFS) | [6 empty] | 1 | Pcs | [6 empty] | Roma Marble & Stone | KSA |  | 50978 |  | 2025-12-22 | BAH | Advance |  | 174400 | $ | 280.6 |  | 174400 |  | 48936640 |  |  |  | 8459.412 |  | FOB |  |  |  |  | Sea |  |  |  | Karachi |  | 2026-03-18 | 2026-04-04 | 2026-04-07 | 2026-04-08 | 2026-04-10 | 2026-04-10 | 23 | EFS | [5 empty] | 0 | 2026-04-18 | 0 | 0 | 0 | 2025-12-17 | 48936640 | Paid |  |  |  | 2026-04-13 | 4201210.544 | Paid | 280.6 | 48936640 | 49426006.4 | 0.02 | 0.065 |  |  |  | Pcs | [8 empty] | Arrived at Works |  | 15 | 1 | 1 |  | 1
Arrived | QBL-II |  | Sample |  | TMPNL0076 |  | PIG Iron | [6 empty] | 300 | Kgs | [6 empty] | Teigu(Hainan) International | China |  | 50922 |  | 2025-12-18 | BAH | Advance |  | 5 | ¥ | 40 |  | 1500 |  | 60000 |  |  |  | 7201.1 |  | Ex Work |  |  |  |  | Air |  |  |  | Lahore | [14 empty] | 0 |  |  | 0 | 0 | 2025-12-17 | 60000 | Paid |  |  |  |  | 17877 | Unpaid | 40 | 60000 | 60600 | 0.23 | 0.065 |  |  |  | Kgs | [8 empty] | Order Cancelled | Sample shipment | 16 |  | 3 |  | 4
Arrived | QBL-II |  | Store |  | 2823-60 |  | Exothermic Powder | [6 empty] | 5 | Ton |  |  | 2025-11-25 |  | 2026-02-21 | 12.5714 | SQ | China |  | 50669 |  | 2025-12-10 | BAH | Advance |  | 715 | $ | 280.55 | 3575 | 3575 | 1002966.25 | 1002966.25 |  |  |  | 3824.1 | EFS | FOB Qingdao |  |  |  |  | Sea | WTAOKHI26016524 |  | QINGDAO | Karachi |  | 2026-01-10 | 2026-01-30 | 2026-02-07 |  |  | 2026-02-07 | 28 | EFS | 2026-02-09 | KAPW-HC-147185 |  | 2026-02-12 |  | 3 | 2026-02-20 |  | 0 | 1 | 2025-12-10 | 1002966.25 | Paid |  |  |  | 2026-02-07 | 298833.7942 | Paid | 280.55 | 1002966.25 | 1012995.9125 | 0.23 | 0.065 |  |  | 280 | Kg | 242 | [7 empty] | Arrived at Works |  | 3 | 1 | 1 | 7 | 4
Arrived | QCL |  | Store |  | 15198-60 |  | Exothermic Sleeves | BGK-2 | [5 empty] | 3000 | Pcs |  |  | 2025-11-21 |  | 2026-02-21 | 13.1429 | Cukurova | Turkey |  | 50668 |  | 2025-12-10 | BAH | Advance |  | 0.75 | £ | 326.4 | 2250 | 2250 | 734400 | 734400 |  |  |  | 6903.901 |  | FOB Izmir |  | GFS PRIDE |  | MEPL International Pakistan | Sea | JIEXP-0057146 |  | Aliaga | Karachi |  | 2025-12-28 | 2026-02-06 | 2026-02-12 | 2026-02-16 | 2026-02-22 | 2026-02-22 | 56 | EFS | 2026-02-23 | KAPW-HC-157134 |  | 2026-03-02 |  | 7 | 2026-03-09 |  | 0 | -16 | 2025-12-10 | 734400 | Paid |  |  |  | 2026-01-10 | 241066.8 | Paid | 326.4 | 734400 | 741744 | 0.26 | 0.065 |  |  | 386 | Pcs | 321 | [7 empty] | Arrived at Works |  | 11 | 1 | 1 | 9 | 2
Arrived | QE |  | Engg. |  | TMPNL0077 |  | Synchronous Servomotor- HSD7-E380 V | SF180-4-018M1530B-A, 18.6 N.M, 2.9KW | [5 empty] | 1 | Pcs |  |  | 2025-11-06 |  |  | 0 | HNC | China | Guangzhou | 50366 |  | 2025-12-03 | BAH | Advance |  | 530.77 | $ | 280.8 | 4037.69 | 530.77 | 1133783.352 | 149040.216 |  |  |  | 8501.1 |  | FCA Shanghai |  |  |  |  | Air | 784-41853744 |  | Shanghai | Lahore | 2025-12-10 | 2025-12-22 | 2025-12-27 |  |  |  | 2025-12-27 | 5 | EFS | 2025-12-30 | LPAF-HC-48677 |  | 2026-01-05 |  | 6 | 2025-12-29 |  | 0 | 0 | 2025-12-03 | 149040.216 | Paid |  |  |  | 2025-12-25 | 48922.4509 | Paid | 280.8 | 149040.216 | 150530.6182 | 0.26 | 0.065 |  |  | 0 | Pcs | [8 empty] | Arrived at Works |  | 17 | 1 | 3 | 4 | 1
Arrived | QE |  | Engg. |  | TMPNL0078 |  | Synchronous Servomotor- HSD7-E380 V | SF180-4-018M1530-A, 18.6 N.M, 2.9KW | [5 empty] | 2 | Pcs |  |  | 2025-11-06 |  |  | 0 | HNC | China | Guangzhou | 50366 |  | 2025-12-03 | BAH | Advance |  | 350.77 | $ | 280.8 |  | 701.54 |  | 196992.432 |  |  |  | 8501.1 |  | FCA Shanghai |  |  |  |  | Air | 784-41853744 |  | Shanghai | Lahore | 2025-12-10 | 2025-12-22 | 2025-12-27 |  |  |  | 2025-12-27 | 5 | EFS | 2025-12-30 | LPAF-HC-48677 |  | 2026-01-05 |  | 6 | 2025-12-29 |  | 0 | 0 | 2025-12-03 | 196992.432 | Paid |  |  |  | 2025-12-25 | 64662.7658 | Paid | 280.8 | 196992.432 | 198962.3563 | 0.26 | 0.065 |  |  | 0 | Pcs | [8 empty] | Arrived at Works |  | 17 | 1 | 3 | 4 | 1
Arrived | QE |  | Engg. |  | TMPNL0079 |  | Synchronous Servomotor- HSD7-E380 V | HSD7-ES-15D30 | [5 empty] | 3 | Pcs |  |  | 2025-11-06 |  |  | 0 | HNC | China | Guangzhou | 50366 |  | 2025-12-03 | BAH | Advance |  | 378.46 | $ | 280.8 |  | 1135.38 |  | 318814.704 |  |  |  | 8504.409 |  | FCA Shanghai |  |  |  |  | Air | 784-41853744 |  | Shanghai | Lahore | 2025-12-10 | 2025-12-22 | 2025-12-27 |  |  |  | 2025-12-27 | 5 | EFS | 2025-12-30 | LPAF-HC-48677 |  | 2026-01-05 |  | 6 | 2025-12-29 |  | 0 | 0 | 2025-12-03 | 318814.704 | Paid |  |  |  | 2025-12-25 | 127191.1262 | Paid | 280.8 | 318814.704 | 322002.851 | 0.33 | 0.065 |  |  | 0 | Pcs | [8 empty] | Arrived at Works |  | 17 | 1 | 3 | 4 | 1
Arrived | QE |  | Engg. |  | TMPNL0080 |  | HNC-808 Series Controller, 4 Axis | MPG for HNC-808 | [5 empty] | 1 | Pcs |  |  | 2025-11-06 |  |  | 0 | HNC | China | Guangzhou | 50366 |  | 2025-12-03 | BAH | Advance |  | 105 | $ | 280.8 |  | 105 |  | 29484 |  |  |  | 8537.109 |  | FCA Shanghai |  |  |  |  | Air | 784-41853744 |  | Shanghai | Lahore | 2025-12-10 | 2025-12-22 | 2025-12-27 |  |  |  | 2025-12-27 | 5 | EFS | 2025-12-30 | LPAF-HC-48677 |  | 2026-01-05 |  | 6 | 2025-12-29 |  | 0 | 0 | 2025-12-03 | 29484 | Paid |  |  |  | 2025-12-25 | 16825.0446 | Paid | 280.8 | 29484 | 29778.84 | 0.5 | 0.065 |  |  | 0 | Pcs | [8 empty] | Arrived at Works |  | 17 | 1 | 3 | 4 | 1
Arrived | QE |  | Engg. |  | TMPNL0081 |  | CNC Controller for CNC Milling Machine | HNC-808DiM 10.4 Inch | [5 empty] | 1 | Pcs |  |  | 2025-11-06 |  |  | 0 | HNC | China | Guangzhou | 50366 |  | 2025-12-03 | BAH | Advance |  | 1565 | $ | 280.8 |  | 1565 |  | 439452 |  |  |  | 8537.109 |  | FCA Shanghai |  |  |  |  | Air | 784-41853744 |  | Shanghai | Lahore | 2025-12-10 | 2025-12-22 | 2025-12-27 |  |  |  | 2025-12-27 | 5 | EFS | 2025-12-30 | LPAF-HC-48677 |  | 2026-01-05 |  | 6 | 2025-12-29 |  | 0 | 0 | 2025-12-03 | 439452 | Paid |  |  |  | 2025-12-25 | 250773.2838 | Paid | 280.8 | 439452 | 443846.52 | 0.5 | 0.065 |  |  | 0 | Pcs | [8 empty] | Arrived at Works |  | 17 | 1 | 3 | 4 | 1
Arrived | QE |  | Store |  | TMPNL0082 |  | Safety Synthetic Round Slings(Yellow) | 1925mmx25000kgs |  |  | SE25-SMHE-0083 |  | Sonkor(MHLUME) | 16 | Pcs |  |  | 2025-11-18 |  |  | 0 | Dofull | China | Taizhou | 50169 |  | 2025-11-26 | BAH | Advance |  | 295 | ¥ | 39.65 |  | 4720 |  | 187148 |  |  |  | 5402.51 |  | FCA Shanghai |  |  | China Southern |  | Air | AOFCTU6609 |  | Pudong | Lahore | 2025-12-15 | 2025-12-18 | 2025-12-20 |  |  |  | 2025-12-20 | 2 | EFS | 2025-12-22 | LPAF-HC-46870 |  | 2025-12-23 |  | 1 | 2025-12-22 |  | 0 | 0 | 2025-11-26 | 187148 | Paid |  |  |  |  | 55760.7466 | Paid | 39.65 | 187148 | 189019.48 | 0.23 | 0.065 |  |  | 17620 | Pcs | [8 empty] | Arrived at Works |  | 18 | 1 | 3 | 11 | 1
Arrived | QE |  | Store |  | TMPNL0083 |  | Reverse Synthetic Round Slings(Blue) | 1770mmx25000kgs |  |  | SE25-SMHE-0083 |  | Sonkor(MHLUME) | 8 | Pcs |  |  | 2025-11-18 |  |  | 0 | Dofull | China | Taizhou | 50169 |  | 2025-11-26 | BAH | Advance |  | 265 | ¥ | 39.65 |  | 2120 |  | 84058 |  |  |  | 5402.51 |  | FCA Shanghai |  |  | China Southern |  | Air | AOFCTU6609 |  | Pudong | Lahore | 2025-12-15 | 2025-12-18 | 2025-12-20 |  |  |  | 2025-12-20 | 2 | EFS | 2025-12-22 | LPAF-HC-46870 |  | 2025-12-23 |  | 1 | 2025-12-22 |  | 0 | 0 | 2025-11-26 | 84058 | Paid |  |  |  |  | 25045.0811 | Paid | 39.65 | 84058 | 84898.58 | 0.23 | 0.065 |  |  | 17296 | Pcs | [8 empty] | Arrived at Works |  | 18 | 1 | 3 | 11 | 1
Arrived | QE |  | Store |  | TMPNL0084 |  | Drive Synthetic Round Slings(Orange) | 1625mmx25000kgs |  |  | SE25-SMHE-0083 |  | Sonkor(MHLUME) | 16 | Pcs |  |  | 2025-11-18 |  |  | 0 | Dofull | China | Taizhou | 50169 |  | 2025-11-26 | BAH | Advance |  | 245 | ¥ | 39.65 |  | 3920 |  | 155428 |  |  |  | 5402.51 |  | FCA Shanghai |  |  | China Southern |  | Air | AOFCTU6609 |  | Pudong | Lahore | 2025-12-15 | 2025-12-18 | 2025-12-20 |  |  |  | 2025-12-20 | 2 | EFS | 2025-12-22 | LPAF-HC-46870 |  | 2025-12-23 |  | 1 | 2025-12-22 |  | 0 | 0 | 2025-11-26 | 155428 | Paid |  |  |  |  | 46309.7726 | Paid | 39.65 | 155428 | 156982.28 | 0.23 | 0.065 |  |  | 15600 | Pcs | [8 empty] | Arrived at Works |  | 18 | 1 | 3 | 11 | 1
Arrived | QEN |  | Store |  | TMPNL0085 |  | Hammer Tips & Bolt | 7/8’’-14/90X55X45mm | [5 empty] | 448 | Set | [5 empty] | 0 | One Piece | China |  | 50032 |  | 2025-11-21 | HMB | Advance |  | 94.2817 | ¥ | 39.49 |  | 42238.2 |  | 1667986.518 |  |  |  | 7326.909 |  | FOB |  | OOCL NAGOYA |  | Facility Shipping | By Sea | SHKHI25243978 |  | Shanghai | Karachi | 2025-11-20 | 2025-12-01 | 2025-12-19 | 2025-12-22 |  |  | 2025-12-22 | 21 | EFS | 2025-12-22 | KAPW-HC-113484 |  | 2025-12-27 |  | 5 | 2026-01-05 | 0 | 0 | 0 | 2025-11-21 | 1667986.518 | Paid |  |  |  | 2025-12-22 | 1200000 | Paid | 39.49 | 1667986.518 | 1684666.3832 | 0.26 | 0.065 |  |  |  | Set | [8 empty] | Arrived at Works | Material is ready,Vessel booking is in process. | 9 | 1 | 1 | 4 | 3
Arrived | QEN |  | Engg. |  | TMPNL0086 |  | Cabinet Air Conditioner for IGBT | EF-1000, 200V 50/60Hz | [5 empty] | 5 | Set | [5 empty] | 0 | Kotron | China | Hanghai | 49139 |  | 2025-10-28 | BAH | Advance |  | 590 | $ | 281.15 | 3628 | 2950 | 1020012.2 | 829392.5 |  |  |  | 8418.699 |  | FOB-LCL |  |  |  | Freight Hub | By Sea | JHN25110554 |  | Shanghai | Karachi | 2025-11-13 | 2025-12-01 | 2025-12-22 |  |  |  | 2025-12-22 | 21 | EFS | 2025-12-22 | KAPE-HC-42150 | Green | 2025-12-24 |  | 2 | 2026-01-05 | 0 | 0 | 0 | 2025-10-28 | 829392.5 | Paid |  |  |  | 2025-12-22 | 724598.7576 | Paid | 281.15 | 829392.5 | 837686.425 | 0.8 | 0.065 |  |  |  | Set | [8 empty] | Arrived at Works |  | 19 | 1 | 1 | 4 | 3
Arrived | QEN |  | Engg. |  | TMPNL0087 |  | Cabinet Air Conditioner for IGBT | EF-1500, 200V 50/60Hz | [5 empty] | 1 | Set | [5 empty] | 0 | Kotron | China | Hanghai | 49139 |  | 2025-10-28 | BAH | Advance |  | 678 | $ | 281.15 |  | 678 |  | 190619.7 |  |  |  | 8418.699 |  | FOB-LCL |  |  |  | Freight Hub | By Sea | JHN25110554 |  | Shanghai | Karachi | 2025-11-13 | 2025-12-01 | 2025-12-22 |  |  |  | 2025-12-22 | 21 | EFS | 2025-12-22 | KAPE-HC-42150 | Green | 2025-12-24 |  | 2 | 2026-01-05 | 0 | 0 | 0 | 2025-10-28 | 190619.7 | Paid |  |  |  | 2025-12-22 | 166534.9009 | Paid | 281.15 | 190619.7 | 192525.897 | 0.8 | 0.065 |  |  |  | Set | [8 empty] | Arrived at Works |  | 19 | 1 | 1 | 4 | 3
Arrived | QEN |  | Store |  | 26135-60 |  | Milling Head | BT50-ER32-200 | [5 empty] | 1 | Pcs | [5 empty] | 0 | Dezhou Haotian | China | Pingyuan | 48509 |  | 2025-10-08 | BAH | Advance |  | 1739 | $ | 281.4 |  | 1739 |  | 489354.6 |  |  |  | 8466.1 |  | CPT-Lahore |  |  |  | UPS | By Air | 1Z33W2606793105300 |  | Shnaghai | Lahore | 2025-10-23 | 2025-10-29 | 2025-10-31 | 2025-11-03 |  |  | 2025-11-03 | 5 | EFS | 2025-11-04 | LPFI-HC-20327 | Green | 2025-11-05 |  | 1 | 2025-11-05 |  | 0 | 0 | 2025-10-08 | 489354.6 | Paid |  |  |  | 2025-11-03 | 150745.6845 | Paid | 281.4 | 489354.6 | 494248.146 | 0.24 | 0.065 |  |  | 619267 | Pcs | 540766 | [7 empty] | Arrived at Works | IDM Awaited | 20 | 1 | 3 | 10 | 3
Arrived | QEN | MS25-34 | Store |  | TMPNL0088 |  | Hobbing Cutter - 24 module | M24X20 X290X60X320 | [5 empty] | 2 | Pcs |  |  |  | 2025-08-26 |  | 0 | LZQ | China | Shanghai | 47073 |  | 2025-08-27 | BAH | Advance |  | 2468 | $ | 281.95 |  | 4936 |  | 1391705.2 | Received | Approved | Approved | 8208.1 | NO | EX-WORK | SINOTECH LOGISTICS |  | China Southern | SINOTECH LOGISTICS | By Air | SA251005266 | 3 | PUDONG | Lahore | 2025-10-25 | 2025-10-25 | 2025-10-28 |  |  |  | 2025-10-28 | 3 | EFS | 2025-10-28 | LPAF-HC-35662 | Green | 2025-10-29 |  | 1 | 2025-10-29 | 0 | 0 | 0 | 2025-08-27 | 1391705.2 | Paid |  |  |  | 2025-10-28 | 498995.8995 | Paid | 281.95 | 1391705.2 | 1405622.252 | 0.29 | 0.065 |  |  | 939679 | Pcs | 953178 | [7 empty] | Arrived at Works |  | 21 | 1 | 3 | 11 | 3
Arrived | QE |  | Store |  | TMPNL0089 |  | Synthetic Ropes | 25T | [5 empty] | 20 | Pcs. | [5 empty] | 0 | Dofull | China | Taizhou | 44669 |  |  | BAH | TT | [5 empty] | 14040 |  | 0 |  |  |  | 5402.51 | NO | FCA | BROCO | 2025-01-25 | Sinotech | Broco - LHR | By Air | 78475261664 |  | Shanghai | Karachi-port | 2025-01-10 | [7 empty] | Eastern |  |  | Green | 2025-08-01 |  |  | 2025-08-04 | 0 | 0 | 0 | [17 empty] | Pcs. | [8 empty] | Arrived at Works | On time | 18 | 2 | 2 | 4 | 1
Arrived | QE |  | Store |  | TMPNL0090 |  | Synthetic Ropes | 25T | [5 empty] | 80 | Pcs. | [5 empty] | 0 | Dofull | China | Taizhou | 44036 |  | 2025-05-15 | BAH | TT | [5 empty] | 14040 |  | 0 |  |  |  | 5402.51 | NO | FCA | BROCO | 2025-01-25 | Sinotech | Broco - LHR | By Air | 78475261664 |  | Shanghai | Karachi-port | 2025-01-10 | [7 empty] | Eastern |  |  | Green | 2025-08-01 |  |  | 2025-08-04 | 0 | 0 | 0 | [17 empty] | Pcs. | [8 empty] | Arrived at Works | On time | 18 | 2 | 2 | 4 | 1
Arrived | QEN | Engineering Item | Sample |  | TMPNL0091 |  | Weding Wire(3mm) | ER312 SS SAW | [5 empty] | 50 | Kgs | [6 empty] | Qingdao Tensileweld | China |  | 43543 |  | 2026-04-23 | BAH | Advance |  | 11.37 | $ | 281 |  | 568.5 |  | 159748.5 |  |  |  | 8331.3 |  | FOB |  |  |  |  | Air | CY2605179/784-83932936 |  | Guangzhou | Lahore | 2026-05-14 | 2026-05-25 | 2026-05-26 |  |  |  | 2026-05-26 | 1 | EFS | 2026-06-02 | LPAF-HC-84523 |  | 2026-06-04 |  | 2 | 2026-06-04 |  | 0 | 0 | 2026-04-23 | 159748.5 | Paid |  |  |  | 2026-05-25 | 87933.5618 | Paid | 281 | 159748.5 | 161345.985 | 0.48 | 0.065 |  |  | 8176 | Kgs | [8 empty] | Arrived at Works |  | 22 | 1 | 3 | 12 | 3
Arrived | QEN | Engineering Item | Sample |  | TMPNL0092 |  | Welding Flux | [6 empty] | 25 | Kgs | [6 empty] | Qingdao Tensileweld | China |  | 43543 |  | 2026-04-23 | BAH | Advance |  | 3.13 | $ | 281 |  | 78.25 |  | 21988.25 |  |  |  | 8331.3 |  | FOB |  |  |  |  | Air |  |  |  | Lahore | 2026-05-14 | 2026-05-25 | 2026-05-26 |  |  |  | 2026-05-26 |  | EFS | 2026-06-02 | LPAF-HC-84523 |  | 2026-06-04 |  | 2 | 2026-06-04 |  | 0 | 0 | 2026-04-23 | 21988.25 | Paid |  |  |  | 2026-05-25 | 12103.4322 | Paid | 281 | 21988.25 | 22208.1325 | 0.48 | 0.065 |  |  | 5451 | Kgs | [8 empty] | Arrived at Works |  | 22 | 1 | 3 |  | 3
Shafts/Ongoing/Import Status/Import Rem | QCL | Refractory Material | Store |  | 26876-60 |  | Exothermic Riser Sleeves | BGK-5/FT-100-S150 | [5 empty] | 1152 | Pcs |  |  | 2026-03-25 |  | 2026-06-25 | 13.1429 | SQ | China |  | 43093 |  | 2026-04-13 | BAH | Advance |  | 3.08 | $ | 279.4 | 3548.16 | 3548.16 | 991355.904 | 991355.904 |  |  |  | 6903.901 | NO | FOB Qingdao |  | KMTC Manila |  |  | Sea | QDWJ26051431 |  | Qingdao | Karachi | 2026-04-25 | 2026-05-25 | 2026-06-22 | 2026-06-24 | 2026-07-02 |  | 2026-07-02 | 38 | EFS | [5 empty] | 0 | 2026-07-12 |  | 0 | -17 | 2026-04-13 | 991355.904 | Paid |  |  |  | 2026-04-30 | 315399.8809 | Paid | 279.4 | 991355.904 | 1001269.463 | 0.25 | 0.065 |  |  | 1233 | Pcs | [8 empty] | Under Custom Clearance |  | 3 | 1 | 1 | 7 | 2
Arrived | QE | Engineering Item | Engg. |  | 19550-60 |  | Portable Surface Roughness Tester | Time-3100 | [5 empty] | 2 | Pcs |  |  | 2026-03-09 |  | 2026-06-01 | 12 | Time Group Inc | China |  | 42764 |  | 2026-04-03 | BAH | Advance |  | 600 | $ | 279.25 |  | 1200 |  | 335100 |  |  |  | 9031.8 |  | CPT Lahore |  |  |  |  | Air |  |  |  | Lahore |  | 2026-04-21 | 2026-04-27 | 2026-04-30 |  |  | 2026-04-30 | 9 | [6 empty] | 0 | 2026-05-04 |  | 0 | 28 | 2026-04-03 | 335100 | Paid |  |  |  | 2026-04-30 | 106612.065 | Unpaid | 279.25 | 335100 | 338451 | 0.25 | 0.065 |  |  | 220268 | Pcs | [8 empty] | Arrived at Works |  | 23 |  | 3 |  | 1
Arrived | QCL | Refractory Material | Sample |  | TMPNL0093 |  | Zirconia Ceramic Foam | D125X22, 10PPI | [5 empty] | 10 | Pcs | [6 empty] | YC | China |  | 42700 |  | 2026-04-01 | BAH | Advance |  | 5.6 | $ | 279.5 | 3231.7312 | 56 | 903268.8844 | 15652 |  |  |  | 6903.901 |  | CFR Karachi |  | XIN CHANG SHU 102W |  |  | Sea | CMSQD26050026 |  | Qingdao | Karachi |  | 2026-05-11 | 2026-05-28 | 2026-06-01 | 2026-06-08 | 2026-06-09 | 2026-06-09 | 29 | [6 empty] | 0 | 2026-06-21 |  | 0 | 0 | 2026-04-01 | 15652 | Paid |  |  |  |  | 4663.5134 | Paid | 279.5 | 15652 | 15808.52 | 0.23 | 0.065 |  |  |  | Pcs | [8 empty] | Arrived at Works |  | 24 |  | 1 | 7 | 2
Arrived | QCL | Refractory Material | Sample |  | TMPNL0094 |  | Zirconia Ceramic Foam | D90X22, 10PPI | [5 empty] | 10 | Pcs | [6 empty] | YC | China |  | 42700 |  | 2026-04-01 | BAH | Advance |  | 2.93 | $ | 279.5 |  | 29.3 |  | 8189.35 |  |  |  | 6903.901 |  | CFR Karachi |  | XIN CHANG SHU 102W |  |  | Sea | CMSQD26050026 |  | Qingdao | Karachi |  | 2026-05-11 | 2026-05-28 | 2026-06-01 | 2026-06-08 | 2026-06-09 | 2026-06-09 | 29 | [6 empty] | 0 | 2026-06-21 |  | 0 | 0 | 2026-04-01 | 8189.35 | Paid |  |  |  |  | 2440.0168 | Paid | 279.5 | 8189.35 | 8271.2435 | 0.23 | 0.065 |  |  |  | Pcs | [8 empty] | Arrived at Works |  | 24 |  | 1 | 7 | 2
Arrived | QCL | Refractory Material | Sample |  | TMPNL0095 |  | Zirconia Ceramic Foam | D70X22, 10PPI | [5 empty] | 10 | Pcs | [6 empty] | YC | China |  | 42700 |  | 2026-04-01 | BAH | Advance |  | 1.77 | $ | 279.5 |  | 17.7 |  | 4947.15 |  |  |  | 6903.901 |  | CFR Karachi |  | XIN CHANG SHU 102W |  |  | Sea | CMSQD26050026 |  | Qingdao | Karachi |  | 2026-05-11 | 2026-05-28 | 2026-06-01 | 2026-06-08 | 2026-06-09 | 2026-06-09 | 29 | [6 empty] | 0 | 2026-06-21 |  | 0 | 0 | 2026-04-01 | 4947.15 | Paid |  |  |  |  | 1474.0033 | Paid | 279.5 | 4947.15 | 4996.6215 | 0.23 | 0.065 |  |  |  | Pcs | [8 empty] | Arrived at Works |  | 24 |  | 1 | 7 | 2
Arrived | QCL | Refractory Material | Sample |  | TMPNL0096 |  | Silicon Carbide Foam Ceramic Filter | D135X30, 10PPI | [5 empty] | 10 | Pcs | [6 empty] | YC | China |  | 42700 |  | 2026-04-01 | BAH | Advance |  | 0.77 | $ | 279.5 |  | 7.7 |  | 2152.15 |  |  |  | 6903.901 |  | CFR Karachi |  | XIN CHANG SHU 102W |  |  | Sea | CMSQD26050026 |  | Qingdao | Karachi |  | 2026-05-11 | 2026-05-28 | 2026-06-01 | 2026-06-08 | 2026-06-09 | 2026-06-09 | 29 | [6 empty] | 0 | 2026-06-21 |  | 0 | 0 | 2026-04-01 | 2152.15 | Paid |  |  |  |  | 641.2331 | Paid | 279.5 | 2152.15 | 2173.6715 | 0.23 | 0.065 |  |  |  | Pcs | [8 empty] | Arrived at Works |  | 24 |  | 1 | 7 | 2
Arrived | QCL | Refractory Material | Sample |  | TMPNL0097 |  | Silicon Carbide Foam Ceramic Filter | D70X30, 10PPI | [5 empty] | 10 | Pcs | [6 empty] | YC | China |  | 42700 |  | 2026-04-01 | BAH | Advance |  | 0.18 | $ | 279.5 |  | 1.8 |  | 503.1 |  |  |  | 6903.901 |  | CFR Karachi |  | XIN CHANG SHU 102W |  |  | Sea | CMSQD26050026 |  | Qingdao | Karachi |  | 2026-05-11 | 2026-05-28 | 2026-06-01 | 2026-06-08 | 2026-06-09 | 2026-06-09 | 29 | [6 empty] | 0 | 2026-06-21 |  | 0 | 0 | 2026-04-01 | 503.1 | Paid |  |  |  |  | 149.8986 | Paid | 279.5 | 503.1 | 508.131 | 0.23 | 0.065 |  |  |  | Pcs | [8 empty] | Arrived at Works |  | 24 |  | 1 | 7 | 2
Arrived | QCL | Refractory Material | Sample |  | TMPNL0098 |  | Silicon Carbide Foam Ceramic Filter | 75X75X22, 10PPI | [5 empty] | 10 | Pcs | [6 empty] | YC | China |  | 42700 |  | 2026-04-01 | BAH | Advance |  | 0.26 | $ | 279.5 |  | 2.6 |  | 726.7 |  |  |  | 6903.901 |  | CFR Karachi |  | XIN CHANG SHU 102W |  |  | Sea | CMSQD26050026 |  | Qingdao | Karachi |  | 2026-05-11 | 2026-05-28 | 2026-06-01 | 2026-06-08 | 2026-06-09 | 2026-06-09 | 29 | [6 empty] | 0 | 2026-06-21 |  | 0 | 0 | 2026-04-01 | 726.7 | Paid |  |  |  |  | 216.5203 | Paid | 279.5 | 726.7 | 733.967 | 0.23 | 0.065 |  |  |  | Pcs | [8 empty] | Arrived at Works |  | 24 |  | 1 | 7 | 2
Arrived | QCL | Refractory Material | Sample |  | TMPNL0099 |  | Riser Sleeves | YC-BS80 | [5 empty] | 10 | Pcs | [6 empty] | YC | China |  | 42700 |  | 2026-04-01 | BAH | Advance |  | 0.46 | $ | 279.5 |  | 4.6 |  | 1285.7 |  |  |  | 6903.901 |  | CFR Karachi |  | XIN CHANG SHU 102W |  |  | Sea | CMSQD26050026 |  | Qingdao | Karachi |  | 2026-05-11 | 2026-05-28 | 2026-06-01 | 2026-06-08 | 2026-06-09 | 2026-06-09 | 29 | [6 empty] | 0 | 2026-06-21 |  | 0 | 0 | 2026-04-01 | 1285.7 | Paid |  |  |  |  | 383.0743 | Paid | 279.5 | 1285.7 | 1298.557 | 0.23 | 0.065 |  |  |  | Pcs | [8 empty] | Arrived at Works |  | 24 |  | 1 | 7 | 2
Arrived | QCL | Refractory Material | Sample |  | TMPNL0100 |  | Riser Sleeves | YC-BS100 | [5 empty] | 10 | Pcs | [6 empty] | YC | China |  | 42700 |  | 2026-04-01 | BAH | Advance |  | 1.05 | $ | 279.5 |  | 10.5 |  | 2934.75 |  |  |  | 6903.901 |  | CFR Karachi |  | XIN CHANG SHU 102W |  |  | Sea | CMSQD26050026 |  | Qingdao | Karachi |  | 2026-05-11 | 2026-05-28 | 2026-06-01 | 2026-06-08 | 2026-06-09 | 2026-06-09 | 29 | [6 empty] | 0 | 2026-06-21 |  | 0 | 0 | 2026-04-01 | 2934.75 | Paid |  |  |  |  | 874.4088 | Paid | 279.5 | 2934.75 | 2964.0975 | 0.23 | 0.065 |  |  |  | Pcs | [8 empty] | Arrived at Works |  | 24 |  | 1 | 7 | 2
Arrived | QCL | Refractory Material | Sample |  | TMPNL0101 |  | Riser Sleeves | YC-BS120 | [5 empty] | 10 | Pcs | [6 empty] | YC | China |  | 42700 |  | 2026-04-01 | BAH | Advance |  | 1.69 | $ | 279.5 |  | 16.9 |  | 4723.55 |  |  |  | 6903.901 |  | CFR Karachi |  | XIN CHANG SHU 102W |  |  | Sea | CMSQD26050026 |  | Qingdao | Karachi |  | 2026-05-11 | 2026-05-28 | 2026-06-01 | 2026-06-08 | 2026-06-09 | 2026-06-09 | 29 | [6 empty] | 0 | 2026-06-21 |  | 0 | 0 | 2026-04-01 | 4723.55 | Paid |  |  |  |  | 1407.3817 | Paid | 279.5 | 4723.55 | 4770.7855 | 0.23 | 0.065 |  |  |  | Pcs | [8 empty] | Arrived at Works |  | 24 |  | 1 | 7 | 2
Arrived | QCL | Refractory Material | Sample |  | TMPNL0102 |  | Riser Sleeves | YC-BS130 | [5 empty] | 10 | Pcs | [6 empty] | YC | China |  | 42700 |  | 2026-04-01 | BAH | Advance |  | 2.79 | $ | 279.5 |  | 27.9 |  | 7798.05 |  |  |  | 6903.901 |  | CFR Karachi |  | XIN CHANG SHU 102W |  |  | Sea | CMSQD26050026 |  | Qingdao | Karachi |  | 2026-05-11 | 2026-05-28 | 2026-06-01 | 2026-06-08 | 2026-06-09 | 2026-06-09 | 29 | [6 empty] | 0 | 2026-06-21 |  | 0 | 0 | 2026-04-01 | 7798.05 | Paid |  |  |  |  | 2323.429 | Paid | 279.5 | 7798.05 | 7876.0305 | 0.23 | 0.065 |  |  |  | Pcs | [8 empty] | Arrived at Works |  | 24 |  | 1 | 7 | 2
Arrived | QCL | Refractory Material | Sample |  | TMPNL0103 |  | Riser Sleeves | YC-CS150 | [5 empty] | 10 | Pcs | [6 empty] | YC | China |  | 42700 |  | 2026-04-01 | BAH | Advance |  | 2.78 | $ | 279.5 |  | 27.8 |  | 7770.1 |  |  |  | 6903.901 |  | CFR Karachi |  | XIN CHANG SHU 102W |  |  | Sea | CMSQD26050026 |  | Qingdao | Karachi |  | 2026-05-11 | 2026-05-28 | 2026-06-01 | 2026-06-08 | 2026-06-09 | 2026-06-09 | 29 | [6 empty] | 0 | 2026-06-21 |  | 0 | 0 | 2026-04-01 | 7770.1 | Paid |  |  |  |  | 2315.1013 | Paid | 279.5 | 7770.1 | 7847.801 | 0.23 | 0.065 |  |  |  | Pcs | [8 empty] | Arrived at Works |  | 24 |  | 1 | 7 | 2
Arrived | QCL | Refractory Material | Sample |  | TMPNL0104 |  | Riser Sleeves | YC-CS180 | [5 empty] | 10 | Pcs | [6 empty] | YC | China |  | 42700 |  | 2026-04-01 | BAH | Advance |  | 4.06 | $ | 279.5 |  | 40.6 |  | 11347.7 |  |  |  | 6903.901 |  | CFR Karachi |  | XIN CHANG SHU 102W |  |  | Sea | CMSQD26050026 |  | Qingdao | Karachi |  | 2026-05-11 | 2026-05-28 | 2026-06-01 | 2026-06-08 | 2026-06-09 | 2026-06-09 | 29 | [6 empty] | 0 | 2026-06-21 |  | 0 | 0 | 2026-04-01 | 11347.7 | Paid |  |  |  |  | 3381.0472 | Paid | 279.5 | 11347.7 | 11461.177 | 0.23 | 0.065 |  |  |  | Pcs | [8 empty] | Arrived at Works |  | 24 |  | 1 | 7 | 2
Arrived | QCL | Refractory Material | Sample |  | TMPNL0105 |  | Riser Sleeves | YC-CS200 | [5 empty] | 10 | Pcs | [6 empty] | YC | China |  | 42700 |  | 2026-04-01 | BAH | Advance |  | 5.01 | $ | 279.5 |  | 50.1 |  | 14002.95 |  |  |  | 6903.901 |  | CFR Karachi |  | XIN CHANG SHU 102W |  |  | Sea | CMSQD26050026 |  | Qingdao | Karachi |  | 2026-05-11 | 2026-05-28 | 2026-06-01 | 2026-06-08 | 2026-06-09 | 2026-06-09 | 29 | [6 empty] | 0 | 2026-06-21 |  | 0 | 0 | 2026-04-01 | 14002.95 | Paid |  |  |  |  | 4172.179 | Paid | 279.5 | 14002.95 | 14142.9795 | 0.23 | 0.065 |  |  |  | Pcs | [8 empty] | Arrived at Works |  | 24 |  | 1 | 7 | 2
Arrived | QCL | Refractory Material | Sample |  | TMPNL0106 |  | Riser Sleeves | YC-CS225 | [5 empty] | 10 | Pcs | [6 empty] | YC | China |  | 42700 |  | 2026-04-01 | BAH | Advance |  | 6.71 | $ | 279.5 |  | 67.1 |  | 18754.45 |  |  |  | 6903.901 |  | CFR Karachi |  | XIN CHANG SHU 102W |  |  | Sea | CMSQD26050026 |  | Qingdao | Karachi |  | 2026-05-11 | 2026-05-28 | 2026-06-01 | 2026-06-08 | 2026-06-09 | 2026-06-09 | 29 | [6 empty] | 0 | 2026-06-21 |  | 0 | 0 | 2026-04-01 | 18754.45 | Paid |  |  |  |  | 5587.8884 | Paid | 279.5 | 18754.45 | 18941.9945 | 0.23 | 0.065 |  |  |  | Pcs | [8 empty] | Arrived at Works |  | 24 |  | 1 | 7 | 2
Arrived | QCL | Refractory Material | Sample |  | TMPNL0107 |  | Riser Sleeves | YC-CS250 | [5 empty] | 5 | Pcs | [6 empty] | YC | China |  | 42700 |  | 2026-04-01 | BAH | Advance |  | 9.77 | $ | 279.5 |  | 48.85 |  | 13653.575 |  |  |  | 6903.901 |  | CFR Karachi |  | XIN CHANG SHU 102W |  |  | Sea | CMSQD26050026 |  | Qingdao | Karachi |  | 2026-05-11 | 2026-05-28 | 2026-06-01 | 2026-06-08 | 2026-06-09 | 2026-06-09 | 29 | [6 empty] | 0 | 2026-06-21 |  | 0 | 0 | 2026-04-01 | 13653.575 | Paid |  |  |  |  | 4068.0827 | Paid | 279.5 | 13653.575 | 13790.1107 | 0.23 | 0.065 |  |  |  | Pcs | [8 empty] | Arrived at Works |  | 24 |  | 1 | 7 | 2
Arrived | QCL | Refractory Material | Sample |  | TMPNL0108 |  | Riser Sleeves | YC-CS300 | [5 empty] | 5 | Pcs | [6 empty] | YC | China |  | 42700 |  | 2026-04-01 | BAH | Advance |  | 13.07 | $ | 279.5 |  | 65.35 |  | 18265.325 |  |  |  | 6903.901 |  | CFR Karachi |  | XIN CHANG SHU 102W |  |  | Sea | CMSQD26050026 |  | Qingdao | Karachi |  | 2026-05-11 | 2026-05-28 | 2026-06-01 | 2026-06-08 | 2026-06-09 | 2026-06-09 | 29 | [6 empty] | 0 | 2026-06-21 |  | 0 | 0 | 2026-04-01 | 18265.325 | Paid |  |  |  |  | 5442.1536 | Paid | 279.5 | 18265.325 | 18447.9783 | 0.23 | 0.065 |  |  |  | Pcs | [8 empty] | Arrived at Works |  | 24 |  | 1 | 7 | 2
Arrived | QCL | Refractory Material | Sample |  | TMPNL0109 |  | Riser Sleeves | YC-CS350 | [5 empty] | 5 | Pcs | [6 empty] | YC | China |  | 42700 |  | 2026-04-01 | BAH | Advance |  | 19.34 | $ | 279.5 |  | 96.7 |  | 27027.65 |  |  |  | 6903.901 |  | CFR Karachi |  | XIN CHANG SHU 102W |  |  | Sea | CMSQD26050026 |  | Qingdao | Karachi |  | 2026-05-11 | 2026-05-28 | 2026-06-01 | 2026-06-08 | 2026-06-09 | 2026-06-09 | 29 | [6 empty] | 0 | 2026-06-21 |  | 0 | 0 | 2026-04-01 | 27027.65 | Paid |  |  |  |  | 8052.8883 | Paid | 279.5 | 27027.65 | 27297.9265 | 0.23 | 0.065 |  |  |  | Pcs | [8 empty] | Arrived at Works |  | 24 |  | 1 | 7 | 2
Arrived | QCL | Refractory Material | Sample |  | TMPNL0110 |  | Riser Sleeves | YC-CT85/160/100 | [5 empty] | 10 | Pcs | [6 empty] | YC | China |  | 42700 |  | 2026-04-01 | BAH | Advance |  | 1.23 | $ | 279.5 |  | 12.3 |  | 3437.85 |  |  |  | 6903.901 |  | CFR Karachi |  | XIN CHANG SHU 102W |  |  | Sea | CMSQD26050026 |  | Qingdao | Karachi |  | 2026-05-11 | 2026-05-28 | 2026-06-01 | 2026-06-08 | 2026-06-09 | 2026-06-09 | 29 | [6 empty] | 0 | 2026-06-21 |  | 0 | 0 | 2026-04-01 | 3437.85 | Paid |  |  |  |  | 1024.3074 | Paid | 279.5 | 3437.85 | 3472.2285 | 0.23 | 0.065 |  |  |  | Pcs | [8 empty] | Arrived at Works |  | 24 |  | 1 | 7 | 2
Arrived | QCL | Refractory Material | Sample |  | TMPNL0111 |  | Riser Sleeves | YC-CT100/200/200 | [5 empty] | 10 | Pcs | [6 empty] | YC | China |  | 42700 |  | 2026-04-01 | BAH | Advance |  | 3.29 | $ | 279.5 |  | 32.9 |  | 9195.55 |  |  |  | 6903.901 |  | CFR Karachi |  | XIN CHANG SHU 102W |  |  | Sea | CMSQD26050026 |  | Qingdao | Karachi |  | 2026-05-11 | 2026-05-28 | 2026-06-01 | 2026-06-08 | 2026-06-09 | 2026-06-09 | 29 | [6 empty] | 0 | 2026-06-21 |  | 0 | 0 | 2026-04-01 | 9195.55 | Paid |  |  |  |  | 2739.8141 | Paid | 279.5 | 9195.55 | 9287.5055 | 0.23 | 0.065 |  |  |  | Pcs | [8 empty] | Arrived at Works |  | 24 |  | 1 | 7 | 2
Arrived | QCL | Refractory Material | Sample |  | TMPNL0112 |  | Riser Sleeves | YC-CT120/240/200 | [5 empty] | 10 | Pcs | [6 empty] | YC | China |  | 42700 |  | 2026-04-01 | BAH | Advance |  | 3.63 | $ | 279.5 |  | 36.3 |  | 10145.85 |  |  |  | 6903.901 |  | CFR Karachi |  | XIN CHANG SHU 102W |  |  | Sea | CMSQD26050026 |  | Qingdao | Karachi |  | 2026-05-11 | 2026-05-28 | 2026-06-01 | 2026-06-08 | 2026-06-09 | 2026-06-09 | 29 | [6 empty] | 0 | 2026-06-21 |  | 0 | 0 | 2026-04-01 | 10145.85 | Paid |  |  |  |  | 3022.956 | Paid | 279.5 | 10145.85 | 10247.3085 | 0.23 | 0.065 |  |  |  | Pcs | [8 empty] | Arrived at Works |  | 24 |  | 1 | 7 | 2
Arrived | QCL | Foundry Material | Sample |  | TMPNL0113 |  | Neutral Ramming Mass | [6 empty] | 0.75 | Kgs | [6 empty] | YC | China |  | 42700 |  | 2026-04-01 | BAH | Advance |  | 1471.28 | $ | 279.5 |  | 1103.46 |  | 308417.07 |  |  |  | 3816 |  | CFR Karachi |  | XIN CHANG SHU 102W |  |  | Sea | CMSQD26050026 |  | Qingdao | Karachi |  | 2026-05-11 | 2026-05-28 | 2026-06-01 | 2026-06-08 | 2026-06-09 | 2026-06-09 | 29 | [6 empty] | 0 | 2026-06-21 |  | 0 | 0 | 2026-04-01 | 308417.07 | Paid |  |  |  |  | 91892.866 | Paid | 279.5 | 308417.07 | 311501.2407 | 0.23 | 0.065 |  |  |  | Kgs | [8 empty] | Arrived at Works |  | 24 |  | 1 | 7 | 2
Arrived | QCL | Foundry Material | Sample |  | TMPNL0114 |  | Liquid Phenolic Resin | YC-JF968 | [5 empty] | 1 | Ton | [6 empty] | YC | China |  | 42700 |  | 2026-04-01 | BAH | Advance |  | 925 | $ | 279.5 |  | 925 |  | 258537.5 |  |  |  | 3824.1 |  | CFR Karachi |  | XIN CHANG SHU 102W |  |  | Sea | CMSQD26050026 |  | Qingdao | Karachi |  | 2026-05-11 | 2026-05-28 | 2026-06-01 | 2026-06-08 | 2026-06-09 | 2026-06-09 | 29 | [6 empty] | 0 | 2026-06-21 |  | 0 | 0 | 2026-04-01 | 258537.5 | Paid |  |  |  |  | 77031.2481 | Paid | 279.5 | 258537.5 | 261122.875 | 0.23 | 0.065 |  |  |  | Ton | [8 empty] | Arrived at Works |  | 24 |  | 1 | 7 | 2
Arrived | QCL | Foundry Material | Sample |  | 2823-60 |  | Exothermic Powder | [6 empty] | 0.025 | Kgs | [6 empty] | YC | China |  | 42700 |  | 2026-04-01 | BAH | Advance |  | 899.85 | $ | 279.5 |  | 22.4962 |  | 6287.7019 |  |  |  | 3824.1 |  | CFR Karachi |  | XIN CHANG SHU 102W |  |  | Sea | CMSQD26050026 |  | Qingdao | Karachi |  | 2026-05-11 | 2026-05-28 | 2026-06-01 | 2026-06-08 | 2026-06-09 | 2026-06-09 | 29 | [6 empty] | 0 | 2026-06-21 |  | 0 | 0 | 2026-04-01 | 6287.7019 | Paid |  |  |  |  | 1873.4208 | Paid | 279.5 | 6287.7019 | 6350.5789 | 0.23 | 0.065 |  |  |  | Kgs | [8 empty] | Arrived at Works |  | 24 |  | 1 | 7 | 2
Arrived | QCL | Foundry Material | Sample |  | TMPNL0115 |  | Curing Agent for Phenolic Resin | YC-JFG60 | [5 empty] | 0.125 | Kgs | [6 empty] | YC | China |  | 42700 |  | 2026-04-01 | BAH | Advance |  | 1494 | $ | 279.5 |  | 186.75 |  | 52196.625 |  |  |  | 3824.1 |  | CFR Karachi |  | XIN CHANG SHU 102W |  |  | Sea | CMSQD26050026 |  | Qingdao | Karachi |  | 2026-05-11 | 2026-05-28 | 2026-06-01 | 2026-06-08 | 2026-06-09 | 2026-06-09 | 29 | [6 empty] | 0 | 2026-06-21 |  | 0 | 0 | 2026-04-01 | 52196.625 | Paid |  |  |  |  | 15551.9844 | Paid | 279.5 | 52196.625 | 52718.5912 | 0.23 | 0.065 |  |  |  | Kgs | [8 empty] | Arrived at Works |  | 24 |  | 1 | 7 | 2
Arrived | QCL | Foundry Material | Sample |  | TMPNL0116 |  | Curing Agent for Phenolic Resin | YC-JFG10 | [5 empty] | 0.125 | Kgs | [6 empty] | YC | China |  | 42700 |  | 2026-04-01 | BAH | Advance |  | 1615 | $ | 279.5 |  | 201.875 |  | 56424.0625 |  |  |  | 3824.1 |  | CFR Karachi |  | XIN CHANG SHU 102W |  |  | Sea | CMSQD26050026 |  | Qingdao | Karachi |  | 2026-05-11 | 2026-05-28 | 2026-06-01 | 2026-06-08 | 2026-06-09 | 2026-06-09 | 29 | [6 empty] | 0 | 2026-06-21 |  | 0 | 0 | 2026-04-01 | 56424.0625 | Paid |  |  |  |  | 16811.5494 | Paid | 279.5 | 56424.0625 | 56988.3031 | 0.23 | 0.065 |  |  |  | Kgs | [8 empty] | Arrived at Works |  | 24 |  | 1 | 7 | 2
Arrived | QCL | Foundry Material | Sample |  | TMPNL0117 |  | Alcohol Based Zirconia Coating | GT-02 | [5 empty] | 0.1 | Kgs | [6 empty] | YC | China |  | 42700 |  | 2026-04-01 | BAH | Advance |  | 0 | $ | 279.5 |  | 0 |  | 0 |  |  |  | 3824.1 |  | CFR Karachi |  | XIN CHANG SHU 102W |  |  | Sea | CMSQD26050026 |  | Qingdao | Karachi |  | 2026-05-11 | 2026-05-28 | 2026-06-01 | 2026-06-08 | 2026-06-09 | 2026-06-09 | 29 | [6 empty] | 0 | 2026-06-21 |  | 0 | 0 | 2026-04-01 | 0 | Paid |  |  |  |  | 0 | Paid | 279.5 | 0 | 0 | 0.23 | 0.065 |  |  |  | Kgs | [8 empty] | Arrived at Works |  | 24 |  | 1 | 7 | 2
Arrived | QCL | Foundry Material | Sample |  | TMPNL0118 |  | Alcohol Based Silica andGraphite Coating | BT-01A | [5 empty] | 0.1 | Kgs | [6 empty] | YC | China |  | 42700 |  | 2026-04-01 | BAH | Advance |  | 728.5 | $ | 279.5 |  | 72.85 |  | 20361.575 |  |  |  | 3824.1 |  | CFR Karachi |  | XIN CHANG SHU 102W |  |  | Sea | CMSQD26050026 |  | Qingdao | Karachi |  | 2026-05-11 | 2026-05-28 | 2026-06-01 | 2026-06-08 | 2026-06-09 | 2026-06-09 | 29 | [6 empty] | 0 | 2026-06-21 |  | 0 | 0 | 2026-04-01 | 20361.575 | Paid |  |  |  |  | 6066.7313 | Paid | 279.5 | 20361.575 | 20565.1908 | 0.23 | 0.065 |  |  |  | Kgs | [8 empty] | Arrived at Works |  | 24 |  | 1 | 7 | 2
Arrived | QCL | Foundry Material | Sample |  | TMPNL0119 |  | Alcohol Based Magnesite Coating | MT-02A | [5 empty] | 0.1 | Kgs | [6 empty] | YC | China |  | 42700 |  | 2026-04-01 | BAH | Advance |  | 663 | $ | 279.5 |  | 66.3 |  | 18530.85 |  |  |  | 3824.1 |  | CFR Karachi |  | XIN CHANG SHU 102W |  |  | Sea | CMSQD26050026 |  | Qingdao | Karachi |  | 2026-05-11 | 2026-05-28 | 2026-06-01 | 2026-06-08 | 2026-06-09 | 2026-06-09 | 29 | [6 empty] | 0 | 2026-06-21 |  | 0 | 0 | 2026-04-01 | 18530.85 | Paid |  |  |  |  | 5521.2668 | Paid | 279.5 | 18530.85 | 18716.1585 | 0.23 | 0.065 |  |  |  | Kgs | [8 empty] | Arrived at Works |  | 24 |  | 1 | 7 | 2
Arrived | QCL | Cutting Tools | Store |  | 6939-60 |  | High Carbon Steel Shots | [6 empty] | 3 | Ton |  |  | 2026-02-24 |  | 2026-05-24 |  | Tengzhou Feng ERDA Metal | China |  | 42566 |  | 2026-03-27 | BAH | Advance |  | 625 | $ | 279.3 | 1875 | 1875 | 523687.5 | 523687.5 |  |  |  | 7205.1 |  | FOB |  | TS Kelang/2601W |  |  | Sea | QDGKHI6288608V |  | Qingdao | Karachi |  | 2026-04-12 | 2026-05-09 |  |  |  | 2026-05-09 | 27 | EFS | 2026-05-11 | KAPE-HC-67679 |  | 2026-05-15 |  | 4 | 2026-05-20 |  | 0 | 4 | 2026-03-27 | 523687.5 | Paid |  |  |  |  | 156032.6906 | Paid | 279.3 | 523687.5 | 528924.375 | 0.23 | 0.065 |  |  | 253 | Kgs | [8 empty] | Arrived at Works | Shipment bookin has been received ETD: 12-04-26 | 25 | 1 | 1 | 7 | 2
Arrived | QCL | Refractory Material | Store |  | 14090-60 |  | Ceramic Foam Filters | 70x22 10 PPI | [5 empty] | 1000 | Pcs | [6 empty] | Shanxi Fuqian | China |  | 42564 |  | 2026-03-27 | BAH | Advance |  | 1.41 | $ | 279.3 | 2310 | 1410 | 645183 | 393813 |  |  |  | 6903.901 |  | FOB |  | OOCL Nagoya | VanGuard | Quick Freight | Sea | SHGKHI6302366V |  | Shanghai | Karachi |  | 2026-04-16 | 2026-05-02 |  |  |  | 2026-05-02 | 16 | EFS | 2026-05-04 | KAPW-HC-194095 |  | 2026-05-06 |  | 2 | 2026-05-12 |  | 0 | 0 | 2026-03-27 | 393813 | Paid |  |  |  | 2026-05-04 | 125291.6059 | Paid | 279.3 | 393813 | 397751.13 | 0.25 | 0.065 |  |  | 573 | Pcs | [8 empty] | Arrived at Works | Shipment Bookin received ETD:11-04-26 | 26 | 1 | 1 | 4 | 2
Arrived | QCL | Refractory Material | Store |  | 24927-60 |  | Ceramic Foam Filters | Dia125x22/10 PPI | [5 empty] | 200 | Pcs | [6 empty] | Shanxi Fuqian | China |  | 42564 |  | 2026-03-27 | BAH | Advance |  | 4.5 | $ | 279.3 |  | 900 |  | 251370 |  |  |  | 6903.901 |  | FOB |  | OOCL Nagoya | VanGuard | Quick Freight | Sea | SHGKHI6302366V |  | Shanghai | Karachi |  | 2026-04-16 | 2026-05-02 |  |  |  | 2026-05-02 | 16 | EFS | 2026-05-04 | KAPW-HC-194095 |  | 2026-05-06 |  | 2 | 2026-05-12 |  | 0 | 0 | 2026-03-27 | 251370 | Paid |  |  |  | 2026-05-04 | 79973.3655 | Paid | 279.3 | 251370 | 253883.7 | 0.25 | 0.065 |  |  | 1502 | Pcs | [8 empty] | Arrived at Works | Shipment Bookin received ETD:11-04-26 | 26 | 1 | 1 | 4 | 2
Arrived | QE | Engineering Item | Engg. |  | TMPNL0120 |  | Hot Rolled Plate(30*2000*7500) | SA572 Gr.65 |  |  | CE26-FLMX-0093 | CE26-MO-0153 |  | 3.533 | Ton |  |  | 2026-03-06 |  | 2026-04-17 | 6 | SMC | China |  | 42452 |  | 2026-03-25 | BAH | Advance |  | 965 | $ | 280 |  | 3409.345 |  | 954616.6 |  |  |  | 7208.519 | NO | FOB |  |  |  |  | By Sea |  |  |  | Karachi |  | 2026-05-21 | 2026-06-07 | 2026-06-10 | 2026-06-12 |  | 2026-06-12 | 22 | [6 empty] | 0 | 2026-06-23 |  | 0 | -67 | 2026-03-25 | 954616.6 | Paid |  |  |  | 2026-06-15 | 313352.899 | Paid | 280 | 954616.6 | 964162.766 | 0.26 | 0.065 |  |  | 410 | Kg | [8 empty] | Arrived at Works | Vessel roll over from 30-04-26 to 11-05-2026 and now 15-05-2026 and now 21-05-2026 due to forwarders mishandling in container arrangment. | 27 |  | 1 |  | 1
Arrived | QBL-II | Foundry Material | Store |  | TMPNL0121 |  | Slag Remover(Casting Perlite) | 0.6-1.2mm | [5 empty] | 5000 | Kgs |  |  | 2025-12-14 |  | 2026-03-23 | 99 | Cukurova | Turkey |  | 40739 |  | 2026-01-22 | HMB | LC |  | 0.15 | £ | 327.5 |  | 750 |  | 245625 |  |  |  | 2530.1 |  | FOB Izmir |  |  |  | CAGOFY LOGISTICS | Sea | 26IST5550571 |  | Aliaga | Karachi |  | 2026-03-13 | 2026-03-31 |  |  |  | 2026-03-31 | 18 | EFS | 2026-03-31 | KAPW-HC-177724 |  | 2026-04-04 |  | 4 | 2026-04-14 | 0 | 0 | -22 | 2026-01-22 | 245625 | Paid |  |  |  | 2026-02-05 | 73183.9688 | Paid | 327.5 | 245625 | 248081.25 | 0.23 | 0.065 |  |  | 138 | Kgs | 191 |  | 2026-06-12 | 44 |  |  |  |  | Arrived at Works | Logistics is arranging LCL mvement from Karachi to Lahore | 11 | 1 | 1 | 9 | 4
Arrived | QCL | Ferro Alloys | Store |  | 2825-156 |  | Ferro Manganese H/C | MN 70%,SI 2%,C 6-8% | [5 empty] | 23 | Ton |  |  | 2026-03-10 |  | 2026-06-11 | 13.2857 | JC Resources | Korea |  | 33803 |  | 2026-05-06 | BAH | CAD |  | 1035 | $ | 278.85 |  | 23805 |  | 6638024.25 |  |  |  | 7202.11 |  | CFR Karachi |  | Melbourne Bridge | TS Lines |  | Sea | 380610012489 |  |  | Karachi |  | 2026-04-19 | 2026-05-10 | 2026-05-22 | 2026-05-24 |  | 2026-05-24 | 35 | EFS | [5 empty] | 0 | 2026-06-08 |  | 0 | 3 |  |  |  | 2026-05-06 | 6638024.25 | Paid | 2026-04-30 | 1977799.3253 | Paid | 278.85 | 6638024.25 | 6704404.4925 | 0.23 | 0.065 |  |  | 322 | Kgs | [8 empty] | Arrived at Works | Arrival at QFL: 03-06-2026. | 13 | 1 | 1 |  | 2
Arrived | QCL | Refractory Material | Store |  | TMPNL0122 |  | Riser Sleeves | FT100-S150 | [5 empty] | 3168 | Pcs |  |  | 2026-02-24 |  | 2026-05-24 | 12.7143 | SQ | China |  | 33771 |  | 2026-05-06 | BAH | CAD |  | 3.604 | $ | 282 | 17464.352 | 11417.472 | 4924947.264 | 3219727.104 |  |  |  | 6903.901 |  | CFR Karachi |  |  | TS Lines | Sharaf Shipping | Sea | 799610180959 |  | Qingdao | Karachi |  | 2026-04-13 | 2026-05-09 | 2026-05-11 |  |  | 2026-05-11 | 28 |  | 2026-05-12 | KAPS-HC-192196 |  | 2026-05-13 |  | 1 | 2026-05-18 |  | 0 | 6 |  |  |  | 2026-04-10 | 3219727.104 | Paid |  | 1056875.4219 | Paid | 282 | 3219727.104 | 3251924.375 | 0.26 | 0.065 |  |  | 1078 | Pcs | [8 empty] | Arrived at Works |  | 3 |  | 1 | 7 | 2
Arrived | QCL | Refractory Material | Store |  | TMPNL0123 |  | Riser Sleeves | FT100-S180 | [5 empty] | 560 | Pcs |  |  | 2026-02-10 |  | 2026-05-10 | 12.7143 | SQ | China |  | 33771 |  | 2026-05-06 | BAH | CAD |  | 4.714 | $ | 282 |  | 2639.84 |  | 744434.88 |  |  |  | 6903.901 |  | CFR Karachi |  |  | TS Lines | Sharaf Shipping | Sea | 799610180959 |  | Qingdao | Karachi |  | 2026-04-13 | 2026-05-09 | 2026-05-11 |  |  | 2026-05-11 | 28 |  | 2026-05-12 | KAPS-HC-192196 |  | 2026-05-13 |  | 1 | 2026-05-18 |  | 0 | -8 |  |  |  | 2026-04-10 | 744434.88 | Paid |  | 244360.7494 | Paid | 282 | 744434.88 | 751879.2288 | 0.26 | 0.065 |  |  | 1401 | Pcs | [8 empty] | Arrived at Works |  | 3 |  | 1 | 7 | 2
Arrived | QCL | Refractory Material | Store |  | TMPNL0124 |  | Riser Sleeves | FT100-S200 | [5 empty] | 560 | Pcs |  |  | 2026-02-24 |  | 2026-05-24 | 12.7143 | SQ | China |  | 33771 |  | 2026-05-06 | BAH | CAD |  | 6.084 | $ | 282 |  | 3407.04 |  | 960785.28 |  |  |  | 6903.901 |  | CFR Karachi |  |  | TS Lines | Sharaf Shipping | Sea | 799610180959 |  | Qingdao | Karachi |  | 2026-04-13 | 2026-05-09 | 2026-05-11 |  |  | 2026-05-11 | 28 |  | 2026-05-12 | KAPS-HC-192196 |  | 2026-05-13 |  | 1 | 2026-05-18 |  | 0 | 6 |  |  |  | 2026-04-10 | 960785.28 | Paid |  | 315377.7682 | Paid | 282 | 960785.28 | 970393.1328 | 0.26 | 0.065 |  |  | 1807 | Pcs | [8 empty] | Arrived at Works |  | 3 |  | 1 | 7 | 2
Arrived | QCL | Foundry Material | Store |  | 2818-156 |  | Ferro Chrome L/C | C 0.1%, Cr 60%, Si 1.5% Max, S 0.05%, P 0.05% | [5 empty] | 9.81 | Ton |  |  | 2026-02-24 |  | 2026-05-24 | 12.7143 | JC Resources | South Korea | Seoul | 31539 |  | 2026-04-21 | BAH | CAD |  | 2550 | $ | 279.4 | 25015.5 | 25015.5 | 6989330.7 | 6989330.7 |  |  |  | 7202.49 | YES | CFR Karachi |  |  |  |  | Sea | GLSSKHI260008 |  | Busan | Karachi |  | 2026-04-03 | 2026-04-25 | 2026-04-29 | 2026-05-04 | 2026-05-10 | 2026-05-10 | 37 | EFS | 2026-05-11 | KAPW-FS-198720 |  | 2026-05-14 |  | 3 | 2026-05-20 |  | 0 | 4 |  |  |  | 2026-04-21 | 6989330.7 | Paid |  | 1870694.3619 | Paid | 279.4 | 6989330.7 | 7059224.007 | 0.2 | 0.065 |  |  | 778 | kg | [8 empty] | Arrived at Works |  | 13 | 1 | 1 | 13 | 2
Arrived | QCL | Foundry Material | Store |  | TMPNL0125 |  | Hardener | HQG-60 | [5 empty] | 6 | Ton |  |  | 2026-01-13 |  | 2026-04-13 | 12.8571 | SQ | China |  | 31193 |  | 2026-04-21 | BAH | CAD |  | 1515 | $ | 279.4 | 26919.42 | 9090 | 7521285.948 | 2539746 |  |  |  | 3824.1 | YES | CFR Karachi |  |  | TS Lines | Sharaf Shipping | Sea | 799610134310 |  | Qingdao | Karachi |  | 2026-03-23 | 2026-04-14 | 2026-04-14 | 2026-04-20 | 2026-04-23 | 2026-04-23 | 31 |  | 2026-04-23 | KAPS-FS-182279 |  | 2026-04-24 |  | 1 | 2026-04-28 |  | 0 | -15 |  |  |  | 2026-04-21 | 2539746 | Paid | 2026-04-14 | 731065.8861 | Paid | 279.4 | 2539746 | 2565143.46 | 0.22 | 0.065 |  |  | 467 | Kg | [8 empty] | Arrived at Works | For QCL only. | 3 |  | 1 | 7 | 2
Arrived | QCL | Foundry Material | Store |  | TMPNL0126 |  | Coating | RISA-5107 | [5 empty] | 4.746 | Ton |  |  | 2026-01-13 |  | 2026-04-13 | 12.8571 | SQ | China |  | 31193 |  | 2026-04-21 | BAH | CAD |  | 770 | $ | 279.4 |  | 3654.42 |  | 1021044.948 |  |  |  | 3824.1 | YES | CFR Karachi |  |  | TS Lines | Sharaf Shipping | Sea | 799610134310 |  | Qingdao | Karachi |  | 2026-03-23 | 2026-04-14 | 2026-04-14 | 2026-04-20 | 2026-04-23 | 2026-04-23 | 31 |  | 2026-04-23 | KAPS-FS-182279 |  | 2026-04-24 |  | 1 | 2026-04-28 |  | 0 | -15 |  |  |  | 2026-04-21 | 1021044.948 | Paid | 2026-04-14 | 293907.7883 | Paid | 279.4 | 1021044.948 | 1031255.3975 | 0.22 | 0.065 |  |  | 246 | Kg | [8 empty] | Arrived at Works | 2.746 Ton for QCL & 2 Ton for QBL-II | 3 |  | 1 | 7 | 2
Arrived | QCL | Foundry Material | Store |  | TMPNL0127 |  | Coating | RISA-5100 | [5 empty] | 7.5 | Ton |  |  | 2026-01-27 |  | 2026-04-27 | 12.8571 | SQ | China |  | 31193 |  | 2026-04-21 | BAH | CAD |  | 1890 | $ | 279.4 |  | 14175 |  | 3960495 |  |  |  | 3824.1 | YES | CFR Karachi |  |  | TS Lines | Sharaf Shipping | Sea | 799610134310 |  | Qingdao | Karachi |  | 2026-03-23 | 2026-04-14 | 2026-04-14 | 2026-04-20 | 2026-04-23 | 2026-04-23 | 31 |  | 2026-04-23 | KAPS-FS-182279 |  | 2026-04-24 |  | 1 | 2026-04-28 |  | 0 | -1 |  |  |  | 2026-04-21 | 3960495 | Paid | 2026-04-14 | 1140028.4857 | Paid | 279.4 | 3960495 | 4000099.95 | 0.22 | 0.065 |  |  | 577 | Kg | [8 empty] | Arrived at Works | 2.5 Ton for QCL & 5 Ton for QBL-II | 3 |  | 1 | 7 | 2
Arrived | QBL-II | Refractory Material | Store |  | 16784-60 |  | T Pipe brick | Dia60 | [5 empty] | 560 | Pcs |  |  | 2026-01-27 |  | 2026-04-27 |  | One Piece | China |  | 29487 |  | 2026-04-08 | BAH | CAD |  | 4.74 | ¥ | 40.95 | 81239.98 | 2654.4 | 3326777.181 | 108697.68 |  |  |  | 6903.901 |  | CFR Karachi |  | OOCL LE HARVE | Yang Ming |  | Sea | YMJAS237026038 |  | Shanghai | Karachi | 2026-03-18 | 2026-03-22 | 2026-04-11 |  |  |  | 2026-04-11 | 20 | EFS | 2026-04-13 | KAPW-HC-183831 |  | 2026-04-14 |  | 1 | 2026-04-18 | 0 | 0 | 9 |  |  |  | 2026-04-06 | 108697.68 | Paid | 2026-04-13 | 31288.6272 | Paid | 40.95 | 108697.68 | 109784.6568 | 0.22 | 0.065 |  |  | 218 | Pcs | [8 empty] | Arrived at Works |  | 9 | 1 | 1 | 4 | 4
Arrived | QBL-II | Refractory Material | Store |  | 16781-60 |  | Straight Pipe | Dia60,L300 | [5 empty] | 3045 | Pcs |  |  | 2026-01-27 |  | 2026-04-27 |  | One Piece | China |  | 29487 |  | 2026-04-08 | BAH | CAD |  | 5.7 | ¥ | 40.95 |  | 17356.5 |  | 710748.675 |  |  |  | 6903.901 |  | CFR Karachi |  | OOCL LE HARVE | Yang Ming |  | Sea | YMJAS237026038 |  | Shanghai | Karachi | 2026-03-18 | 2026-03-22 | 2026-04-11 |  |  |  | 2026-04-11 | 20 | EFS | 2026-04-13 | KAPW-HC-183831 |  | 2026-04-14 |  | 1 | 2026-04-18 | 0 | 0 | 9 |  |  |  | 2026-04-06 | 710748.675 | Paid | 2026-04-13 | 204589.0061 | Paid | 40.95 | 710748.675 | 717856.1618 | 0.22 | 0.065 |  |  | 265 | Pcs | [8 empty] | Arrived at Works |  | 9 | 1 | 1 | 4 | 4
Arrived | QBL-II | Refractory Material | Store |  | 16878-60 |  | Straight Pipe | Dia80,L300 | [5 empty] | 1260 | Pcs |  |  | 2026-01-27 |  | 2026-04-27 |  | One Piece | China |  | 29487 |  | 2026-04-08 | BAH | CAD |  | 8.65 | ¥ | 40.95 |  | 10899 |  | 446314.05 |  |  |  | 6903.901 |  | CFR Karachi |  | OOCL LE HARVE | Yang Ming |  | Sea | YMJAS237026038 |  | Shanghai | Karachi | 2026-03-18 | 2026-03-22 | 2026-04-11 |  |  |  | 2026-04-11 | 20 | EFS | 2026-04-13 | KAPW-HC-183831 |  | 2026-04-14 |  | 1 | 2026-04-18 | 0 | 0 | 9 |  |  |  | 2026-04-06 | 446314.05 | Paid | 2026-04-13 | 128471.4993 | Paid | 40.95 | 446314.05 | 450777.1905 | 0.22 | 0.065 |  |  | 411 | Pcs | [8 empty] | Arrived at Works |  | 9 | 1 | 1 | 4 | 4
Arrived | QBL-II | Refractory Material | Store |  | TMPNL0128 |  | Right Angle Elbow | Dia60 | [5 empty] | 840 | Pcs |  |  | 2026-01-27 |  | 2026-04-27 |  | One Piece | China |  | 29487 |  | 2026-04-08 | BAH | CAD |  | 4.21 | ¥ | 40.95 |  | 3536.4 |  | 144815.58 |  |  |  | 6903.901 |  | CFR Karachi |  | OOCL LE HARVE | Yang Ming |  | Sea | YMJAS237026038 |  | Shanghai | Karachi | 2026-03-18 | 2026-03-22 | 2026-04-11 |  |  |  | 2026-04-11 | 20 | EFS | 2026-04-13 | KAPW-HC-183831 |  | 2026-04-14 |  | 1 | 2026-04-18 | 0 | 0 | 9 |  |  |  | 2026-04-06 | 144815.58 | Paid | 2026-04-13 | 41685.1647 | Paid | 40.95 | 144815.58 | 146263.7358 | 0.22 | 0.065 |  |  | 190 | Pcs | [8 empty] | Arrived at Works |  | 9 | 1 | 1 | 4 | 4
Arrived | QBL-II | Refractory Material | Store |  | TMPNL0129 |  | Pouring Basin | Dia170-60 | [5 empty] | 360 | Pcs |  |  | 2026-01-27 |  | 2026-04-27 |  | One Piece | China |  | 29487 |  | 2026-04-08 | BAH | CAD |  | 12.56 | ¥ | 40.95 |  | 4521.6 |  | 185159.52 |  |  |  | 6903.901 |  | CFR Karachi |  | OOCL LE HARVE | Yang Ming |  | Sea | YMJAS237026038 |  | Shanghai | Karachi | 2026-03-18 | 2026-03-22 | 2026-04-11 |  |  |  | 2026-04-11 | 20 | EFS | 2026-04-13 | KAPW-HC-183831 |  | 2026-04-14 |  | 1 | 2026-04-18 | 0 | 0 | 9 |  |  |  | 2026-04-06 | 185159.52 | Paid | 2026-04-13 | 53298.1678 | Paid | 40.95 | 185159.52 | 187011.1152 | 0.22 | 0.065 |  |  | 608 | Pcs | [8 empty] | Arrived at Works |  | 9 | 1 | 1 | 4 | 4
Arrived | QBL-II | Refractory Material | Store |  | 25655-60 |  | Fire Slab-Straight | 250*250*20 | [5 empty] | 2000 | Pcs |  |  | 2026-01-27 |  | 2026-04-27 |  | One Piece | China |  | 29487 |  | 2026-04-08 | BAH | CAD |  | 10.76 | ¥ | 40.95 |  | 21520 |  | 881244 |  |  |  | 6903.901 |  | CFR Karachi |  | OOCL LE HARVE | Yang Ming |  | Sea | YMJAS237026038 |  | Shanghai | Karachi | 2026-03-18 | 2026-03-22 | 2026-04-11 |  |  |  | 2026-04-11 | 20 | EFS | 2026-04-13 | KAPW-HC-183831 |  | 2026-04-14 |  | 1 | 2026-04-18 | 0 | 0 | 9 |  |  |  | 2026-04-06 | 881244 | Paid | 2026-04-13 | 253666.0854 | Paid | 40.95 | 881244 | 890056.44 | 0.22 | 0.065 |  |  | 519 | Pcs | [8 empty] | Arrived at Works |  | 9 | 1 | 1 | 4 | 4
Arrived | QBL-II | Refractory Material | Store |  | 25656-60 |  | Fire Slab-Straight | 375*125*20 | [5 empty] | 2472 | Pcs |  |  | 2026-01-27 |  | 2026-04-27 |  | One Piece | China |  | 29487 |  | 2026-04-08 | BAH | CAD |  | 7.89 | ¥ | 40.95 |  | 19504.08 |  | 798692.076 |  |  |  | 6903.901 |  | CFR Karachi |  | OOCL LE HARVE | Yang Ming |  | Sea | YMJAS237026038 |  | Shanghai | Karachi | 2026-03-18 | 2026-03-22 | 2026-04-11 |  |  |  | 2026-04-11 | 20 | EFS | 2026-04-13 | KAPW-HC-183831 |  | 2026-04-14 |  | 1 | 2026-04-18 | 0 | 0 | 9 |  |  |  | 2026-04-06 | 798692.076 | Paid | 2026-04-13 | 229903.5141 | Paid | 40.95 | 798692.076 | 806678.9968 | 0.22 | 0.065 |  |  | 382 | Pcs | [8 empty] | Arrived at Works |  | 9 | 1 | 1 | 4 | 4
Arrived | QBL-II | Refractory Material | Store |  | TMPNL0130 |  | Curved Elbow | Dia60 | [5 empty] | 480 | Pcs |  |  | 2026-01-27 |  | 2026-04-27 |  | One Piece | China |  | 29487 |  | 2026-04-08 | BAH | CAD |  | 2.6 | ¥ | 40.95 |  | 1248 |  | 51105.6 |  |  |  | 6903.901 |  | CFR Karachi |  | OOCL LE HARVE | Yang Ming |  | Sea | YMJAS237026038 |  | Shanghai | Karachi | 2026-03-18 | 2026-03-22 | 2026-04-11 |  |  |  | 2026-04-11 | 20 | EFS | 2026-04-13 | KAPW-HC-183831 |  | 2026-04-14 |  | 1 | 2026-04-18 | 0 | 0 | 9 |  |  |  | 2026-04-06 | 51105.6 | Paid | 2026-04-13 | 14710.747 | Paid | 40.95 | 51105.6 | 51616.656 | 0.22 | 0.065 |  |  | 117 | Pcs | [8 empty] | Arrived at Works |  | 9 | 1 | 1 | 4 | 4
Arrived | QBL-II |  | Store |  | 16887-156 |  | Ferro Moly | 60%/(10-50mm) | [5 empty] | 1000 | Kgs |  |  | 2025-12-24 |  | 2026-03-23 |  | JC Resources | Korea |  | 22408 |  | 2026-02-24 | BAH | CAD |  | 32.7 | $ | 282 | 32700 | 32700 | 9221400 | 9221400 |  |  |  | 7202.7 |  | CFR Karachi |  | KMTC Chennai |  | Dynamic Shipping | Sea | GLSSKHI2602002 |  | Busan | Karachi |  | 2026-01-30 | 2026-02-27 | 2026-02-28 |  |  | 2026-02-28 |  | EFS | 2026-03-02 | KAPW-HC-161910 |  | 2026-03-02 |  | 0 | 2026-03-19 |  | 0 | 4 |  |  |  | 2026-02-24 | 9221400 | Paid | 2026-02-26 | 2747516.13 | Paid | 282 | 9221400 | 9313614 | 0.23 | 0.065 |  |  | 9622 | Kgs | 9412 |  | 2026-06-26 | 72 |  |  |  |  | Arrived at Works |  | 13 | 1 | 1 | 13 | 4
Arrived | QBL-II |  | Trading |  | TMPNL0131 |  | Phosphor Copper Master Alloy | Wafle Type | [5 empty] | 1.5 | Ton | [5 empty] | 0 | JEIL | South Korea | Busan | 16847 |  | 2026-01-19 | BAH | CAD |  | 12250 | $ | 282 | 18375 | 18375 | 5181750 | 5181750 |  |  |  | 7405 |  | FOB-Busan |  | BELAWAN |  | FREIGHT HUB | By Sea | FBSIN251529 |  | Busan | Karachi | 2025-12-10 | 2025-12-24 | 2026-01-17 | 2026-01-29 |  |  | 2026-01-29 | 36 | EFS | [5 empty] | 0 | 2026-02-10 |  | 0 | 0 | 2026-01-20 | 5181750 | Paid |  |  |  |  | 1543902.4125 | Paid | 282 | 5181750 | 5233567.5 | 0.23 | 0.065 |  |  |  | Ton | [8 empty] | Arrived at Works | Material for Trading Purpose | 28 | 1 | 1 | 13 | 4
Shafts/Ongoing/Import Status/Import Rem | QCL | Foundry Material | Store |  | 2944-147 |  | Chromite Sand | BA45 | [5 empty] | 27 | MT |  |  | 2026-05-12 |  | 2026-08-12 | 13.1429 | Randyrok | South Africa |  | 4021 |  |  | HMB | Advance |  | 527.07 | $ | 281 | 28461.78 | 14230.89 | 7997760.18 | 3998880.09 |  |  |  | 2610 | NO | CFR |  |  | MSC | MSC Pakistan | Sea | MEDUW5194289 |  | Durban | Karachi |  | 2026-06-15 | 2026-07-01 |  |  |  | 2026-07-01 | 16 | EFS | [5 empty] | 0 | 2026-07-11 |  | 0 | 32 | 2026-05-20 | 3998880.09 | Unpaid |  |  |  | 2026-06-10 | 1191466.3228 | Paid | 281 | 3998880.09 | 4038868.8909 | 0.23 | 0.065 |  |  | 171 | Kgs | [8 empty] | Under Custom Clearance |  | 29 | 1 | 1 | 1 | 2
Shafts/Ongoing/Import Status/Import Rem | QBL-II | Foundry Material | Store |  | 2944-147 |  | Chromite Sand | BA45 | [5 empty] | 27 | MT |  |  | 2026-04-28 |  | 2026-07-28 | 13 | Randyrok | South Africa |  | 4021 |  |  | HMB | Advance |  | 527.07 | $ | 281 |  | 14230.89 |  | 3998880.09 |  |  |  | 2610 | NO | CFR |  |  | MSC | MSC Pakistan | Sea | MEDUW5194289 |  | Durban | Karachi |  | 2026-06-15 | 2026-07-01 |  |  |  | 2026-07-01 | 16 | EFS | [5 empty] | 0 | 2026-07-11 |  | 0 | 17 | 2026-05-20 | 3998880.09 | Unpaid |  |  |  | 2026-06-10 | 1191466.3228 | Paid | 281 | 3998880.09 | 4038868.8909 | 0.23 | 0.065 |  |  | 171 | Kgs | [8 empty] | Under Custom Clearance |  | 29 | 1 | 1 | 1 | 4
Shafts/Ongoing/Import Status/Import Rem | QE | Engineering Item | Engg. |  | 27331-60 |  | Super Nut | 2-1/4" |  |  | CE26-TSLU-0013 | CE26-MO-0162 | Texas Shredder | 6 | Pcs |  |  | 2026-04-28 |  | 2026-07-21 | 12 | ABS | Malaysia |  | 4003 |  | 2026-05-06 | HMB | Advance |  | 900 | $ | 279.6 | 5400 | 5400 | 1509840 | 1509840 |  |  |  | 7318.159 | NO | FCA |  |  |  |  | Air |  |  |  | Lahore | 2026-06-15 | 2026-06-30 | 2026-07-01 | 2026-07-02 |  |  | 2026-07-02 | 2 | EFS | [5 empty] | 0 | 2026-07-03 |  | 0 | 18 | 2026-05-06 | 1509840 | Paid |  |  |  | 2026-06-30 | 1166577.876 | Paid | 279.6 | 1509840 | 1524938.4 | 0.7 | 0.065 |  |  | 393090 | Pcs | [8 empty] | Under Custom Clearance | Material RFD is scheduled for 22 June 2026. The air forwarder is being arranged by the logistics team accordingly. | 30 | 1 | 3 |  | 1
Shafts/Ongoing/Import Status/Import Rem | QCL | Foundry Material | Store |  | 12328-60 |  | Criterion | 80E | [5 empty] | 4000 | Kgs |  |  | 2026-02-24 |  | 2026-05-24 |  | Foseco | UAE |  | 3990 |  | 20-0-4-26 | HMB | Advance |  | 1.561 | € | 328.1 | 6244 | 6244 | 2048656.4 | 2048656.4 |  |  |  | 3816 |  | CFR Karachi |  |  |  |  | Sea | GDYKHI262601 |  |  | Karachi |  | 2026-07-10 | 2026-08-20 |  |  |  | 2026-08-20 | 41 | EFS | [5 empty] | 0 | 2026-08-30 |  | 0 | -98 | 2026-04-20 | 2048656.4 | Paid |  |  |  | 2026-06-10 | 610397.1744 | Unpaid | 328.1 | 2048656.4 | 2069142.964 | 0.23 | 0.065 |  |  | 611 | Kgs | [8 empty] | Ready Awaiting Sailing |  | 31 | 1 | 1 |  | 2
Arrived | QCL | Ferro Alloys | Store |  | 23560-60 |  | Ferro Manganese L/C | Min 99.7% | [5 empty] | 5 | Ton |  |  | 2026-03-25 |  | 2026-06-25 |  | Adbase Import(Paktech) | Hong Kong |  | 3988 |  | 20-0-4-26 | HMB | Advance |  | 2840 | $ | 279.05 | 14200 | 14200 | 3962510 | 3962510 |  |  |  | 8111 | NO | CFR Karachi |  |  |  |  | Sea | JTN2601120 |  | Guangzhou | Karachi |  | 2026-04-30 | 2026-05-24 |  |  |  | 2026-05-24 |  |  | 2026-05-25 | KAPW-HC-206523 |  | 2026-06-04 |  | 10 | 2026-06-08 |  | 0 | 17 | 2026-04-20 | 3962510 | Paid |  |  |  | 2026-04-30 | 1180629.8545 | Paid | 279.05 | 3962510 | 4002135.1 | 0.23 | 0.065 |  |  | 866 | Kg | [8 empty] | Arrived at Works |  | 32 |  | 1 | 12 | 2
Shafts/Ongoing/Import Status/Import Rem | QEN | Engineering Item | Engg. |  | 27198-60 |  | Spherical Roller Bearing | 23160 CCK/W33/C3 |  |  | SL26-FATD-0462 |  | FATIMA SUGAR | 2 | Pcs |  |  | 2026-04-26 |  | 2026-06-25 |  | SKF | Sweden |  | 3976 |  | 2026-04-14 | HMB | Advance |  | 3594.685 | $ | 279.1 | 20573.06 | 7189.37 | 5741941.046 | 2006553.167 |  | 22 |  | 8482.3 |  | CFR Karachi |  |  |  |  | Sea |  |  |  | Karachi | 2026-07-17 | 2026-07-24 | 2026-09-22 |  |  |  | 2026-09-22 | [7 empty] | 0 | 2026-10-02 |  | 0 | -99 | 2026-04-14 | 2006553.167 | Paid |  |  |  | 2026-06-10 | 800514.386 | Unpaid | 279.1 | 2006553.167 | 2026618.6987 | 0.33 | 0.065 |  |  | 1154889 | Pcs | [8 empty] | Under Production | Shipment will shipped from Belgium | 33 |  | 1 |  | 3
Shafts/Ongoing/Import Status/Import Rem | QEN | Engineering Item | Engg. |  | 27199-60 |  | Spherical Roller Bearing | 23260 CCK/W33/C3 |  |  | SL26-FATD-0463 |  | FATIMA SUGAR | 2 | Pcs |  |  | 2026-04-26 |  | 2026-06-25 |  | SKF | Sweden |  | 3976 |  | 2026-04-14 | HMB | Advance |  | 5294.97 | $ | 279.1 |  | 10589.94 |  | 2955652.254 |  |  |  | 8482.3 |  | CFR Karachi |  |  |  |  | Sea |  |  |  | Karachi | 2026-07-17 | 2026-07-24 | 2026-09-22 |  |  |  | 2026-09-22 | [7 empty] | 0 | 2026-10-02 |  | 0 | -99 | 2026-04-14 | 2955652.254 | Paid |  |  |  | 2026-06-10 | 1179157.4667 | Unpaid | 279.1 | 2955652.254 | 2985208.7765 | 0.33 | 0.065 |  |  | 1696940 | Pcs | [8 empty] | Under Production | Shipment will shipped from Belgium | 33 |  | 1 |  | 3
Shafts/Ongoing/Import Status/Import Rem | QEN | Engineering Item | Engg. |  | 27200-60 |  | Adopter Sleeve | OH 3260 H |  |  | SL26-FATD-0463 |  | FATIMA SUGAR | 2 | Pcs |  |  | 2026-04-26 |  | 2026-06-25 |  | SKF | Sweden |  | 3976 |  | 2026-04-14 | HMB | Advance |  | 1396.875 | $ | 279.1 |  | 2793.75 |  | 779735.625 |  |  |  | 8482.999 |  | CFR Karachi |  |  |  |  | Sea |  |  |  | Karachi | 2026-09-04 | 2026-09-11 | 2026-11-10 |  |  |  | 2026-11-10 | [7 empty] | 0 | 2026-11-20 |  | 0 | -148 | 2026-04-14 | 779735.625 | Paid |  |  |  | 2026-06-10 | 232322.2295 | Unpaid | 279.1 | 779735.625 | 787532.9813 | 0.23 | 0.065 |  |  | 415692 | Pcs | [8 empty] | Under Production | Shipment will shipped from Belgium | 33 |  | 1 |  | 3
Arrived | QBL-II | Foundry Material | Store |  | 2944-147 |  | Chromite Sand | BA45 | [5 empty] | 27 | Ton |  |  | 2026-03-26 |  | 2026-06-26 | 13.1429 | Randyrok | SA |  | 3974 |  | 2026-04-14 | HMB | Advance |  | 527.0048 | $ | 279.1 | 14229.1296 | 14229.1296 | 3971350.0714 | 3971350.0714 |  |  |  | 2610 |  | CFR Karachi |  | MSC VILDA X | MSC |  | Sea | MEDUW5142429 |  | Durban | Karachi |  | 2026-04-24 | 2026-06-06 | 2026-06-12 | 2026-06-15 |  | 2026-06-15 | 52 | EFS | [5 empty] | 0 | 2026-06-25 |  | 0 | 1 | 2026-04-14 | 3971350.0714 | Paid |  |  |  |  | 1183263.7538 | Paid | 279.1 | 3971350.0714 | 4011063.5721 | 0.23 | 0.065 |  |  | 170 | Kgs | [8 empty] | Arrived at Works |  | 29 | 1 | 1 | 1 | 4
Shafts/Ongoing/Import Status/Import Rem | QE | Lifting Equipment | Engg. |  | 13897-60 |  | Synthetic Safety Sling "YELLOW" - 75 TON | 3100MM X 75000KGS | [5 empty] | 40 | Pcs | [6 empty] | Dofull | China |  | 3966 |  | 2026-04-10 | HMB | Advance |  | 1400 | ¥ | 41.3 | 172180 | 56000 | 7111034 | 2312800 |  |  |  | 5609 | NO | FOB Shanghai |  |  |  |  | Sea | HWKHI2600960 |  | Shanghai | Karachi | 2026-05-15 | 2026-05-28 | 2026-06-19 | 2026-06-27 | 2026-07-02 | 2026-07-05 | 2026-07-05 | [7 empty] | 0 | 2026-07-15 |  | 0 | 0 | 2026-04-13 | 2312800 | Paid |  |  |  | 2026-04-30 | 969410.12 | Unpaid | 41.3 | 2312800 | 2335928 | 0.35 | 0.065 |  |  | 72758 | Pcs | [8 empty] | In Transit | Vessel Schdule awaited | 18 |  | 1 | 4 | 1
Shafts/Ongoing/Import Status/Import Rem | QE | Lifting Equipment | Engg. |  | 13898-60 |  | Synthetic Safety Sling "YELLOW" - 50 TON | 2662MM X 50000KGS | [5 empty] | 28 | Pcs | [6 empty] | Dofull | China |  | 3966 |  | 2026-04-10 | HMB | Advance |  | 710 | ¥ | 41.3 |  | 19880 |  | 821044 |  |  |  | 5609 | NO | FOB Shanghai |  |  |  |  | Sea | HWKHI2600960 |  | Shanghai | Karachi | 2026-05-15 | 2026-05-28 | 2026-06-19 | 2026-06-27 | 2026-07-02 | 2026-07-05 | 2026-07-05 | [7 empty] | 0 | 2026-07-15 |  | 0 | 0 | 2026-04-13 | 821044 | Paid |  |  |  | 2026-04-30 | 344140.5926 | Unpaid | 41.3 | 821044 | 829254.44 | 0.35 | 0.065 |  |  | 37241 | Pcs | [8 empty] | In Transit | Vessel Schdule awaited | 18 |  | 1 | 4 | 1
Shafts/Ongoing/Import Status/Import Rem | QE | Lifting Equipment | Engg. |  | 13893-60 |  | Synthetic Reverse Sling "BLUE" - 75 TON | 2910MM X 75000KGS | [5 empty] | 20 | Pcs | [6 empty] | Dofull | China |  | 3966 |  | 2026-04-10 | HMB | Advance |  | 1360 | ¥ | 41.3 |  | 27200 |  | 1123360 |  |  |  | 5609 | NO | FOB Shanghai |  |  |  |  | Sea | HWKHI2600960 |  | Shanghai | Karachi | 2026-05-15 | 2026-05-28 | 2026-06-19 | 2026-06-27 | 2026-07-02 | 2026-07-05 | 2026-07-05 | [7 empty] | 0 | 2026-07-15 |  | 0 | 0 | 2026-04-13 | 1123360 | Paid |  |  |  | 2026-04-30 | 470856.344 | Unpaid | 41.3 | 1123360 | 1134593.6 | 0.35 | 0.065 |  |  | 70448 | Pcs | [8 empty] | In Transit | Vessel Schdule awaited | 18 |  | 1 | 4 | 1
Shafts/Ongoing/Import Status/Import Rem | QE | Lifting Equipment | Engg. |  | 13894-60 |  | Synthetic Reverse Sling "BLUE" - 50 TON | 2600MM X 50000KGS | [5 empty] | 14 | Pcs | [6 empty] | Dofull | China |  | 3966 |  | 2026-04-10 | HMB | Advance |  | 690 | ¥ | 41.3 |  | 9660 |  | 398958 |  |  |  | 5609 | NO | FOB Shanghai |  |  |  |  | Sea | HWKHI2600960 |  | Shanghai | Karachi | 2026-05-15 | 2026-05-28 | 2026-06-19 | 2026-06-27 | 2026-07-02 | 2026-07-05 | 2026-07-05 | [7 empty] | 0 | 2026-07-15 |  | 0 | 0 | 2026-04-13 | 398958 | Paid |  |  |  | 2026-04-30 | 167223.2457 | Unpaid | 41.3 | 398958 | 402947.58 | 0.35 | 0.065 |  |  | 36239 | Pcs | [8 empty] | In Transit | Vessel Schdule awaited | 18 |  | 1 | 4 | 1
Shafts/Ongoing/Import Status/Import Rem | QE | Lifting Equipment | Engg. |  | 13895-60 |  | Synthetic Drive Sling "ORANGE" - 75 TON | 2600MM X 75000KGS | [5 empty] | 40 | Pcs | [6 empty] | Dofull | China |  | 3966 |  | 2026-04-10 | HMB | Advance |  | 1080 | ¥ | 41.3 |  | 43200 |  | 1784160 |  |  |  | 5609 | NO | FOB Shanghai |  |  |  |  | Sea | HWKHI2600960 |  | Shanghai | Karachi | 2026-05-15 | 2026-05-28 | 2026-06-19 | 2026-06-27 | 2026-07-02 | 2026-07-05 | 2026-07-05 | [7 empty] | 0 | 2026-07-15 |  | 0 | 0 | 2026-04-13 | 1784160 | Paid |  |  |  | 2026-04-30 | 747830.664 | Unpaid | 41.3 | 1784160 | 1802001.6 | 0.35 | 0.065 |  |  | 56307 | Pcs | [8 empty] | In Transit | Vessel Schdule awaited | 18 |  | 1 | 4 | 1
Shafts/Ongoing/Import Status/Import Rem | QE | Lifting Equipment | Engg. |  | 13896-60 |  | Synthetic Drive Sling "ORANGE" - 50 TON | 2425MM X 50000KGS | [5 empty] | 28 | Pcs | [6 empty] | Dofull | China |  | 3966 |  | 2026-04-10 | HMB | Advance |  | 580 | ¥ | 41.3 |  | 16240 |  | 670712 |  |  |  | 5609 | NO | FOB Shanghai |  |  |  |  | Sea | HWKHI2600960 |  | Shanghai | Karachi | 2026-05-15 | 2026-05-28 | 2026-06-19 | 2026-06-27 | 2026-07-02 | 2026-07-05 | 2026-07-05 | [7 empty] | 0 | 2026-07-15 |  | 0 | 0 | 2026-04-13 | 670712 | Paid |  |  |  | 2026-04-30 | 281128.9348 | Unpaid | 41.3 | 670712 | 677419.12 | 0.35 | 0.065 |  |  | 30653 | Pcs | [8 empty] | In Transit | Vessel Schdule awaited | 18 |  | 1 | 4 | 1
Arrived | QBL-II | Foundry Material | Store |  | 2944-147 |  | Chromite Sand | BA45 | [5 empty] | 27 | Ton |  |  | 2026-02-25 |  | 2026-05-25 | 12.7143 | Randyrok | SA |  | 3945 |  | 2026-03-27 | HMB | Advance |  | 528.3333 | $ | 279.7 | 14265 | 14265 | 3989920.5 | 3989920.5 |  |  |  | 2610 |  | CFR Karachi |  | MSC ESTHI | MSC |  | Sea | MEDUW5127560 |  | Durban | Karachi |  | 2026-04-16 | 2026-05-24 | 2026-05-28 | 2026-06-04 |  | 2026-06-04 | 49 | EFS | [5 empty] | 0 | 2026-06-18 | 16.1429 | 0 | -24 | 2026-03-27 | 3989920.5 | Paid |  |  |  | 2026-06-08 | 1188796.813 | Paid | 279.7 | 3989920.5 | 4029819.705 | 0.23 | 0.065 |  |  | 170 | Kgs | [8 empty] | Arrived at Works | Shipment booking received ETD:23-04-26 | 29 | 1 | 1 | 1 | 4
Shafts/Ongoing/Import Status/Import Rem | QBL-II | Foundry Material | Engg. |  | TMPNL0132 |  | Centrifugal Casting Mold | 480/267X1550 | [5 empty] | 2 | Pcs |  |  | 2026-02-20 |  | 2026-05-20 | 12.7143 | Tianjin Federal Centrifugal | China |  | 3943 |  | 2026-03-27 | HMB | Advance |  | 5250 | $ | 279.7 | 10500 | 10500 | 2936850 | 2936850 |  |  |  | 8480.49 |  | FOB |  |  |  |  | Sea |  |  |  | Karachi | 2026-07-06 | 2026-07-09 | 2026-07-31 |  |  |  | 2026-07-31 | 22 | EFS | [5 empty] | 0 | 2026-08-10 | 24.4286 | 0 | -82 | 2026-03-27 | 2936850 | Paid |  |  |  |  | 875034.4575 | Unpaid | 279.7 | 2936850 | 2966218.5 | 0.23 | 0.065 |  |  | 3350142 | Pcs | [8 empty] | Ready Awaiting Sailing | Mold was rejected during UT inspection and now mold is under re-production. Material is re-prodcuced of dt: 17-06-26. Forwarder has been nominaed, shipment booking is awaited. | 34 | 1 | 1 |  | 4
Arrived | QCL | Refractory Material | Store |  | 13940-60 |  | Stelex Pro Filter | 125X30/10 | [5 empty] | 500 | Pcs | [6 empty] | E-Born | China |  | 3941 |  | 2026-03-27 | HMB | Advance |  | 6.83 | $ | 279.7 | 5780 | 3415 | 1616666 | 955175.5 |  |  |  | 6903.901 |  | CPT Lahore |  |  |  |  | Air | SF0223992781706/78483508320 |  | Guangzhou | Lahore | 2026-04-20 | 2026-04-21 | 2026-04-27 |  |  |  | 2026-04-27 | 6 |  | 2026-04-28 | LPAF-HC-76105 |  | 2026-04-29 |  | 1 | 2026-04-29 | 0 | 0 | 0 | 2026-03-27 | 955175.5 | Paid |  |  |  |  | 303889.0853 | Paid | 279.7 | 955175.5 | 964727.255 | 0.25 | 0.065 |  |  | 2224 | Pcs | [8 empty] | Arrived at Works |  | 35 |  | 3 | 12 | 2
Arrived | QCL | Refractory Material | Store |  | 13940-60 |  | Stelex Pro Filter | 90X25/10 | [5 empty] | 500 | Pcs | [6 empty] | E-Born | China |  | 3941 |  | 2026-03-27 | HMB | Advance |  | 4.73 | $ | 279.7 |  | 2365 |  | 661490.5 |  |  |  | 6903.901 |  | CPT Lahore |  |  |  |  | Air | SF0223992781706/78483508320 |  | Guangzhou | Lahore | 2026-04-20 | 2026-04-21 | 2026-04-27 |  |  |  | 2026-04-27 | 6 |  | 2026-04-28 | LPAF-HC-76105 |  | 2026-04-29 |  | 1 | 2026-04-29 | 0 | 0 | 0 | 2026-03-27 | 661490.5 | Paid |  |  |  |  | 210453.2026 | Paid | 279.7 | 661490.5 | 668105.405 | 0.25 | 0.065 |  |  | 1547 | Pcs | [8 empty] | Arrived at Works |  | 35 |  | 3 | 12 | 2
Arrived | QCL | Foundry Material | Store |  | 23558-60 |  | Neutral Ramming Mass | CXNRM- C-98.5% | [5 empty] | 6 | Ton |  |  | 2026-02-24 |  | 2026-05-24 | 12.7143 | HK Jinyen | Hong Kong |  | 3939 |  | 2026-03-27 | HMB | Advance |  | 1210 | $ | 279.7 | 7260 | 7260 | 2030622 | 2030622 |  |  |  | 3816 |  | FOB |  |  |  |  | Sea | JOYN2601603 |  | Shanghai | Karachi | 2026-04-09 | 2026-04-29 | 2026-05-13 | 2026-05-15 |  |  | 2026-05-15 | 16 | EFS | 2026-05-18 | KAPW-HC-202220 |  | 2026-05-21 |  | 3 | 2026-06-01 | 13.8571 | 0 | -8 | 2026-03-27 | 2030622 | Paid |  |  |  | 2026-04-30 | 646042.3893 | Paid | 279.7 | 2030622 | 2050928.22 | 0.25 | 0.065 |  |  | 426 | Kg | [8 empty] | Arrived at Works |  | 36 | 1 | 1 | 4 | 2
Arrived | QEN | Capex | Capital |  | TMPNL0133 |  | Servo Motor With Brake | SF180-4-048M1530-A | [5 empty] | 4 | Set | [6 empty] | HNC | China |  | 3937 |  | 2026-03-27 | HMB | Advance |  | 603.76 | $ | 279.7 | 12689.94 | 2415.04 | 3549376.218 | 675486.688 |  |  |  | 8501.1 |  | FOB |  |  | YTO |  | Air | 860-05558232/SA260505401 |  | KUNMING | Lahore |  | 2026-06-01 | 2026-06-02 |  |  |  | 2026-06-02 | 1 | EFS | 2026-06-05 | LPAF-HC-85469 |  | 2026-06-06 |  | 1 | 2026-06-05 | 0 | 0 | 0 | 2026-03-27 | 675486.688 | Paid |  |  |  | 2026-04-10 | 194438.8431 | Paid | 279.7 | 675486.688 | 682241.5549 | 0.22 | 0.065 |  |  | 202027 | Set | [8 empty] | Arrived at Works | Shipment booking has been shared with logistics, Air freight rates awaited. | 17 | 1 | 3 | 14 | 3
Arrived | QEN | Capex | Capital |  | TMPNL0134 |  | Servo Motor With Brake | SF180-4-035M1530B-A | [5 empty] | 2 | Set | [6 empty] | HNC | China |  | 3937 |  | 2026-03-27 | HMB | Advance |  | 669.53 | $ | 279.7 |  | 1339.06 |  | 374535.082 |  |  |  | 8501.1 |  | FOB |  |  | YTO |  | Air | 860-05558232/SA260505401 |  | KUNMING | Lahore |  | 2026-06-01 | 2026-06-02 |  |  |  | 2026-06-02 | 1 | EFS | 2026-06-05 | LPAF-HC-85469 |  | 2026-06-06 |  | 1 | 2026-06-05 | 0 | 0 | 0 | 2026-03-27 | 374535.082 | Paid |  |  |  | 2026-04-10 | 107809.9234 | Paid | 279.7 | 374535.082 | 378280.4328 | 0.22 | 0.065 |  |  | 224524 | Set | [8 empty] | Arrived at Works | Shipment booking has been shared with logistics, Air freight rates awaited. | 17 | 1 | 3 | 14 | 3
Arrived | QEN | Capex | Capital |  | TMPNL0135 |  | Servo Motor With Brake | SF180-4-018M1530B-A | [5 empty] | 2 | Set | [6 empty] | HNC | China |  | 3937 |  | 2026-03-27 | HMB | Advance |  | 532.73 | $ | 279.7 |  | 1065.46 |  | 298009.162 |  |  |  | 8501.1 |  | FOB |  |  | YTO |  | Air | 860-05558232/SA260505401 |  | KUNMING | Lahore |  | 2026-06-01 | 2026-06-02 |  |  |  | 2026-06-02 | 1 | EFS | 2026-06-05 | LPAF-HC-85469 |  | 2026-06-06 |  | 1 | 2026-06-05 | 0 | 0 | 0 | 2026-03-27 | 298009.162 | Paid |  |  |  | 2026-04-10 | 85781.9373 | Paid | 279.7 | 298009.162 | 300989.2536 | 0.22 | 0.065 |  |  | 178873 | Set | [8 empty] | Arrived at Works | Shipment booking has been shared with logistics, Air freight rates awaited. | 17 | 1 | 3 | 14 | 3
Arrived | QEN | Capex | Capital |  | TMPNL0136 |  | Servo Drive | HSD7-ES-28D30 | [5 empty] | 4 | Set | [6 empty] | HNC | China |  | 3937 |  | 2026-03-27 | HMB | Advance |  | 692.77 | $ | 279.7 |  | 2771.08 |  | 775071.076 |  |  |  | 8504.409 |  | FOB |  |  | YTO |  | Air | 860-05558232/SA260505401 |  | KUNMING | Lahore |  | 2026-06-01 | 2026-06-02 |  |  |  | 2026-06-02 | 1 | EFS | 2026-06-05 | LPAF-HC-85469 |  | 2026-06-06 |  | 1 | 2026-06-05 | 0 | 0 | 0 | 2026-03-27 | 775071.076 | Paid |  |  |  | 2026-04-10 | 223104.2092 | Paid | 279.7 | 775071.076 | 782821.7868 | 0.22 | 0.065 |  |  | 246457 | Set | [8 empty] | Arrived at Works | Shipment booking has been shared with logistics, Air freight rates awaited. | 17 | 1 | 3 | 14 | 3
Arrived | QEN | Capex | Capital |  | TMPNL0137 |  | Servo Drive | HSD7-ES-15D30 | [5 empty] | 2 | Set | [6 empty] | HNC | China |  | 3937 |  | 2026-03-27 | HMB | Advance |  | 359.54 | $ | 279.7 |  | 719.08 |  | 201126.676 |  |  |  | 8504.409 |  | FOB |  |  | YTO |  | Air | 860-05558232/SA260505401 |  | KUNMING | Lahore |  | 2026-06-01 | 2026-06-02 |  |  |  | 2026-06-02 | 1 | EFS | 2026-06-05 | LPAF-HC-85469 |  | 2026-06-06 |  | 1 | 2026-06-05 | 0 | 0 | 0 | 2026-03-27 | 201126.676 | Paid |  |  |  | 2026-04-10 | 57894.3137 | Paid | 279.7 | 201126.676 | 203137.9428 | 0.22 | 0.065 |  |  | 128685 | Set | [8 empty] | Arrived at Works | Shipment booking has been shared with logistics, Air freight rates awaited. | 17 | 1 | 3 | 14 | 3
Arrived | QEN | Capex | Capital |  | TMPNL0138 |  | Servo Drive | HSD7-ES-21D30 | [5 empty] | 2 | Set | [6 empty] | HNC | China |  | 3937 |  | 2026-03-27 | HMB | Advance |  | 394.61 | $ | 279.7 |  | 789.22 |  | 220744.834 |  |  |  | 8504.409 |  | FOB |  |  | YTO |  | Air | 860-05558232/SA260505401 |  | KUNMING | Lahore |  | 2026-06-01 | 2026-06-02 |  |  |  | 2026-06-02 | 1 | EFS | 2026-06-05 | LPAF-HC-85469 |  | 2026-06-06 |  | 1 | 2026-06-05 | 0 | 0 | 0 | 2026-03-27 | 220744.834 | Paid |  |  |  | 2026-04-10 | 63541.4005 | Paid | 279.7 | 220744.834 | 222952.2823 | 0.22 | 0.065 |  |  | 141132 | Set | [8 empty] | Arrived at Works | Shipment booking has been shared with logistics, Air freight rates awaited. | 17 | 1 | 3 | 14 | 3
Arrived | QEN | Capex | Capital |  | TMPNL0139 |  | MPG for HNC-808 Series Controller | AOSBAO-4A-5L | [5 empty] | 2 | Set | [6 empty] | HNC | China |  | 3937 |  | 2026-03-27 | HMB | Advance |  | 99.75 | $ | 279.7 |  | 199.5 |  | 55800.15 |  |  |  | 8537.109 |  | FOB |  |  | YTO |  | Air | 860-05558232/SA260505401 |  | KUNMING | Lahore |  | 2026-06-01 | 2026-06-02 |  |  |  | 2026-06-02 | 1 | EFS | 2026-06-05 | LPAF-HC-85469 |  | 2026-06-06 |  | 1 | 2026-06-05 | 0 | 0 | 0 | 2026-03-27 | 55800.15 | Paid |  |  |  | 2026-04-10 | 16062.0732 | Paid | 279.7 | 55800.15 | 56358.1515 | 0.22 | 0.065 |  |  | 41623 | Set | [8 empty] | Arrived at Works | Shipment booking has been shared with logistics, Air freight rates awaited. | 17 | 1 | 3 | 14 | 3
Arrived | QEN | Capex | Capital |  | TMPNL0140 |  | Milling Controller | HNC-808DiM 10.4 Inch | [5 empty] | 2 | Set | [6 empty] | HNC | China |  | 3937 |  | 2026-03-27 | HMB | Advance |  | 1486.75 | $ | 279.7 |  | 2973.5 |  | 831687.95 |  |  |  | 8537.109 |  | FOB |  |  | YTO |  | Air | 860-05558232/SA260505401 |  | KUNMING | Lahore |  | 2026-06-01 | 2026-06-02 |  |  |  | 2026-06-02 | 1 | EFS | 2026-06-05 | LPAF-HC-85469 |  | 2026-06-06 |  | 1 | 2026-06-05 | 0 | 0 | 0 | 2026-03-27 | 831687.95 | Paid |  |  |  | 2026-04-10 | 239401.3764 | Paid | 279.7 | 831687.95 | 840004.8295 | 0.22 | 0.065 |  |  | 605320 | Set | [8 empty] | Arrived at Works | Shipment booking has been shared with logistics, Air freight rates awaited. | 17 | 1 | 3 | 14 | 3
Arrived | QEN | Capex | Capital |  | TMPNL0141 |  | I/O Module | HIO-1200U, I/O Connection | [5 empty] | 2 | Set | [6 empty] | HNC | China |  | 3937 |  | 2026-03-27 | HMB | Advance |  | 209 | $ | 279.7 |  | 418 |  | 116914.6 |  |  |  | 8538.909 |  | FOB |  |  | YTO |  | Air | 860-05558232/SA260505401 |  | KUNMING | Lahore |  | 2026-06-01 | 2026-06-02 |  |  |  | 2026-06-02 | 1 | EFS | 2026-06-05 | LPAF-HC-85469 |  | 2026-06-06 |  | 1 | 2026-06-05 | 0 | 0 | 0 | 2026-03-27 | 116914.6 | Paid |  |  |  | 2026-04-10 | 33653.8676 | Paid | 279.7 | 116914.6 | 118083.746 | 0.22 | 0.065 |  |  | 77161 | Set | [8 empty] | Arrived at Works | Shipment booking has been shared with logistics, Air freight rates awaited. | 17 | 1 | 3 | 14 | 3
Arrived | QBL-II | Cutting Tools | Store |  | 19487-60 |  | Band Saw Blades | 80x1.6x14800mm | [5 empty] | 5 | Pcs |  |  | 2026-02-25 |  | 2026-05-25 | 12.7143 | Dofull | China |  | 3933 |  | 2026-03-26 | HMB | Advance |  | 55000 | ¥ | 40.85 | 275000 | 275000 | 11233750 | 11233750 |  |  |  | 8202.2 | NO | FOB |  |  |  |  | Sea | SHSHKHI26042200 |  | Shanghai | Karachi |  | 2026-04-16 | 2026-05-02 |  |  |  | 2026-05-02 | 16 | EFS | 2026-05-04 | KAPW-HC-194205 |  | 2026-05-07 |  | 3 | 2026-05-12 | 10.8571 | 0 | 13 | 2026-03-26 | 11233750 | Paid |  |  |  | 2026-05-04 | 3687478.4375 | Paid | 40.85 | 11233750 | 11346087.5 | 0.26 | 0.065 |  |  |  | Pcs | [8 empty] | Arrived at Works | Shipment bookin received ETD:16-04-26 | 18 | 1 | 1 | 4 | 4
Shafts/Ongoing/Import Status/Import Rem | QCL | Foundry Material | Store |  | TMPNL0142 |  | Artificial Graphite | [6 empty] | 10 | Ton |  |  | 2026-02-24 |  | 2026-05-24 | 12.7143 | HEIBEI Coke | China |  | 3931 |  | 2026-03-26 | HMB | Advance |  | 580 | $ | 279.35 | 5800 | 5800 | 1620230 | 1620230 |  |  |  | 3801.1 | NO | CFR Karachi |  |  |  |  | Sea |  |  |  | Karachi |  | 2026-05-21 | 2026-06-12 | 2026-06-17 | 2026-06-21 | 2026-06-24 | 2026-06-24 | 34 | EFS | [5 empty] | 0 | 2026-07-08 | 19.1429 | 0 | -45 | 2026-03-26 | 1620230 | Paid |  |  |  |  | 482747.5285 | Unpaid | 279.35 | 1620230 | 1636432.3 | 0.23 | 0.065 |  |  | 206 | Kgs | [8 empty] | Under De-Stuffing |  | 37 | 1 | 1 |  | 2
Arrived | QCL | Cutting Tools | Store |  | TMPNL0143 |  | Swing Frame Grinding Wheel | 500X50X50mm | [5 empty] | 50 | Pcs |  |  | 2026-02-24 |  | 2026-05-24 | 12.7143 | Aten | Turkey |  | 3906 |  | 2026-03-10 | HMB | Advance |  | 125 | $ | 282 | 6250 | 6250 | 1762500 | 1762500 |  |  |  | 6804.1 |  | FOB |  | TOR 0126E | AKKON |  | Sea | X126320050044 |  | MARPORT | Karachi |  | 2026-04-12 | 2026-04-27 | 2026-04-28 |  |  | 2026-04-28 | 16 | EFS | 2026-04-28 | KAPW-HC-191422 |  | 2026-05-06 |  | 8 | 2026-05-12 | 11 | 0 | 12 | 2026-03-09 | 1762500 | Paid |  |  |  |  | 578540.625 | Paid | 282 | 1762500 | 1780125 | 0.26 | 0.065 |  |  | 38154 | Pcs | [8 empty] | Arrived at Works |  | 38 | 1 | 1 | 15 | 2
Arrived | QCL | Capex | Store |  | TMPNL0144 |  | Digital Sensor | [6 empty] | 2 | Pcs |  |  | 2026-01-02 |  | 2026-03-30 | 12.4286 | Foseco | UAE |  | 3904 |  | 2026-03-10 | HMB | Advance |  | 5351.375 | € | 332 | 10702.75 | 10702.75 | 3553313 | 3553313 |  |  |  | 9025.9 | NO | CPT Lahore |  |  |  |  | Air | GOAA69941212/15744815842 |  | Malpensa | Lahore |  | 2026-05-31 | 2026-06-02 |  |  |  | 2026-06-02 | 2 |  | 2026-06-05 | LPAf-HC-85468 |  | 2026-06-08 |  | 3 | 2026-06-08 | 22.4286 | 0 | -70 | 2026-03-09 | 3553313 | Paid |  |  |  |  | 1166374.9922 | Paid | 332 | 3553313 | 3588846.13 | 0.26 | 0.065 |  |  |  | Pcs | [8 empty] | Arrived at Works |  | 31 |  | 3 | 16 | 2
Arrived | QE | Engineering Item | Engg. |  | TMPNL0145 |  | Steel Plate | S30815(16*1500*3000) |  |  | CE26-FLTD-0003 |  | Fuller | 1 | Kgs | 568.8 | 568.8 | 2026-02-16 |  | 2026-05-18 | 13 | Henan Bebon | China |  | 3895 |  | 2026-03-03 | HMB | Advance |  | 5.63 | $ | 280 | 7205.274 | 3202.344 |  | 896656.32 |  |  |  | 7219.21 |  | FOB |  |  |  |  | Sea | SHSHKHI26034761 |  | Shanghai | Karachi |  | 2026-04-01 | 2026-04-18 | 2026-04-20 |  |  | 2026-04-20 | 19 |  | 2026-04-21 | KAPW-HC-187885 |  | 2026-04-27 |  | 6 | 2026-05-09 | 11.7143 | 0 | 9 | 2026-03-03 | 896656.32 | Paid |  |  |  | 2026-04-20 | 750000 | Paid | 280 | 896656.32 | 905622.8832 | 0.22 | 0.065 |  |  | 1808 | Kgs | [8 empty] | Arrived at Works | Gateout from Customs on 27-04-26 and pending delivery on Logistics End | 39 |  | 1 | 4 | 1
Arrived | QE | Engineering Item | Engg. |  | TMPNL0146 |  | Steel Plate | S30815(20*1500*3000) |  |  | CE26-FLTD-0003 |  | Fuller | 1 | Kgs | 711 | 711 | 2026-02-16 |  | 2026-05-18 | 13 | Henan Bebon | China |  | 3895 |  | 2026-03-03 | HMB | Advance |  | 5.63 | $ | 280 |  | 4002.93 |  | 1120820.4 |  |  |  | 7219.21 |  | FOB |  |  |  |  | Sea | SHSHKHI26034761 |  | Shanghai | Karachi |  | 2026-04-01 | 2026-04-18 | 2026-04-20 |  |  | 2026-04-20 | 19 |  | 2026-04-21 | KAPW-HC-187885 |  | 2026-04-27 |  | 6 | 2026-05-09 | 11.7143 | 0 | 9 | 2026-03-03 | 1120820.4 | Paid |  |  |  | 2026-04-20 | 750000 | Paid | 280 | 1120820.4 | 1132028.604 | 0.22 | 0.065 |  |  | 1891 | Kgs | [8 empty] | Arrived at Works | Gateout from Customs on 27-04-26 and pending delivery on Logistics End | 39 |  | 1 | 4 | 1
Arrived | QEN | Capex | Capital |  | TMPNL0147 |  | Gearbox for Nozzle Drilling | PLF-160-L2-16 | [5 empty] | 6 | Pcs | [6 empty] | HNC | China |  | 3889 |  | 2026-02-16 | HMB | Advance |  | 401.57 | $ | 280 | 6023.55 | 2409.42 | 1686594 | 674637.6 |  |  |  | 8483.409 | YES | FOB |  | YM EXPRESS 094W | Cosco |  | Sea | JHN26040144 |  | Shanghai | Karachi |  | 2026-04-17 | 2026-05-05 |  |  |  | 2026-05-05 | 18 |  | 2026-05-06 | KAPE-FS-67045 |  | 2026-05-12 |  | 6 | 2026-05-20 | 0 | 0 | 0 | 2026-02-16 | 674637.6 | Paid |  |  |  | 2026-02-05 | 378168.1067 | Paid | 280 | 674637.6 | 681383.976 | 0.49 | 0.065 |  |  |  | Pcs | [8 empty] | Arrived at Works | Shipment booking received ETD:17-04-2026/Shipment has been de-stuffed today dt: 08-05-2026H, Shipment will be Gateout Cleareed from custom today dt: 11-05-2026. | 17 |  | 1 | 4 | 3
Arrived | QEN | Capex | Capital |  | TMPNL0148 |  | Gearbox for Nozzle Drilling | ZPLF-120-L2-16 | [5 empty] | 3 | Pcs | [6 empty] | HNC | China |  | 3889 |  | 2026-02-16 | HMB | Advance |  | 401.57 | $ | 280 | 6023.55 | 1204.71 | 1686594 | 337318.8 |  |  |  | 8483.409 | YES | FOB |  | YM EXPRESS 094W | Cosco |  | Sea | JHN26040144 |  | Shanghai | Karachi |  | 2026-04-17 | 2026-05-05 |  |  |  | 2026-05-05 | 18 |  | 2026-05-06 | KAPE-FS-67045 |  | 2026-05-12 |  | 6 | 2026-05-20 | 0 | 0 | 0 | 2026-02-16 | 337318.8 | Paid |  |  |  | 2026-02-05 | 189084.0533 | Paid | 280 | 337318.8 | 340691.988 | 0.49 | 0.065 |  |  |  | Pcs | [8 empty] | Arrived at Works | Shipment booking received ETD:17-04-2026/Shipment has been de-stuffed today dt: 08-05-2026H, Shipment will be Gateout Cleareed from custom today dt: 11-05-2026. | 17 |  | 1 | 4 | 3
Arrived | QEN | Capex | Capital |  | TMPNL0149 |  | Gearbox for Long Hole Drilling | PLF-160-L2-16 | [5 empty] | 3 | Pcs | [6 empty] | HNC | China |  | 3889 |  | 2026-02-16 | HMB | Advance |  | 401.57 | $ | 280 | 6023.55 | 1204.71 | 1686594 | 337318.8 |  |  |  | 8483.409 | YES | FOB |  | YM EXPRESS 094W | Cosco |  | Sea | JHN26040144 |  | Shanghai | Karachi |  | 2026-04-17 | 2026-05-05 |  |  |  | 2026-05-05 | 18 |  | 2026-05-06 | KAPE-FS-67045 |  | 2026-05-12 |  | 6 | 2026-05-20 | 0 | 0 | 0 | 2026-02-16 | 337318.8 | Paid |  |  |  | 2026-02-05 | 189084.0533 | Paid | 280 | 337318.8 | 340691.988 | 0.49 | 0.065 |  |  |  | Pcs | [8 empty] | Arrived at Works | Shipment booking received ETD:17-04-2026/Shipment has been de-stuffed today dt: 08-05-2026H, Shipment will be Gateout Cleareed from custom today dt: 11-05-2026. | 17 |  | 1 | 4 | 3
Arrived | QEN | Capex | Capital |  | TMPNL0150 |  | Gearbox for Long Hole Drilling | ZPLF-120-L2-16 | [5 empty] | 3 | Pcs | [6 empty] | HNC | China |  | 3889 |  | 2026-02-16 | HMB | Advance |  | 401.57 | $ | 280 |  | 1204.71 |  | 337318.8 |  |  |  | 8483.409 | YES | FOB |  | YM EXPRESS 094W | Cosco |  | Sea | JHN26040144 |  | Shanghai | Karachi |  | 2026-04-17 | 2026-05-05 |  |  |  | 2026-05-05 | 18 |  | 2026-05-06 | KAPE-FS-67045 |  | 2026-05-12 |  | 6 | 2026-05-20 | 0 | 0 | 0 | 2026-02-16 | 337318.8 | Paid |  |  |  | 2026-02-05 | 189084.0533 | Paid | 280 | 337318.8 | 340691.988 | 0.49 | 0.065 |  |  |  | Pcs | [8 empty] | Arrived at Works | Shipment booking received ETD:17-04-2026/Shipment has been de-stuffed today dt: 08-05-2026H, Shipment will be Gateout Cleareed from custom today dt: 11-05-2026. | 17 |  | 1 | 4 | 3
Arrived | QBL-II | Foundry Material | Store |  | 2944-147 |  | Chromite Sand | BA45 | [5 empty] | 27 | Ton |  |  | 2026-01-13 |  | 2026-04-13 | 12.8571 | Randyrok | South Africa |  | 3882 |  | 2026-02-09 | HMB | Advance |  | 528.37 | $ | 279.85 | 28531.98 | 14265.99 | 7984674.603 | 3992337.3015 |  |  |  | 2610 |  | CFR Karachi |  | MSC BARBARA | MSC |  | Sea | MEDUW5065034 |  | Durban | Karachi |  | 2026-02-17 | 2026-03-13 | 2026-03-20 | 2026-03-24 | 2026-04-09 | 2026-04-09 | 51 |  | 2026-04-09 | KPPI-HC-57318 |  | 2026-04-10 |  | 1 | 2026-04-14 | 13 | 0 | -1 | 2026-02-10 | 3992337.3015 | Paid |  |  |  | 2026-04-09 | 1149194.2922 | Paid | 279.85 | 3992337.3015 | 4032260.6745 | 0.22 | 0.065 |  |  | 171 | Kg | [8 empty] | Arrived at Works | For QCL only. | 29 |  | 1 | 1 | 4
Arrived | QBL-II | Foundry Material | Store |  | 2944-147 |  | Chromite Sand | BA45 | [5 empty] | 27 | Ton |  |  | 2026-01-27 |  | 2026-04-27 | 12.8571 | Randyrok | South Africa |  | 3882 |  | 2026-02-09 | HMB | Advance |  | 528.37 | $ | 279.85 |  | 14265.99 |  | 3992337.3015 |  |  |  | 2610 |  | CFR Karachi |  | MSC BARBARA | MSC |  | Sea | MEDUW5065034 |  | Durban | Karachi |  | 2026-02-17 | 2026-03-13 | 2026-03-20 | 2026-03-24 | 2026-04-09 | 2026-04-09 | 51 |  | 2026-04-09 | KPPI-HC-57318 |  | 2026-04-10 |  | 1 | 2026-04-14 | 11 | 0 | 13 | 2026-02-10 | 3992337.3015 | Paid |  |  |  | 2026-04-09 | 1149194.2922 | Paid | 279.85 | 3992337.3015 | 4032260.6745 | 0.22 | 0.065 |  |  | 171 | Kg | [8 empty] | Arrived at Works | For QBL-II only. | 29 |  | 1 | 1 | 4
Arrived | QEN | Capex | Engg. |  | TMPNL0151 |  | Drilling / Tapping Spindle | [6 empty] | 2 | Pcs | [5 empty] | 0 | Hardy | Taiwan | Taichung | 3874 |  | 2026-01-27 | BAH | Advance |  | 15539 | $ | 282 | 31078 | 31078 | 8763996 | 8763996 |  |  |  | 8466.939 |  | FCA |  |  | QAR |  | Air | AOF26903767 |  | Taipei | Lahore |  | 2026-04-03 | 2026-04-05 | 2026-04-06 | 2026-04-07 |  | 2026-04-07 | 4 | EFS | 2026-04-06 | LPAF-FS-69694 |  | 2026-04-08 |  | 2 | 2026-04-08 | 0 | 0 | 0 | 2026-01-20 | 8763996 | Paid |  |  |  | 2026-04-06 | 1250 | Paid | 282 | 8763996 | 8851635.96 | 0.26 | 0.065 |  |  | 2450047 | Pcs | [8 empty] | Arrived at Works | On time | 40 | 1 | 3 | 17 | 3
Arrived | QE |  | Trading |  | TMPNL0152 |  | Prime Hot Rolled Steel Plate(400MM) | 1045 | 2280 | 3880 |  |  |  | 1 | Ton | 27.78 | 27.78 |  |  |  | 0 | Dajin | China |  | 3851 |  | 2025-12-11 | HMB | Advance |  | 652 | $ | 280.7 | 18112.56 | 18112.56 | 5084195.592 | 5084195.592 |  |  |  | 7208.909 |  | CFR Karachi |  |  |  |  | Sea |  |  |  | Karachi | [7 empty] | 0 | [6 empty] | 0 |  |  | 0 |  | 2025-12-11 | 5084195.592 | Paid |  |  |  |  | 1668887.2031 | Unpaid | 280.7 | 5084195.592 | 5135037.5479 | 0.26 | 0.065 |  |  | 214 | Ton | [8 empty] | Order Cancelled | Order has been cancelled ( Payment Return is under process) | 10 |  | 1 |  | 1
Arrived | QCL |  | Store |  | TMPNL0153 |  | CPC-Artificial Graphite | Fixed Carbon- 98.5% Min | [5 empty] | 10 | Ton |  |  | 2025-11-21 |  | 2026-02-21 | 13.1429 | HEIBEI Coke | China |  | 3849 |  | 2025-12-10 | HMB | Advance |  | 607 | $ | 280.5 | 6070 | 6070 | 1702635 | 1702635 |  |  |  | 3801.1 |  | CFR Karachi |  | X-Press CARINA |  | SHIPCO TRANSPORT PAKISTAn | Sea | SC21KARL3305 |  | XINGANG | Karachi |  | 2026-01-16 | 2026-02-05 | 2026-02-08 |  |  | 2026-02-08 | 23 | EFS | 2026-02-09 | KAPW-HC-146993 |  | 2026-02-16 |  | 7 | 2026-02-20 |  | 0 | 1 | 2025-12-10 | 1702635 | Paid |  |  |  | 2026-02-08 | 507300.0982 | Paid | 280.5 | 1702635 | 1719661.35 | 0.23 | 0.065 |  |  | 214 | Kgs | 216 | [7 empty] | Arrived at Works |  | 37 | 1 | 1 | 18 | 2
Arrived | QBL-II |  | Store |  | 19766-60 |  | Pig Iron | C4-4.3, Si<0.45, P<0.035,S<0.02 | [5 empty] | 27 | Ton |  |  | 2025-11-14 |  | 2026-02-13 | 13 | Heibei Longfengsheng | China |  | 3841 |  | 2025-12-03 | HMB | Advance |  | 610 | $ | 280.75 | 16470 | 16470 | 4623952.5 | 4623952.5 |  |  |  | 7201.1 |  | CFR Karachi |  | TS BANGKOK | T.S Lines | TS Lines Pak | By Sea | 800610001653 |  | XINGANG | Karachi | 2026-01-05 | 2026-01-24 | 2026-02-23 | 2026-02-24 |  |  | 2026-02-24 | 31 | EFS | 2026-02-25 | KAPS-HC-148690 |  | 2026-02-27 |  | 2 | 2026-03-04 |  | 0 | -19 | 2025-12-02 | 4623952.5 | Paid |  |  |  |  | 1377706.6474 | Paid | 280.75 | 4623952.5 | 4670192.025 | 0.23 | 0.065 |  |  | 201 | Kg | 192 |  | 2026-06-12 | 73 |  |  |  |  | Arrived at Works |  | 41 | 1 | 1 | 18 | 4
Arrived | QE |  | Engg. |  | TMPNL0154 |  | SPHERICAL PLAIN BEARING | GE 240 ES-2RS -200040210 |  |  | SE25-FCGL-0618 |  | Fives(FCB) | 4 | Pcs |  |  | 2025-10-28 |  | 2026-02-25 | 17.1429 | SKF | Sweden |  | 3839 |  | 2025-12-02 | HMB | Advance |  | 2666.57 | $ | 280.8 | 10666.28 | 10666.28 | 2995091.424 | 2995091.424 |  |  |  | 8482.3 |  | CFR Karachi |  |  |  |  | Sea |  |  | Jebel Ali | Karachi |  | 2026-04-22 | 2026-04-24 |  |  |  | 2026-04-24 | 2 | EFS | [5 empty] | 0 | 2026-04-29 |  | 0 | -63 | 2025-12-01 | 2995091.424 | Paid |  |  |  | 2026-04-24 | 892387.4898 | Paid | 280.8 | 2995091.424 | 3025042.3382 | 0.23 | 0.065 |  |  | 0 | Pcs | [8 empty] | Arrived at Works | Material availability was confirmed by the supplier at the time of order placement on 06 March 2026 at the Dubai warehouse. However, vessel booking from Jebel Ali Port is still unconfirmed due to the ongoing war situation in the Gulf region. SKF has quoted an air freight cost of USD 1,405. Discussions regarding the additional payment through T/T are currently in process with the bank, and the bank has agreed to process the freight payment through advance T/T. SKF has requested us to wait until Monday, as they are already working on an alternative sea route solution. Air freight booking released by SKF shipment booking has been received ETD:10-04-2026. | 33 | 1 | 1 | 19 | 1
Arrived | QCL |  | Store |  | 19572-60 |  | Tic Cermet Rod | 14(D)*30(L) | [5 empty] | 300 | Pcs |  |  | 2025-11-18 |  | 2026-02-18 | 13.1429 | Westion | China | Zhuzhou | 3837 |  | 2025-12-02 | HMB | Advance |  | 83 | ¥ | 39.85 | 107900 | 24900 | 4299815 | 992265 |  |  |  | 8209 |  | CFR Karachi |  |  |  |  | By Sea |  |  |  | Karachi | 2026-01-05 | 2026-01-29 | 2026-02-20 |  |  |  | 2026-02-20 | 22 | EFS | 2026-02-23 | KAPE-HC-56997 |  | 2026-02-28 |  | 5 | 2026-03-09 |  | 0 | -19 | 2025-12-01 | 992265 | Paid |  |  |  |  | 325710.9863 | Paid | 39.85 | 992265 | 1002187.65 | 0.26 | 0.065 |  |  | 3423 | Kgs | 3478 | [7 empty] | Arrived at Works |  | 42 | 1 | 1 |  | 2
Arrived | QCL |  | Store |  | 19571-60 |  | Tic Cermet Rod | 14(D)*50(L) | [5 empty] | 1000 | Pcs |  |  | 2025-11-18 |  | 2026-02-18 | 13.1429 | Westion | China | Zhuzhou | 3837 |  | 2025-12-02 | HMB | Advance |  | 83 | ¥ | 39.85 |  | 83000 |  | 3307550 |  |  |  | 8209 |  | CFR Karachi |  |  |  |  | By Sea |  |  |  | Karachi | 2026-01-05 | 2026-01-29 | 2026-02-20 |  |  |  | 2026-02-20 | 22 | EFS | 2026-02-23 | KAPE-HC-56997 |  | 2026-02-28 |  | 5 | 2026-03-09 |  | 0 | -19 | 2025-12-01 | 3307550 | Paid |  |  |  |  | 1085703.2875 | Paid | 39.85 | 3307550 | 3340625.5 | 0.26 | 0.065 |  |  | 3423 | Kgs | 3478 | [7 empty] | Arrived at Works |  | 42 | 1 | 1 |  | 2
Arrived | QBL-II |  | Store |  | 24370-60 |  | Resin Sand | T-80 | [5 empty] | 1 | Ton |  |  | 2025-11-14 |  | 2026-02-13 | 13 | Heibei Leigin | China | Handan | 3835 |  | 2025-12-02 | HMB | Advance |  | 6000 | ¥ | 39.85 | 25000 | 6000 | 996250 | 239100 |  |  |  | 3816 | No | FOB-LCL |  | EVER LIVING |  | GLOBAL CONSOLIDATORS PAKISTAN | By Sea | AMIGL250609320A |  | Tianjin | Karachi | 2025-12-19 | 2026-01-07 | 2026-01-31 | 2026-02-01 | 2026-02-03 |  | 2026-02-03 | 27 | EFS | 2026-02-03 | KAPW-HC-143628 |  |  |  | -46056 | 2026-02-20 |  | 0 | -7 | 2025-12-01 | 239100 | Paid |  |  |  |  | 73654.755 | Paid | 39.85 | 239100 | 241491 | 0.24 | 0.065 |  |  | 359 | Kg | 301 | [7 empty] | Arrived at Works |  | 43 | 1 | 1 | 20 | 4
Arrived | QBL-II |  | Store |  | 24369-60 |  | Asbestos Disc | 308*70*5 | [5 empty] | 1000 | Pcs |  |  | 2025-11-14 |  | 2026-02-13 | 13 | Heibei Leigin | China | Handan | 3835 |  | 2025-12-02 | HMB | Advance |  | 19 | ¥ | 39.85 |  | 19000 |  | 757150 |  |  |  | 6811.4 | No | FOB-LCL |  | EVER LIVING |  | GLOBAL CONSOLIDATORS PAKISTAN | By Sea | AMIGL250609320A |  | Tianjin | Karachi | 2025-12-19 | 2026-01-07 | 2026-01-31 | 2026-02-01 | 2026-02-03 |  | 2026-02-03 | 27 | EFS | 2026-02-03 | KAPW-HC-143628 |  | 2026-02-10 |  | 7 | 2026-02-20 |  | 0 | -7 | 2025-12-01 | 757150 | Paid |  |  |  |  | 432067.6475 | Paid | 39.85 | 757150 | 764721.5 | 0.5 | 0.065 |  |  | 1016 | Pcs | 966 | [7 empty] | Arrived at Works |  | 43 | 1 | 1 | 20 | 4
Arrived | QBL-II |  | Store |  | 2944-147 |  | Chromite Sand | BA45 | [5 empty] | 27 | Ton |  |  | 2025-10-27 |  | 2026-01-28 | 13.2857 | Randyrok | South Africa | Johannesburg | 3833 |  | 2025-11-21 | HMB | Advance |  | 540.37 | $ | 281 | 14589.99 | 14589.99 | 4099787.19 | 4099787.19 |  |  |  | 2610 | No | CFR-FCL |  | MSC Sarah V | MSC |  | By Sea | MEDUFI689672 |  | Durban | Karachi | 2025-11-30 | 2025-12-08 | 2025-12-30 | 2026-01-05 | 2026-01-11 |  | 2026-01-11 | 34 |  | 2026-01-12 | KAPS-HC-119932 |  | 2026-01-13 |  | 1 | 2026-01-20 |  | 0 | 8 | 2025-11-21 | 4099787.19 | Paid |  |  |  | 2026-01-12 | 351966.7303 | Paid | 281 | 4099787.19 | 4140785.0619 | 0.02 | 0.065 |  |  | 175 | kg | 170 | [7 empty] | Arrived at Works |  | 29 |  | 1 | 1 | 4
Arrived | QCL |  | Store |  | 23558-60 |  | Neutral Ramming Mass | CXNRM- C-98.5% | [5 empty] | 6 | Ton |  |  | 2025-10-23 |  | 2026-01-23 |  | HK Jinyuen | Hong Kong | Kowloon | 3831 |  | 2025-11-21 | HMB | Advance |  | 1015.5 | $ | 280.8 | 6093 | 6093 | 1710914.4 | 1710914.4 |  |  |  | 3816.002 |  | FOB-LCL |  | WAN HAI 626 |  | Broco | By Sea | JHN25120283 |  | Shanghai | Karachi | 2025-11-30 | 2025-12-29 | 2026-01-22 |  |  |  | 2026-01-22 | 24 | EFS | 2026-01-23 | KAPW-HC-136173 |  | 2026-01-27 |  | 4 | 2026-02-10 |  | 0 | -18 | 2025-11-13 | 1710914.4 | Paid |  |  |  | 2026-01-22 | 181442.4721 | Paid | 280.8 | 1710914.4 | 1728023.544 | 0.04 | 0.065 |  |  | 365 | Kgs | 326 | [7 empty] | Arrived at Works |  | 44 | 1 | 1 | 4 | 2
Arrived | QBL-II |  | Store |  | 19678-60 |  | Exothermic Riser Sleeves | FPS500-S70/140/BGK-1 | [5 empty] | 1200 | Pcs | [5 empty] | 0 | SQ | China |  | 3820 |  | 2025-10-30 | HMB | Advance |  | 1.22 | $ | 281.5 |  | 1464 |  | 412116 |  |  |  | 6903.901 |  | CFR Karachi |  | X-PRESS PHOENIX |  | Yaaseen Shipping | By Sea | JJCQDKRA5550323 |  | Qingdao | Karachi | 2025-11-26 | 2025-12-13 | 2026-01-07 | 2026-01-09 | 2026-01-11 |  | 2026-01-11 | 29 | EFS | 2026-01-12 | KAPS-HC-119931 |  | 2026-01-13 |  | 1 | 2026-01-21 |  | 0 | 0 | 2025-10-30 | 412116 | Paid |  |  |  | 2026-01-12 | 131114.7054 | Paid | 281.5 | 412116 | 416237.16 | 0.25 | 0.065 |  |  |  | Pcs | [8 empty] | Arrived at Works | Sample for QBL-II | 3 | 1 | 1 | 7 | 4
Arrived | QBL-II |  | Store |  | 12576-60 |  | Exothermic Riser Sleeves | FT100(III)T120/240/200/OBG-7 | [5 empty] | 216 | Pcs | [5 empty] | 0 | SQ | China |  | 3820 |  | 2025-10-30 | HMB | Advance |  | 4.35 | $ | 281.5 |  | 939.6 |  | 264497.4 |  |  |  | 6903.901 |  | CFR Karachi |  | X-PRESS PHOENIX |  | Yaaseen Shipping | By Sea | JJCQDKRA5550323 |  | Qingdao | Karachi | 2025-11-26 | 2025-12-13 | 2026-01-07 | 2026-01-09 | 2026-01-11 |  | 2026-01-11 | 29 | EFS | 2026-01-12 | KAPS-HC-119931 |  | 2026-01-13 |  | 1 | 2026-01-21 |  | 0 | 0 | 2025-10-30 | 264497.4 | Paid |  |  |  | 2026-01-12 | 84149.8478 | Paid | 281.5 | 264497.4 | 267142.374 | 0.25 | 0.065 |  |  |  | Pcs | [8 empty] | Arrived at Works | Sample for QBL-II | 3 | 1 | 1 | 7 | 4
Arrived | QBL-II |  | Store |  | 16681-60 |  | Exothermic Pads | FT400 B1520x450x60/785x400x10 | [5 empty] | 15 | Pcs | [5 empty] | 0 | SQ | China |  | 3820 |  | 2025-10-30 | HMB | Advance |  | 47.62 | $ | 281.5 |  | 714.3 |  | 201075.45 |  |  |  | 6903.901 |  | CFR Karachi |  | X-PRESS PHOENIX |  | Yaaseen Shipping | By Sea | JJCQDKRA5550323 |  | Qingdao | Karachi | 2025-11-26 | 2025-12-13 | 2026-01-07 | 2026-01-09 | 2026-01-11 |  | 2026-01-11 | 29 | EFS | 2026-01-12 | KAPS-HC-119931 |  | 2026-01-13 |  | 1 | 2026-01-21 |  | 0 | 0 | 2025-10-30 | 201075.45 | Paid |  |  |  | 2026-01-12 | 63972.1544 | Paid | 281.5 | 201075.45 | 203086.2045 | 0.25 | 0.065 |  |  |  | Pcs | [8 empty] | Arrived at Works | Sample for QBL-II | 3 | 1 | 1 | 7 | 4
Arrived | QBL-II |  | Store |  | TMPNL0155 |  | Chromite Sand | BA45 | [5 empty] | 54 | Ton |  |  | 2025-09-22 |  | 2026-01-01 | 14.4286 | Randyrok | South Africa | Johannesburg | 3791 |  | 2025-10-01 | HMB | Advance |  | 540.37 | $ | 284 |  | 29179.98 |  | 8287114.32 |  |  |  | 2610 | Yes | CFR-FCL |  | MSC ADITI | MSC | MSC Pakistan | By Sea | MEDUJ5685972 | 0 | Durban | Karachi |  | 2025-10-18 | 2025-11-12 | 2025-11-15 |  |  | 2025-11-15 | 28 | EFS | 2025-11-17 | KAPS-FS-85481 | Green | 2025-11-20 |  | 3 | 2025-11-23 | 8.8571 | 0 | 39 | 2025-10-01 | 8287114.32 | Paid |  |  |  | 2025-11-17 | 2469145.7116 | Paid | 284 | 8287114.32 | 8369985.4632 | 0.23 | 0.065 |  |  | 183 | kg | 173 | [7 empty] | Arrived at Works |  | 29 | 1 | 1 | 1 | 4
Arrived | QBL-II |  | Store |  | 1610-60 |  | Cutting Disc | 24" | [5 empty] | 15 | Pcs |  |  | 2025-08-20 |  |  | 0 | Zenith | China | Zhengzhou | 3755 |  | 2025-09-05 | HMB | Advance |  | 94 | $ | 282.15 |  | 1410 |  | 397831.5 |  |  |  | 8207.9 | NO | FOB - LCL | Ceva Logistic | CMA CGM NINGBO | CMA CGM | Ceva Logistic | By Sea | QDWH251018762 | 0 |  | Karachi | 2025-09-20 | 2025-10-18 | 2025-11-08 | 2025-11-16 |  |  | 2025-11-16 | 29 | EFS | 2025-11-17 | KAPW-HC-89169 | Green | 2025-11-27 |  | 10 | 2025-11-26 | 14 | 0 | 0 | 2025-09-05 | 397831.5 | Paid |  |  | Unpaid | 2025-11-17 | 134606.288 | Paid | 282.15 | 397831.5 | 401809.815 | 0.27 | 0.065 |  |  | 31212 | Pcs | 31448 | [7 empty] | Arrived at Works |  | 45 | 1 | 1 |  | 4
Arrived | QEN |  | Store |  | 24573-60 |  | Submerged Welding Wire | AWS A5.28 | [5 empty] | 2000 | Kg |  |  |  | 2025-08-19 |  | 0 | Hunan Fushun | China | Changsha | 3727 |  | 2025-08-22 | HMB | Advance |  | 3.8 | $ | 282.1 |  | 7600 |  | 2143960 |  |  |  | 8311.3 | NO | FOB-FCL | PNSC | X-PRESS CARINA | One Line | PNSC | By Sea | TJZHL250938046N | 0 | XINGANG | Karachi | 2025-09-08 | 2025-10-03 | 2025-10-27 | 2025-10-29 |  |  | 2025-10-29 | 26 | EFS | 2025-10-30 | KAPW-HC-78052 | Green | 2025-11-05 |  | 6 | 2025-11-10 | 0 | 0 | 0 | 2025-08-22 | 2143960 | Paid |  |  |  | 2025-10-28 | 920294.83 | Paid | 282.1 | 2143960 | 2165399.6 | 0.36 | 0.065 |  |  | 1424 | Kg | 1339 | [7 empty] | Arrived at Works | Cargo De-stuffing at port is under process. | 46 | 1 | 1 | 18 | 3
Arrived | QEN | MS25-31 | Store |  | TMPNL0156 |  | 3 Way Vise | EMTAV-4 | [5 empty] | 1 | Pcs | [5 empty] | 0 | HARDY | Taiwan | Taichung | 3719 |  | 2025-08-15 | HMB | Advance |  | 782 | $ | 282.2 |  | 782 |  | 220680.4 | Received | Approved | Approved | 8205.7 | NO | FOB-LCL | Logistic Mode | ESL Dachan Bay |  | Logistic Mode | By Sea | TCKHI2509053822 | 0 | KEELUNG | Karachi | 2025-08-25 | 2025-09-12 | 2025-10-05 | 2025-10-07 |  |  | 2025-10-07 | 25 | EFS | 2025-10-08 | KAPW-HC-62610 | Green | 2025-10-17 |  | 9 | 2025-10-24 | 0 | 0 | 0 | 2025-08-15 | 220680.4 | Paid |  |  |  | 2025-10-07 | 88040.4456 | Paid | 282.2 | 220680.4 | 222887.204 | 0.33 | 0.065 |  |  | 328444 | Pcs | 309232 | [7 empty] | Arrived at Works | Vessel booking received ETD: 13-09-2025 | 40 | 1 | 1 | 21 | 3
Arrived | QE | MS25-28 | Store |  | TMPNL0157 |  | Twin Hose 5mts Coupler NPT 1/4 | [6 empty] | 1 | Pcs | [5 empty] | 0 | SOV Hydraulic | China | Shanghai | 3715 |  | 2025-08-12 | HMB | Advance |  | 200 | $ | 283 |  | 200 |  | 56600 |  |  |  | 3917.33 | NO | FCA-AIR | Broco |  | China Southern | Broco | By Air | SA250804901 | 3 | Shanghai | Lahore | 2025-08-18 | 2025-08-21 | 2025-09-11 |  |  |  | 2025-09-11 | 21 | EFS | 2025-08-23 | KPAF-HC-19080 |  | 2025-08-23 |  | 0 | 2025-08-23 | 0 | 0 | 0 | 2025-08-12 | 56600 | Paid |  |  | Unpaid | 2025-09-11 | 33442.11 | Paid | 283 | 56600 | 57166 | 0.52 | 0.065 |  |  |  | Pcs | [8 empty] | Arrived at Works |  | 47 | 1 | 3 | 4 | 1
Arrived | QEN |  |  |  | TMPNL0158 |  | Torque Wrench | [6 empty] | 1 | Set |  | 0.112 |  |  |  | 0 |  |  |  | 3715 |  |  | HMB | TT | [5 empty] | 8335 |  | 0 | [30 empty] | 2025-08-23 | 0 | 0 | 0 | [17 empty] | Set | [8 empty] | Arrived at Works | On time |  |  |  |  | 3
Arrived | QE | MS25-28 | Store |  | TMPNL0159 |  | Square Drive HydrolicTorque Wrench | SOV-10MXTA | [5 empty] | 1 | Pcs | [5 empty] | 0 | SOV Hydraulic | China | Shanghai | 3715 |  | 2025-08-12 | HMB | Advance |  | 3600 | $ | 283 |  | 3600 |  | 1018800 |  |  |  | 8467.89 | NO | FCA-AIR | Broco |  | China Southern | Broco | By Air | SA250804901 | 3 | Shanghai | Lahore | 2025-08-18 | 2025-08-21 | 2025-09-11 |  |  |  | 2025-09-11 | 21 | EFS | 2025-08-23 | KPAF-HC-19080 |  | 2025-08-23 |  | 0 | 2025-08-23 | 0 | 0 | 0 | 2025-08-12 | 1018800 | Paid |  |  | Unpaid | 2025-09-11 | 324131.22 | Paid | 283 | 1018800 | 1028988 | 0.25 | 0.065 |  |  |  | Pcs | [8 empty] | Arrived at Works |  | 47 | 1 | 3 | 4 | 1
Arrived | QE | MS25-28 | Store |  | TMPNL0160 |  | Electric Hydrolic Pump With HAWE Soleoid | SOV-BSB-2W, Motor Single Phase 220V/50HZ | [5 empty] | 1 | Pcs | [5 empty] | 0 | SOV Hydraulic | China | Shanghai | 3715 |  | 2025-08-12 | HMB | Advance |  | 3935 | $ | 283 |  | 3935 |  | 1113605 |  |  |  | 8413.199 | NO | FCA-AIR | Broco |  | China Southern | Broco | By Air | SA250804901 | 3 | Shanghai | Lahore | 2025-08-18 | 2025-08-21 | 2025-09-11 |  |  |  | 2025-09-11 | 21 | EFS | 2025-08-23 | KPAF-HC-19080 |  | 2025-08-23 |  | 0 | 2025-08-23 | 0 | 0 | 0 | 2025-08-12 | 1113605 | Paid |  |  | Unpaid | 2025-09-11 | 657973.5143 | Paid | 283 | 1113605 | 1124741.05 | 0.52 | 0.065 |  |  |  | Pcs | [8 empty] | Arrived at Works |  | 47 | 1 | 3 | 4 | 1
Arrived | QE | MS25-28 | Store |  | TMPNL0161 |  | 10MXTA Sockets | 55mm(M36),60mm(M39),65mm(M42),70mm(M45),75mm(M48),80mm(M52),85mm(M56),90mm(M60),95mm(M64), | [5 empty] | 1 | Pcs | [5 empty] | 0 | SOV Hydraulic | China | Shanghai | 3715 |  | 2025-08-12 | HMB | Advance |  | 600 | $ | 283 |  | 600 |  | 169800 |  |  |  | 8204.2 | NO | FCA-AIR | Broco |  | China Southern | Broco | By Air | SA250804901 | 3 | Shanghai | Lahore | 2025-08-18 | 2025-08-21 | 2025-09-11 |  |  |  | 2025-09-11 | 21 | EFS | 2025-08-23 | KPAF-HC-19080 |  | 2025-08-23 |  | 0 | 2025-08-23 | 0 | 0 | 0 | 2025-08-12 | 169800 | Paid |  |  | Unpaid | 2025-09-11 | 60881.79 | Paid | 283 | 169800 | 171498 | 0.29 | 0.065 |  |  |  | Pcs | [8 empty] | Arrived at Works |  | 47 | 1 | 3 | 4 | 1
Arrived | QBL-II |  | Store |  | 2944-147 |  | Chromite Sand | Sample | [5 empty] | 1 | Ton | [5 empty] | 0 | IMD | South Africa | Gauteng | 3709 |  | 2025-08-06 | HMB | Advance |  | 655 | $ | 283 |  | 655 |  | 185365 |  |  |  | 2610 | Yes | FOB-LCL |  | Abraya Bhum | YML |  | By Sea | SCZA00140743 | 0 | Durban | Karachi |  | 2025-09-01 | 2025-09-25 | 2025-10-10 |  |  | 2025-10-10 | 39 | EFS | 2025-10-10 | KAPW-HC-63399 | Green | 2025-10-16 |  | 6 | 2025-10-24 | 0 | 0 | 0 | 2025-08-06 | 185365 | Paid |  |  |  | 2025-10-10 | 57101.6882 | Paid | 283 | 185365 | 187218.65 | 0.24 | 0.065 |  |  | 270 | Kg | 290 | [7 empty] | Arrived at Works | Sample Shipment, Vessel rollover ETA shift from 25-09-25 to 10-10-25. | 48 | 1 | 1 | 1 | 4
Arrived | QE |  | Engg. |  | 26368-125 |  | Hex Bolts (Black oxide 12.9) | M39x190 | [5 empty] | 144 | Pcs | [5 empty] | 0 | GT | China | Shanghai | 3644 |  | 2025-06-05 | HMB | Advance |  | 4.05 | $ | 282.6 |  | 583.2 |  | 164812.32 |  | Approved | Approved | 7318.151 | NO | FOB-LCL | Broco | KOTA MANZANILLO | Johan Freight | Broco | By Sea | HANL25080529 | 0 | Ningbo | Karachi | 2025-08-05 | 2025-09-03 | 2025-09-22 |  |  |  | 2025-09-22 | 19 | EFS | 2025-09-22 | KAPW-HC-53485 | Green | 2025-09-27 |  | 5 | 2025-10-04 | 0 | 0 | 0 | 2025-06-05 | 164812.32 | Paid |  |  | Unpaid | 2025-09-22 | 140659.0745 | Paid | 282.6 | 164812.32 | 166460.4432 | 0.78 | 0.065 |  |  |  | Pcs | 1467 | [7 empty] | Arrived at Works | Cargo De-stuffing at port is under process. | 49 | 1 | 1 | 22 | 1
Arrived | QE |  | Engg. |  | 26368-125 |  | Hex Bolts (Black oxide 12.9) | M42x170 | [5 empty] | 320 | Pcs | [5 empty] | 0 | GT | China | Shanghai | 3644 |  | 2025-06-05 | HMB | Advance |  | 4.53 | $ | 282.6 |  | 1449.6 |  | 409656.96 |  | Approved | Approved | 7318.151 | NO | FOB-LCL | Broco | KOTA MANZANILLO | Johan Freight | Broco | By Sea | HANL25080529 | 0 | Ningbo | Karachi | 2025-08-05 | 2025-09-03 | 2025-09-22 |  |  |  | 2025-09-22 | 19 | EFS | 2025-09-22 | KAPW-HC-53485 | Green | 2025-09-27 |  | 5 | 2025-10-04 | 0 | 0 | 0 | 2025-06-05 | 409656.96 | Paid |  |  | Unpaid | 2025-09-22 | 349621.7325 | Paid | 282.6 | 409656.96 | 413753.5296 | 0.78 | 0.065 |  |  |  | Pcs | 1640 | [7 empty] | Arrived at Works | Cargo De-stuffing at port is under process. | 49 | 1 | 1 | 22 | 1
Arrived | QE |  | Engg. |  | 26368-125 |  | Hex Bolts (Black oxide 12.9) | M45x120 | [5 empty] | 32 | Pcs | [5 empty] | 0 | GT | China | Shanghai | 3644 |  | 2025-06-05 | HMB | Advance |  | 3.74 | $ | 282.6 |  | 119.68 |  | 33821.568 |  | Approved | Approved | 7318.151 | NO | FOB-LCL | Broco | KOTA MANZANILLO | Johan Freight | Broco | By Sea | HANL25080529 | 0 | Ningbo | Karachi | 2025-08-05 | 2025-09-03 | 2025-09-22 |  |  |  | 2025-09-22 | 19 | EFS | 2025-09-22 | KAPW-HC-53485 | Green | 2025-09-27 |  | 5 | 2025-10-04 | 0 | 0 | 0 | 2025-06-05 | 33821.568 | Paid |  |  | Unpaid | 2025-09-22 | 28865.0172 | Paid | 282.6 | 33821.568 | 34159.7837 | 0.78 | 0.065 |  |  |  | Pcs | 1361 | [7 empty] | Arrived at Works | Cargo De-stuffing at port is under process. | 49 | 1 | 1 | 22 | 1
Arrived | QE |  | Engg. |  | 26368-125 |  | Hex Bolts (Black oxide 12.9) | M56x160 | [5 empty] | 96 | Pcs | [5 empty] | 0 | GT | China | Shanghai | 3644 |  | 2025-06-05 | HMB | Advance |  | 8.87 | $ | 282.6 |  | 851.52 |  | 240639.552 |  | Approved | Approved | 7318.151 | NO | FOB-LCL | Broco | KOTA MANZANILLO | Johan Freight | Broco | By Sea | HANL25080529 | 0 | Ningbo | Karachi | 2025-08-05 | 2025-09-03 | 2025-09-22 |  |  |  | 2025-09-22 | 19 | EFS | 2025-09-22 | KAPW-HC-53485 | Green | 2025-09-27 |  | 5 | 2025-10-04 | 0 | 0 | 0 | 2025-06-05 | 240639.552 | Paid |  |  | Unpaid | 2025-09-22 | 205373.8257 | Paid | 282.6 | 240639.552 | 243045.9475 | 0.78 | 0.065 |  |  |  | Pcs | 3206 | [7 empty] | Arrived at Works | Cargo De-stuffing at port is under process. | 49 | 1 | 1 | 22 | 1
Arrived | QE |  | Engg. |  | 26368-125 |  | Hex Bolts (Black oxide 12.9) | M56x250 | [5 empty] | 96 | Pcs | [5 empty] | 0 | GT | China | Shanghai | 3644 |  | 2025-06-05 | HMB | Advance |  | 12.07 | $ | 282.6 |  | 1158.72 |  | 327454.272 |  | Approved | Approved | 7318.151 | NO | FOB-LCL | Broco | KOTA MANZANILLO | Johan Freight | Broco | By Sea | HANL25080529 | 0 | Ningbo | Karachi | 2025-08-05 | 2025-09-03 | 2025-09-22 |  |  |  | 2025-09-22 | 19 | EFS | 2025-09-22 | KAPW-HC-53485 | Green | 2025-09-27 |  | 5 | 2025-10-04 | 0 | 0 | 0 | 2025-06-05 | 327454.272 | Paid |  |  | Unpaid | 2025-09-22 | 279465.8484 | Paid | 282.6 | 327454.272 | 330728.8147 | 0.78 | 0.065 |  |  |  | Pcs | 4362 | [7 empty] | Arrived at Works | Cargo De-stuffing at port is under process. | 49 | 1 | 1 | 22 | 1
Arrived | QE |  | Engg. |  | 26368-125 |  | Hex Bolts (Black oxide 12.9) | M48x160 | [5 empty] | 384 | Pcs | [5 empty] | 0 | GT | China | Shanghai | 3644 |  | 2025-06-05 | HMB | Advance |  | 6.04 | $ | 282.6 |  | 2319.36 |  | 655451.136 |  | Approved | Approved | 7318.151 | NO | FOB-LCL | Broco | KOTA MANZANILLO | Johan Freight | Broco | By Sea | HANL25080529 | 0 | Ningbo | Karachi | 2025-08-05 | 2025-09-03 | 2025-09-22 |  |  |  | 2025-09-22 | 19 | EFS | 2025-09-22 | KAPW-HC-53485 | Green | 2025-09-27 |  | 5 | 2025-10-04 | 0 | 0 | 0 | 2025-06-05 | 655451.136 | Paid |  |  | Unpaid | 2025-09-22 | 559394.772 | Paid | 282.6 | 655451.136 | 662005.6474 | 0.78 | 0.065 |  |  |  | Pcs | 2186 | [7 empty] | Arrived at Works | Cargo De-stuffing at port is under process. | 49 | 1 | 1 | 22 | 1
Arrived | QCL |  |  |  | TMPNL0162 |  | HYDRAULIC BONDED CASTABLE TYPE LCC (Sample Order) | [6 empty] | 300 | Kg | [5 empty] | 0 |  |  |  | 3545 | [9 empty] | 582 | 0 | 0 | [11 empty] | ORG2505436EXY | [12 empty] | 2025-06-04 | KAPW-HC-196764 |  |  |  |  | 2025-06-15 | 0 | 0 | 0 | [17 empty] | Kg | [8 empty] | Arrived at Works | On time |  |  |  |  | 2
Arrived | QBL-II |  | Store |  | TMPNL0163 |  | Ferro Moly - ( Trading Purpose ) | [6 empty] | 1 | Ton | [5 empty] | 0 | Paktech | Pakistan | Karachi | 3533 |  | 2025-03-04 | HMB | TT | [5 empty] | 31000 | 0 | 0 |  |  |  | 7202.7 | No | CFR |  | 2025-03-17 | EUNSAN | Green W. - KHI | LCL | ESSASEL25031386 |  | Busan | Karachi-port | 2025-03-12 | 2025-03-17 | 2025-04-18 |  |  |  |  | 4.5714 | Eastern | 2025-04-18 |  | Red |  |  |  | 2025-05-02 | 0 | 0 | 0 | [17 empty] | Ton | [8 empty] | Arrived at Works | On time | 50 | 2 | 2 | 13 | 4
Shafts/Ongoing/Import Status/Import Rem | QCL | Scrap | Store |  | 19969-60 |  | Cast Iron Scrap | [6 empty] | 60.073 | Ton | [6 empty] | KE Metal | USA |  | 2730 | B3 | 2026-05-25 | HMB | LC |  | 440 | $ | 281 |  | 26432.12 |  | 7427425.72 |  |  |  | 7204.109 | NO | CFR |  |  |  |  | Sea |  |  |  | Karachi |  | 2026-06-08 | 2026-07-10 | 2026-07-12 |  |  | 2026-07-12 | 34 | MHQ | [5 empty] | 0 | 2026-07-22 | 0 | 0 | 0 | [6 empty] | 2026-06-10 | 600000 | Unpaid | 281 | 7427425.72 | 7501699.9772 | 0.28 | 0.065 |  |  | 152 | Kgs | [8 empty] | In Transit |  | 8 | 3 | 1 |  | 2
Shafts/Ongoing/Import Status/Import Rem | QCL | Scrap | Store |  | 19969-60 |  | Cast Iron Scrap | [6 empty] | 206.133 | Ton | [6 empty] | KE Metal | USA |  | 2730 | B1 | 2026-05-25 | HMB | LC |  | 440 | $ | 281 | 90698.52 | 90698.52 | 25486284.12 | 25486284.12 |  |  |  | 7204.109 | NO | CFR |  |  |  |  | Sea |  |  |  | Karachi |  | 2026-06-07 | 2026-07-16 | 2026-07-21 |  |  | 2026-07-21 | 44 | MHQ | [5 empty] | 0 | 2026-07-31 | 0 | 0 | 0 | [6 empty] | 2026-06-10 | 600000 | Unpaid | 281 | 25486284.12 | 25741146.9612 | 0.28 | 0.065 |  |  | 152 | Kgs | [8 empty] | In Transit |  | 8 | 3 | 1 |  | 2
Shafts/Ongoing/Import Status/Import Rem | QCL | Scrap | Store |  | 19969-60 |  | Cast Iron Scrap | [6 empty] | 102.977 | Ton | [6 empty] | KE Metal | USA |  | 2730 | B2 | 2026-05-25 | HMB | LC |  | 440 | $ | 281 | 45309.88 | 45309.88 | 12732076.28 | 12732076.28 |  |  |  | 7204.109 | NO | CFR |  |  |  |  | Sea |  |  |  | Karachi |  | 2026-06-07 | 2026-07-16 | 2026-07-23 | 2026-07-28 |  | 2026-07-28 | 51 | MHQ | [5 empty] | 0 | 2026-08-07 | 0 | 0 | 0 | [6 empty] | 2026-06-10 | 600000 | Unpaid | 281 | 12732076.28 | 12859397.0428 | 0.28 | 0.065 |  |  | 152 | Kgs | [8 empty] | In Transit |  | 8 | 3 | 1 |  | 2
Arrived | QCL | Foundry Material | Store |  | 2847-60 |  | Slag Remover(Casting Perlite) | 0.6-1.2MM | [5 empty] | 12000 | Kg |  |  | 2026-02-25 |  | 2026-05-25 | 12.7143 | Cukurova | Turkey |  | 62845 |  | 2026-03-31 | BAH | LC |  | 0.1569 | € | 320.48 | 17049.6 | 1882.8241 | 5464055.808 | 603407.4735 |  |  |  | 2530.1 |  | CFR Karachi |  | SEASPAN BRILLIANCE 101E | One Line | One Line Pakistan | Sea | ONEYISTG06274300 |  | Aliaga | Karachi |  | 2026-05-02 | 2026-06-05 | 2026-06-14 | 2026-06-20 |  | 2026-06-20 | 49 | EFS | [5 empty] | 0 | 2026-06-29 |  | 0 | -35 |  |  |  | 2026-05-25 | 603407.4735 | Paid | 2026-06-22 | 191974.0877 | Paid | 320.48 | 603407.4735 | 609441.5482 | 0.25 | 0.065 |  |  | 60 | Kg | [8 empty] | Arrived at Works | Vessel Booking received. ETD: 22-04-26, Vessel rollover ETD:02-05-2026. ( 7 MT for QCL & 5 MT for QBL) | 11 | 1 | 1 | 9 | 2
Arrived | QCL | Refractory Material | Store |  | 24031-60 |  | Exothermic Riser Sleeves | Beseks 3500 BG 12/300 | [5 empty] | 72 | Pcs |  |  | 2026-02-25 |  | 2026-05-25 | 12.7143 | Cukurova | Turkey |  | 62845 |  | 2026-03-31 | BAH | LC |  | 15.4287 | € | 320.48 |  | 1110.8662 |  | 356010.4093 |  |  |  | 6903.901 |  | CFR Karachi |  | SEASPAN BRILLIANCE 101E | One Line | One Line Pakistan | Sea | ONEYISTG06274300 |  | Aliaga | Karachi |  | 2026-05-02 | 2026-06-05 | 2026-06-14 | 2026-06-20 |  | 2026-06-20 | 49 | EFS | [5 empty] | 0 | 2026-06-29 |  | 0 | -35 |  |  |  | 2026-05-25 | 356010.4093 | Paid | 2026-06-22 | 113264.7117 | Paid | 320.48 | 356010.4093 | 359570.5134 | 0.25 | 0.065 |  |  | 5454 | Pcs | [8 empty] | Arrived at Works | Vessel Booking received. ETD: 22-04-26, Vessel rollover ETD:02-05-2026. ( For QBL-2) | 11 | 1 | 1 | 9 | 2
Arrived | QCL | Refractory Material | Store |  | 25556-60 |  | Exothermic Riser Sleeves | Beseks 3500 BGK 12/400 | [5 empty] | 64 | Pcs |  |  | 2026-02-25 |  | 2026-05-24 | 12.5714 | Cukurova | Turkey |  | 62845 |  | 2026-03-31 | BAH | LC |  | 26.4118 | € | 320.48 |  | 1690.3577 |  | 541725.8206 |  |  |  | 6903.901 |  | CFR Karachi |  | SEASPAN BRILLIANCE 101E | One Line | One Line Pakistan | Sea | ONEYISTG06274300 |  | Aliaga | Karachi |  | 2026-05-02 | 2026-06-05 | 2026-06-14 | 2026-06-20 |  | 2026-06-20 | 49 | EFS | [5 empty] | 0 | 2026-06-29 |  | 0 | -36 |  |  |  | 2026-05-25 | 541725.8206 | Paid | 2026-06-22 | 172350.0698 | Paid | 320.48 | 541725.8206 | 547143.0788 | 0.25 | 0.065 |  |  | 9082 | Pcs | [8 empty] | Arrived at Works | Vessel Booking received. ETD: 22-04-26, Vessel rollover ETD:02-05-2026. ( For QBL-2) | 11 | 1 | 1 | 9 | 2
Arrived | QCL | Refractory Material | Store |  | 12566-60 |  | Exothermic Riser Sleeves | Beseks 3500 BGK 3 | [5 empty] | 3240 | Pcs |  |  | 2026-02-25 |  | 2026-05-24 | 12.5714 | Cukurova | Turkey |  | 62845 |  | 2026-03-31 | BAH | LC |  | 1.4226 | € | 320.48 |  | 4609.1534 |  | 1477141.495 |  |  |  | 6903.901 |  | CFR Karachi |  | SEASPAN BRILLIANCE 101E | One Line | One Line Pakistan | Sea | ONEYISTG06274300 |  | Aliaga | Karachi |  | 2026-05-02 | 2026-06-05 | 2026-06-14 | 2026-06-20 |  | 2026-06-20 | 49 | EFS | [5 empty] | 0 | 2026-06-29 |  | 0 | -36 |  |  |  | 2026-05-25 | 1477141.495 | Paid | 2026-06-22 | 469952.5666 | Paid | 320.48 | 1477141.495 | 1491912.91 | 0.25 | 0.065 |  |  | 509 | Pcs | [8 empty] | Arrived at Works | Vessel Booking received. ETD: 22-04-26, Vessel rollover ETD:02-05-2026. ( For QCL) | 11 | 1 | 1 | 9 | 2
Arrived | QCL | Refractory Material | Store |  | 22496-60 |  | Exothermic Riser Sleeves | Beseks 3500 BGK 4.5 | [5 empty] | 720 | Pcs |  |  | 2026-02-25 |  | 2026-05-24 | 12.5714 | Cukurova | Turkey |  | 62845 |  | 2026-03-31 | BAH | LC |  | 2.7824 | € | 320.48 |  | 2003.3249 |  | 642025.5518 |  |  |  | 6903.901 |  | CFR Karachi |  | SEASPAN BRILLIANCE 101E | One Line | One Line Pakistan | Sea | ONEYISTG06274300 |  | Aliaga | Karachi |  | 2026-05-02 | 2026-06-05 | 2026-06-14 | 2026-06-20 |  | 2026-06-20 | 49 | EFS | [5 empty] | 0 | 2026-06-29 |  | 0 | -36 |  |  |  | 2026-05-25 | 642025.5518 | Paid | 2026-06-22 | 204260.4293 | Paid | 320.48 | 642025.5518 | 648445.8073 | 0.25 | 0.065 |  |  | 978 | Pcs | [8 empty] | Arrived at Works | Vessel Booking received. ETD: 22-04-26, Vessel rollover ETD:02-05-2026. ( For QCL) | 11 | 1 | 1 | 9 | 2
Arrived | QCL | Refractory Material | Store |  | TMPNL0164 |  | Riser Sleeves | BGK-2 | [5 empty] | 3000 | Pcs |  |  | 2026-02-10 |  | 2026-05-04 | 11.8571 | Cukurova | Turkey | Izmir | 2707 |  | 2026-03-17 | HMB | LC |  | 0.75 | € | 333 | 12833.1 | 2250 | 4273422.3 | 749250 |  |  |  | 6903.901 | NO | CFR - FCL |  | Remah | One Line |  | Sea | ONEYISTG05971600 |  | Aliaga | Karachi |  | 2026-04-07 | 2026-05-09 | 2026-05-14 | 2026-05-18 | 2026-05-21 | 2026-05-21 | 44 | EFS | 2026-05-21 | KAPS-HC-198331 |  | 2026-05-22 |  | 1 | 2026-06-01 | 15.8571 | 0 | -28 |  |  |  |  | 749250 | Paid |  | 227022.75 | Paid | 333 | 749250 | 756742.5 | 0.235 | 0.065 |  |  | 279 | Pcs | [8 empty] | Arrived at Works | Shipment ETD is 07-04-2026 and ETA Karachi rollover from 09-05-2026 to 14-05-2026 , to 18-05-2026 and now 21-05-2026 | 11 | 1 | 1 | 9 | 2
Arrived | QCL | Refractory Material | Store |  | TMPNL0165 |  | Riser Sleeves | BGK-8 | [5 empty] | 120 | Pcs |  |  | 2026-01-23 |  | 2026-04-23 | 12.8571 | Cukurova | Turkey | Izmir | 2707 |  | 2026-03-17 | HMB | LC |  | 6.45 | € | 333 |  | 774 |  | 257742 |  |  |  | 6903.901 | NO | CFR - FCL |  | Remah | One Line |  | Sea | ONEYISTG05971600 |  | Aliaga | Karachi |  | 2026-04-07 | 2026-05-09 | 2026-05-14 | 2026-05-18 | 2026-05-21 | 2026-05-21 | 44 | EFS | 2026-05-21 | KAPS-HC-198331 |  | 2026-05-22 |  | 1 | 2026-06-01 | 18.4286 | 0 | -39 |  |  |  |  | 257742 | Paid |  | 78095.826 | Paid | 333 | 257742 | 260319.42 | 0.235 | 0.065 |  |  | 2460 | Pcs | [8 empty] | Arrived at Works | Shipment ETD is 07-04-2026 and ETA Karachi rollover from 09-05-2026 to 14-05-2026 , to 18-05-2026 and now 21-05-2026 | 11 | 1 | 1 | 9 | 2
Arrived | QCL | Refractory Material | Store |  | TMPNL0166 |  | Riser Sleeves | KBG 6/9 | [5 empty] | 11550 | Pcs |  |  | 2026-01-23 |  | 2026-04-23 | 12.8571 | Cukurova | Turkey | Izmir | 2707 |  | 2026-03-17 | HMB | LC |  | 0.47 | € | 333 |  | 5428.5 |  | 1807690.5 |  |  |  | 6903.901 | NO | CFR - FCL |  | Remah | One Line |  | Sea | ONEYISTG05971600 |  | Aliaga | Karachi |  | 2026-04-07 | 2026-05-09 | 2026-05-14 | 2026-05-18 | 2026-05-21 | 2026-05-21 | 44 | EFS | 2026-05-21 | KAPS-HC-198331 |  | 2026-05-22 |  | 1 | 2026-06-01 | 18.4286 | 0 | -39 |  |  |  |  | 1807690.5 | Paid |  | 547730.2215 | Paid | 333 | 1807690.5 | 1825767.405 | 0.235 | 0.065 |  |  | 173 | Pcs | [8 empty] | Arrived at Works | Shipment ETD is 07-04-2026 and ETA Karachi rollover from 09-05-2026 to 14-05-2026 , to 18-05-2026 and now 21-05-2026 | 11 | 1 | 1 | 9 | 2
Arrived | QCL | Refractory Material | Store |  | TMPNL0167 |  | Riser Sleeves | BGK-4 | [5 empty] | 588 | Pcs |  |  | 2026-02-10 |  | 2026-05-04 | 11.8571 | Cukurova | Turkey | Izmir | 2707 |  | 2026-03-17 | HMB | LC |  | 2.1 | € | 333 |  | 1234.8 |  | 411188.4 |  |  |  | 6903.901 | NO | CFR - FCL |  | Remah | One Line |  | Sea | ONEYISTG05971600 |  | Aliaga | Karachi |  | 2026-04-07 | 2026-05-09 | 2026-05-14 | 2026-05-18 | 2026-05-21 | 2026-05-21 | 44 | EFS | 2026-05-21 | KAPS-HC-198331 |  | 2026-05-22 |  | 1 | 2026-06-01 | 15.8571 | 0 | -28 |  |  |  |  | 411188.4 | Paid |  | 124590.0852 | Paid | 333 | 411188.4 | 415300.284 | 0.235 | 0.065 |  |  | 799 | Pcs | [8 empty] | Arrived at Works | Shipment ETD is 07-04-2026 and ETA Karachi rollover from 09-05-2026 to 14-05-2026 , to 18-05-2026 and now 21-05-2026 | 11 | 1 | 1 | 9 | 2
Arrived | QCL | Refractory Material | Store |  | TMPNL0168 |  | Riser Sleeves | BGK-5.5 | [5 empty] | 300 | Pcs |  |  | 2026-02-10 |  | 2026-05-04 | 11.8571 | Cukurova | Turkey | Izmir | 2707 |  | 2026-03-17 | HMB | LC |  | 3.9 | € | 333 |  | 1170 |  | 389610 |  |  |  | 6903.901 | NO | CFR - FCL |  | Remah | One Line | 1 | Sea | ONEYISTG05971600 |  | Aliaga | Karachi |  | 2026-04-07 | 2026-05-09 | 2026-05-14 | 2026-05-18 | 2026-05-21 | 2026-05-21 | 44 | EFS | 2026-05-21 | KAPS-HC-198331 |  | 2026-05-22 |  | 1 | 2026-06-01 | 15.8571 | 0 | -28 |  |  |  |  | 389610 | Paid |  | 118051.83 | Paid | 333 | 389610 | 393506.1 | 0.235 | 0.065 |  |  | 1572 | Pcs | [8 empty] | Arrived at Works | Shipment ETD is 07-04-2026 and ETA Karachi rollover from 09-05-2026 to 14-05-2026 , to 18-05-2026 and now 21-05-2026 | 11 | 1 | 1 | 9 | 2
Arrived | QCL | Refractory Material | Store |  | TMPNL0169 |  | Riser Sleeves | BGK-4.5 | [5 empty] | 180 | Pcs |  |  | 2026-02-10 |  | 2026-05-04 | 11.8571 | Cukurova | Turkey | Izmir | 2707 |  | 2026-03-17 | HMB | LC |  | 2.66 | € | 333 |  | 478.8 |  | 159440.4 |  |  |  | 6903.901 | NO | CFR - FCL |  | Remah | One Line |  | Sea | ONEYISTG05971600 |  | Aliaga | Karachi |  | 2026-04-07 | 2026-05-09 | 2026-05-14 | 2026-05-18 | 2026-05-21 | 2026-05-21 | 44 | EFS | 2026-05-21 | KAPS-HC-198331 |  | 2026-05-22 |  | 1 | 2026-06-01 | 15.8571 | 0 | -28 |  |  |  |  | 159440.4 | Paid |  | 48310.4412 | Paid | 333 | 159440.4 | 161034.804 | 0.235 | 0.065 |  |  | 1042 | Pcs | [8 empty] | Arrived at Works | Shipment ETD is 07-04-2026 and ETA Karachi rollover from 09-05-2026 to 14-05-2026 , to 18-05-2026 and now 21-05-2026 | 11 | 1 | 1 | 9 | 2
Arrived | QCL | Refractory Material | Store |  | TMPNL0170 |  | Riser Sleeves | BGK-2 COVER | [5 empty] | 1568 | Pcs |  |  | 2026-02-10 |  | 2026-05-04 | 11.8571 | Cukurova | Turkey | Izmir | 2707 |  | 2026-03-17 | HMB | LC |  | 0.25 | € | 333 |  | 392 |  | 130536 |  |  |  | 6903.901 | NO | CFR - FCL |  | Remah | One Line |  | Sea | ONEYISTG05971600 |  | Aliaga | Karachi |  | 2026-04-07 | 2026-05-09 | 2026-05-14 | 2026-05-18 | 2026-05-21 | 2026-05-21 | 44 | EFS | 2026-05-21 | KAPS-HC-198331 |  | 2026-05-22 |  | 1 | 2026-06-01 | 15.8571 | 0 | -28 |  |  |  |  | 130536 | Paid |  | 39552.408 | Paid | 333 | 130536 | 131841.36 | 0.235 | 0.065 |  |  | 93 | Pcs | [8 empty] | Arrived at Works | Shipment ETD is 07-04-2026 and ETA Karachi rollover from 09-05-2026 to 14-05-2026 , to 18-05-2026 and now 21-05-2026 | 11 | 1 | 1 | 9 | 2
Arrived | QCL | Refractory Material | Sample |  | TMPNL0171 |  | Riser Sleeves | 2800BGK-2 | [5 empty] | 10 | Pcs | [5 empty] | 0 | Cukurova | Turkey | Izmir | 2707 |  | 2026-03-17 | HMB | LC |  | 0.1 | € | 333 |  | 1 |  | 333 |  |  |  | 6903.901 | NO | CFR - FCL |  | Remah | One Line |  | Sea | ONEYISTG05971600 |  | Aliaga | Karachi |  | 2026-04-07 | 2026-05-09 | 2026-05-14 | 2026-05-18 | 2026-05-21 | 2026-05-21 | 44 | EFS | 2026-05-21 | KAPS-HC-198331 |  | 2026-05-22 |  | 1 | 2026-06-01 | 0 | 0 | 0 |  |  |  |  | 333 | Paid |  | 100.899 | Paid | 333 | 333 | 336.33 | 0.235 | 0.065 |  |  | 279 | Pcs | [8 empty] | Arrived at Works | Shipment ETD is 07-04-2026 and ETA Karachi rollover from 09-05-2026 to 14-05-2026 , to 18-05-2026 and now 21-05-2026 | 11 | 1 | 1 | 9 | 2
Arrived | QCL | Refractory Material | Sample |  | TMPNL0172 |  | Riser Sleeves | 2800BGK-3 | [5 empty] | 10 | Pcs | [5 empty] | 0 | Cukurova | Turkey | Izmir | 2707 |  | 2026-03-17 | HMB | LC |  | 0.1 | € | 333 |  | 1 |  | 333 |  |  |  | 6903.901 | NO | CFR - FCL |  | Remah | One Line |  | Sea | ONEYISTG05971600 |  | Aliaga | Karachi |  | 2026-04-07 | 2026-05-09 | 2026-05-14 | 2026-05-18 | 2026-05-21 | 2026-05-21 | 44 | EFS | 2026-05-21 | KAPS-HC-198331 |  | 2026-05-22 |  | 1 | 2026-06-01 | 0 | 0 | 0 |  |  |  |  | 333 | Paid |  | 100.899 | Paid | 333 | 333 | 336.33 | 0.235 | 0.065 |  |  | 279 | Pcs | [8 empty] | Arrived at Works | Shipment ETD is 07-04-2026 and ETA Karachi rollover from 09-05-2026 to 14-05-2026 , to 18-05-2026 and now 21-05-2026 | 11 | 1 | 1 | 9 | 2
Arrived | QCL | Refractory Material | Sample |  | TMPNL0173 |  | Riser Sleeves | 2800BGK-4 | [5 empty] | 10 | Pcs | [5 empty] | 0 | Cukurova | Turkey | Izmir | 2707 |  | 2026-03-17 | HMB | LC |  | 0.1 | € | 333 |  | 1 |  | 333 |  |  |  | 6903.901 | NO | CFR - FCL |  | Remah | One Line |  | Sea | ONEYISTG05971600 |  | Aliaga | Karachi |  | 2026-04-07 | 2026-05-09 | 2026-05-14 | 2026-05-18 | 2026-05-21 | 2026-05-21 | 44 | EFS | 2026-05-21 | KAPS-HC-198331 |  | 2026-05-22 |  | 1 | 2026-06-01 | 0 | 0 | 0 |  |  |  |  | 333 | Paid |  | 100.899 | Paid | 333 | 333 | 336.33 | 0.235 | 0.065 |  |  | 279 | Pcs | [8 empty] | Arrived at Works | Shipment ETD is 07-04-2026 and ETA Karachi rollover from 09-05-2026 to 14-05-2026 , to 18-05-2026 and now 21-05-2026 | 11 | 1 | 1 | 9 | 2
Arrived | QCL | Refractory Material | Sample |  | TMPNL0174 |  | Riser Sleeves | 2800BGK-4.5 | [5 empty] | 10 | Pcs | [5 empty] | 0 | Cukurova | Turkey | Izmir | 2707 |  | 2026-03-17 | HMB | LC |  | 0.1 | € | 333 |  | 1 |  | 333 |  |  |  | 6903.901 | NO | CFR - FCL |  | Remah | One Line |  | Sea | ONEYISTG05971600 |  | Aliaga | Karachi |  | 2026-04-07 | 2026-05-09 | 2026-05-14 | 2026-05-18 | 2026-05-21 | 2026-05-21 | 44 | EFS | 2026-05-21 | KAPS-HC-198331 |  | 2026-05-22 |  | 1 | 2026-06-01 | 0 | 0 | 0 |  |  |  |  | 333 | Paid |  | 100.899 | Paid | 333 | 333 | 336.33 | 0.235 | 0.065 |  |  | 279 | Pcs | [8 empty] | Arrived at Works | Shipment ETD is 07-04-2026 and ETA Karachi rollover from 09-05-2026 to 14-05-2026 , to 18-05-2026 and now 21-05-2026 | 11 | 1 | 1 | 9 | 2
Arrived | QCL | Refractory Material | Sample |  | TMPNL0175 |  | Riser Sleeves | 2800BGK-5.5 | [5 empty] | 10 | Pcs | [5 empty] | 0 | Cukurova | Turkey | Izmir | 2707 |  | 2026-03-17 | HMB | LC |  | 0.1 | € | 333 |  | 1 |  | 333 |  |  |  | 6903.901 | NO | CFR - FCL |  | Remah | One Line |  | Sea | ONEYISTG05971600 |  | Aliaga | Karachi |  | 2026-04-07 | 2026-05-09 | 2026-05-14 | 2026-05-18 | 2026-05-21 | 2026-05-21 | 44 | EFS | 2026-05-21 | KAPS-HC-198331 |  | 2026-05-22 |  | 1 | 2026-06-01 | 0 | 0 | 0 |  |  |  |  | 333 | Paid |  | 100.899 | Paid | 333 | 333 | 336.33 | 0.235 | 0.065 |  |  | 279 | Pcs | [8 empty] | Arrived at Works | Shipment ETD is 07-04-2026 and ETA Karachi rollover from 09-05-2026 to 14-05-2026 , to 18-05-2026 and now 21-05-2026 | 11 | 1 | 1 | 9 | 2
Arrived | QBL-II | Refractory Material | Store |  | TMPNL0176 |  | IZOPHELA PADS | 550X300X22 | [5 empty] | 250 | Pcs |  |  | 2026-01-27 |  | 2026-04-27 | 12.8571 | Cukurova | Turkey | Izmir | 2707 |  | 2026-03-17 | HMB | LC |  | 4.4 | € | 333 |  | 1100 |  | 366300 |  |  |  | 6903.901 | NO | CFR - FCL |  | Remah | One Line |  | Sea | ONEYISTG05971600 |  | Aliaga | Karachi |  | 2026-04-07 | 2026-05-09 | 2026-05-14 | 2026-05-18 | 2026-05-21 | 2026-05-21 | 44 | EFS | 2026-05-21 | KAPS-HC-198331 |  | 2026-05-22 |  | 1 | 2026-06-01 | 17.8571 | 0 | -35 |  |  |  |  | 366300 | Paid |  | 110988.9 | Paid | 333 | 366300 | 369963 | 0.235 | 0.065 |  |  | 1635 | Pcs | [8 empty] | Arrived at Works | Shipment ETD is 07-04-2026 and ETA Karachi rollover from 09-05-2026 to 14-05-2026 , to 18-05-2026 and now 21-05-2026 | 11 | 1 | 1 | 9 | 4
Arrived | QCL | Foundry Material | Store |  | 24612-60 |  | Resin | A-85 | [5 empty] | 24000 | Kgs |  |  | 2026-01-13 |  | 2026-04-13 | 12.8571 | Cukurova | Turkey |  | 2696 |  | 2026-02-10 | HMB | LC |  | 0.64 | € | 323.8 | 15360 | 15360 | 4973568 | 4973568 |  |  |  | 3824.1 | YES | CFR Karachi |  | CINZIA | CMA CGM |  | Sea | SB1923381 |  | Shanghai | Karachi |  | 2026-03-05 | 2026-04-16 | 2026-04-23 | 2026-04-29 |  | 2026-04-29 | 55 | EFS | 2026-04-30 | KAPS-FS-186504 |  | 2026-05-04 |  | 4 | 2026-05-07 | 0 | 0 | -24 |  |  |  | 2026-03-24 | 4973568 | Paid | 2026-04-30 | 1431641.5488 | Paid | 323.8 | 4973568 | 5023303.68 | 0.22 | 0.065 |  |  | 242 | Kgs | [8 empty] | Arrived at Works | Shipment ETD is 07-04-2026 and ETA Karachi rollover from 09-05-2026 to 14-05-2026 , to 18-05-2026 and now 21-05-2026 | 11 | 1 | 1 | 4 | 2
Shafts/Ongoing/Import Status/Import Rem | QEN | Capex | Capital |  | TMPNL0177 |  | Spindle Gearbox of T130 | CNC Boring Head | [5 empty] | 2 | Pcs | [6 empty] | Luoyang Yujie | China |  | 2695 |  | 2026-02-04 | HMB | LC |  | 79868 | $ | 280 | 159736 | 159736 | 44726080 | 44726080 |  |  |  | 8466.939 |  | FOB Qingdao |  |  |  |  | Sea |  |  |  | Karachi |  | 2026-08-27 | 2026-09-21 |  |  |  | 2026-09-21 | 25 | EFS | [5 empty] | 0 | 2026-09-29 |  |  | 0 |  |  |  | 2026-02-15 | 44726080 | Unpaid | 2026-02-05 | 3839733.968 | Unpaid | 280 | 44726080 | 45173340.8 | 0.02 | 0.065 |  |  | 23824819 | Pcs | [8 empty] | Under Production | 30% Advance and 70% LC at Sight | 51 | 1 | 1 |  | 3
Arrived | QEN | Shafts | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 4140 | OD 835, ID 407 | 780 | SL26-ASMZ-0061 |  | Alliance | 1 | Pcs | 2.56 | 2.56 | 2026-01-16 |  | 2026-05-07 | 15.8571 | Dajin | China |  | 2691 |  | 2026-01-29 | HMB | LC |  | 11400 | ¥ | 40.2 | 191058 | 29184 | 7680531.6 | 1173196.8 |  |  |  | 7228.4 |  | FOB Shanghai |  |  | CNC Line |  | Sea | HTHC26033195-01 |  | Qingdao | Karachi |  | 2026-04-07 | 2026-05-02 | 2026-05-05 |  |  | 2026-05-05 | 28 | EFS | 2026-05-06 | KAPS-FS-189187 |  | 2026-05-08 |  | 2 | 2026-05-12 | 16.5714 | 0 | -5 |  |  |  | 2026-04-24 | 1173196.8 | Paid | 2026-05-06 | 100718.9453 | Paid | 40.2 | 1173196.8 | 1184928.768 | 0.02 | 0.065 |  |  | 560 | Kgs | [8 empty] | Arrived at Works | Material will be ready on dt: 27-03-2026, Shipment booking has been received ETD:07-04-2026, Shipment will reach at QEN on Monday dt: 12-05-2026 | 10 | 1 | 1 | 7 | 3
Arrived | QEN | Shafts | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 4140 | 413 | 2600 | SL26-ASMZ-0060 |  | Alliance | 1 | Pcs | 2.74 | 2.74 | 2026-01-16 |  | 2026-05-07 | 15.8571 | Dajin | China |  | 2691 |  | 2026-01-29 | HMB | LC |  | 8200 | ¥ | 40.2 |  | 22468 | 7680531.6 | 903213.6 |  |  |  | 7228.4 |  | FOB Shanghai |  |  | CNC Line |  | Sea | HTHC26033195-01 |  | Qingdao | Karachi |  | 2026-04-07 | 2026-05-02 | 2026-05-05 |  |  | 2026-05-05 | 28 | EFS | 2026-05-06 | KAPS-FS-189187 |  | 2026-05-08 |  | 2 | 2026-05-12 | 16.5714 | 0 | -5 |  |  |  | 2026-04-24 | 903213.6 | Paid | 2026-05-06 | 77540.8876 | Paid | 40.2 | 903213.6 | 912245.736 | 0.02 | 0.065 |  |  | 417 | Kgs | [8 empty] | Arrived at Works | Material will be ready on dt: 27-03-2026, Shipment booking has been received ETD:07-04-2026, Shipment will reach at QEN on Monday dt: 12-05-2026 | 10 | 1 | 1 | 7 | 3
Arrived | QEN | Shafts | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 4140 | 704 | 5300 | SE25-PGMP-0031 |  | GMP | 1 | Pcs | 16.21 | 16.21 | 2026-01-23 |  | 2026-05-15 | 16 | Dajin | China |  | 2691 |  | 2026-01-29 | HMB | LC |  | 8600 | ¥ | 40.2 |  | 139406 |  | 5604121.2 |  |  |  | 7228.4 |  | FOB Shanghai |  |  | CNC Line |  | Sea | HTHC26033195-01 |  | Qingdao | Karachi |  | 2026-04-07 | 2026-05-02 | 2026-05-05 |  |  | 2026-05-05 | 28 | EFS | 2026-05-06 | KAPS-FS-189187 |  | 2026-05-08 |  | 2 | 2026-05-12 | 15.5714 | 0 | 3 |  |  |  | 2026-04-24 | 5604121.2 | Paid | 2026-05-06 | 481113.805 | Paid | 40.2 | 5604121.2 | 5660162.412 | 0.02 | 0.065 |  |  | 416 | Kgs | [8 empty] | Arrived at Works | Material will be ready on dt: 27-03-2026, Shipment booking has been received ETD:07-04-2026, Shipment will reach at QEN on Monday dt: 12-05-2026 | 10 | 1 | 1 | 7 | 3
Arrived | QCL | Capex | Capital |  | TMPNL0181 |  | LINE FILTER TYPE | UD300+ (G2) | [5 empty] | 2 | Pcs | [5 empty] | 0 | ATLAS COPCO | China | Wuxi | 2687 |  | 2026-01-26 | HMB | LC |  | 1340 | € | 327.5 | 55000 | 2680 | 18012500 | 877700 |  |  |  | 8421.399 |  | CFR Karachi |  |  | Heung A Line |  | Sea | HASLC01260304535 |  |  | Karachi | 2026-03-05 | 2026-03-19 | 2026-04-09 |  |  |  | 2026-04-09 | 21 | EFS | 2026-04-13 | KAPS-HC-175531 |  | 2026-04-14 |  | 1 | 2026-04-18 | 0 | 0 | 0 |  |  |  | 2026-04-10 | 877700 | Paid | 2026-04-13 | 491994.735 | Paid | 327.5 | 877700 | 886477 | 0.49 | 0.065 |  |  |  | Pcs | [8 empty] | Arrived at Works |  | 52 | 1 | 1 |  | 2
Arrived | QCL | Capex | Capital |  | TMPNL0182 |  | Air Screw Compressor | 90 KW(GA90VSD+ P A 13 ML 400 50) | [5 empty] | 1 | Pcs | [5 empty] | 0 | ATLAS COPCO | China | Wuxi | 2687 |  | 2026-01-26 | HMB | LC |  | 24660 | € | 327.5 |  | 24660 |  | 8076150 |  |  |  | 8414.802 |  | CFR Karachi |  |  | Heung A Line |  | Sea | HASLC01260304535 |  |  | Karachi | 2026-02-27 | 2026-03-19 | 2026-04-09 |  |  |  | 2026-04-09 | 21 | EFS | 2026-04-13 | KAPS-HC-175531 |  | 2026-04-14 |  | 1 | 2026-04-18 | 0 | 0 | 0 |  |  |  | 2026-04-10 | 8076150 | Paid | 2026-04-13 | 3548256.5025 | Paid | 327.5 | 8076150 | 8156911.5 | 0.37 | 0.065 |  |  |  | Pcs | [8 empty] | Arrived at Works |  | 52 | 1 | 1 |  | 2
Arrived | QCL | Capex | Capital |  | TMPNL0183 |  | Air Screw Compressor | 75 KW(GA75LVSD+ P A 13 ML 400 50) | [5 empty] | 1 | Pcs | [5 empty] | 0 | ATLAS COPCO | China | Wuxi | 2687 |  | 2026-01-26 | HMB | LC |  | 21660 | € | 327.5 |  | 21660 |  | 7093650 |  |  |  | 8414.802 |  | CFR Karachi |  |  | Heung A Line |  | Sea | HASLC01260304535 |  |  | Karachi | 2026-02-27 | 2026-03-19 | 2026-04-09 |  |  |  | 2026-04-09 | 21 | EFS | 2026-04-13 | KAPS-HC-175531 |  | 2026-04-14 |  | 1 | 2026-04-18 | 0 | 0 | 0 |  |  |  | 2026-04-10 | 7093650 | Paid | 2026-04-13 | 3116595.1275 | Paid | 327.5 | 7093650 | 7164586.5 | 0.37 | 0.065 |  |  |  | Pcs | [8 empty] | Arrived at Works |  | 52 | 1 | 1 |  | 2
Arrived | QCL | Capex | Capital |  | TMPNL0184 |  | AIR DRYER TYPE | FX400-230/1/50-ML | [5 empty] | 2 | Pcs | [5 empty] | 0 | ATLAS COPCO | China | Wuxi | 2687 |  | 2026-01-26 | HMB | LC |  | 3000 | € | 327.5 |  | 6000 |  | 1965000 |  |  |  | 8419.39 |  | CFR Karachi |  |  | Heung A Line |  | Sea | HASLC01260304535 |  |  | Karachi | 2026-02-27 | 2026-03-19 | 2026-04-09 |  |  |  | 2026-04-09 | 21 | EFS | 2026-04-13 | KAPS-HC-175531 |  | 2026-04-14 |  | 1 | 2026-04-18 | 0 | 0 | 0 |  |  |  | 2026-04-10 | 1965000 | Paid | 2026-04-13 | 585471.75 | Paid | 327.5 | 1965000 | 1984650 | 0.23 | 0.065 |  |  |  | Pcs | [8 empty] | Arrived at Works |  | 52 | 1 | 1 |  | 2
Shafts/Ongoing/Import Status/Import Rem | QEN | Capex | Capital |  | TMPNL0185 |  | Spindle Gearbox of T130 | CNC Boring Head | [5 empty] | 1 | Pcs | [6 empty] | Luoyang Yujie | China |  | 2683 |  | 2026-01-19 | HMB | LC |  | 79868 | $ | 282 | 79868 | 79868 | 22522776 | 22522776 |  |  |  | 8466.939 |  | FOB Qingdao |  |  |  |  | Sea |  |  |  | Karachi |  | 2026-06-27 | 2026-07-22 |  |  |  | 2026-07-22 | 25 | EFS | [5 empty] | 0 | 2026-07-30 | 0 | 0 | 0 |  |  |  | 2026-01-25 | 22522776 | Unpaid | 2026-02-05 | 1933580.3196 | Unpaid | 282 | 22522776 | 22748003.76 | 0.02 | 0.065 |  |  | 23824819 | Pcs | [8 empty] | Under Production | 30% Advance and 70% LC at Sight | 51 | 1 | 1 |  | 3
Arrived | QCL | Foundry Material | Store |  | TMPNL0186 |  | Foundry Coke | 80-140mm | [5 empty] | 115.88 | Ton |  |  | 2025-12-24 |  | 2026-03-24 | 12.8571 | Italiana Coke | Italy |  | 2682 | B1 | 2026-01-28 | HMB | LC |  | 498 | $ | 282 | 57708.24 | 57708.24 | 16273723.68 | 16273723.68 |  |  |  | 2704.001 | YES | CFR Karachi |  | Maersk Newbury | Maersk Line |  | Sea | 266773520 |  | VADO LIGURE | Karachi |  | 2026-03-11 | 2026-04-16 | 2026-04-27 |  |  | 2026-04-27 | 47 | EFS | 2026-04-29 | KPPI-FS-60703 |  | 2026-04-30 |  | 1 | 2026-05-05 | 0 | 0 | -42 |  |  |  | 2026-04-02 | 16273723.68 | Paid | 2026-04-29 | 4848755.9705 | Paid | 282 | 16273723.68 | 16436460.9168 | 0.23 | 0.065 |  |  | 166 | Kgs | [8 empty] | Arrived at Works |  | 53 | 1 | 1 | 23 | 2
Arrived | QCL | Foundry Material | Store |  | TMPNL0187 |  | Foundry Coke | 80-140mm | [5 empty] | 30.74 | Ton |  |  | 2025-12-24 |  | 2026-03-24 | 12.8571 | Italiana Coke | Italy |  | 2682 | B2 | 2026-01-28 | HMB | LC |  | 498 | $ | 282 | 15308.52 | 15308.52 | 4317002.64 | 4317002.64 |  |  |  | 2704.001 | YES | CFR Karachi |  | Maersk Serangoon | Maersk Line |  | Sea | 267326384 |  | VADO LIGURE | Karachi |  | 2026-03-31 | 2026-05-04 | 2026-05-11 |  |  | 2026-05-11 | 41 | EFS | 2026-05-12 | KPPI-FS-63178 |  | 2026-05-14 |  | 2 | 2026-05-19 | 18.4286 | 0 | -56 |  |  |  | 2026-04-20 | 4317002.64 | Paid | 2026-02-05 | 1286250.9366 | Paid | 282 | 4317002.64 | 4360172.6664 | 0.23 | 0.065 |  |  | 166 | Kgs | [8 empty] | Arrived at Works |  | 53 | 1 | 1 | 23 | 2
Arrived | QEN | Capex | Capital |  | TMPNL0188 |  | Ball Screw | DFNUR5010-A1-G1200-1000-C5 | [5 empty] | 1 | Set | [6 empty] | Xhejiang Jianzhuang | China | Lishui | 2680 |  | 2026-01-09 | HMB | LC |  | 310.2 | $ | 282 | 17842.14 | 310.2 | 5031483.48 | 87476.4 |  |  |  | 8483.409 | YES | CFR Karachi |  | BHUDTHI BHUM V. 034W |  | Seagull Shipping | Sea | A92GX08775B |  | Ningbo | Karachi |  | 2026-04-21 | 2026-05-12 | 2026-05-14 | 2026-05-16 | 2026-05-21 | 2026-05-21 | 30 | EFS | 2026-05-22 | KAPW-FS-205466 |  | 2026-05-25 |  | 3 | 2026-06-01 | 18.4286 | 0 | 0 |  |  |  | 2026-04-15 | 87476.4 | Paid | 2025-03-20 | 48151.3844 | Paid | 282 | 87476.4 | 88351.164 | 0.48 | 0.065 |  |  |  | Set | [8 empty] | Arrived at Works | 50% Advance and 50% LC at Sight ( 50% TT Processed) | 54 | 1 | 1 | 22 | 3
Arrived | QEN | Capex | Capital |  | TMPNL0189 |  | Ball Screw | DFNUR6320-A1-G5000-4500-C5 | [5 empty] | 2 | Set | [6 empty] | Xhejiang Jianzhuang | China | Lishui | 2680 |  | 2026-01-09 | HMB | LC |  | 1817.02 | $ | 282 |  | 3634.04 |  | 1024799.28 |  |  |  | 8483.409 | YES | CFR Karachi |  | BHUDTHI BHUM V. 034W |  | Seagull Shipping | Sea | A92GX08775B |  | Ningbo | Karachi |  | 2026-04-21 | 2026-05-12 | 2026-05-14 | 2026-05-16 | 2026-05-21 | 2026-05-21 | 30 | EFS | 2026-05-22 | KAPW-FS-205466 |  | 2026-05-25 |  | 3 | 2026-06-01 | 18.4286 | 0 | 0 |  |  |  | 2026-04-15 | 1024799.28 | Paid | 2025-03-20 | 564100.7637 | Paid | 282 | 1024799.28 | 1035047.2728 | 0.48 | 0.065 |  |  |  | Set | [8 empty] | Arrived at Works | 50% Advance and 50% LC at Sight ( 50% TT Processed) | 54 | 1 | 1 | 22 | 3
Arrived | QEN | Capex | Capital |  | TMPNL0190 |  | Ball Screw | DFNUR6320-A1-G4500-4000-C5 | [5 empty] | 1 | Set | [6 empty] | Xhejiang Jianzhuang | China | Lishui | 2680 |  | 2026-01-09 | HMB | LC |  | 1700.46 | $ | 282 |  | 1700.46 |  | 479529.72 |  |  |  | 8483.409 | YES | CFR Karachi |  | BHUDTHI BHUM V. 034W |  | Seagull Shipping | Sea | A92GX08775B |  | Ningbo | Karachi |  | 2026-04-21 | 2026-05-12 | 2026-05-14 | 2026-05-16 | 2026-05-21 | 2026-05-21 | 30 | EFS | 2026-05-22 | KAPW-FS-205466 |  | 2026-05-25 |  | 3 | 2026-06-01 | 18.4286 | 0 | 0 |  |  |  | 2026-04-15 | 479529.72 | Paid | 2025-03-20 | 263957.1344 | Paid | 282 | 479529.72 | 484325.0172 | 0.48 | 0.065 |  |  |  | Set | [8 empty] | Arrived at Works | 50% Advance and 50% LC at Sight ( 50% TT Processed) | 54 | 1 | 1 | 22 | 3
Arrived | QEN | Capex | Capital |  | TMPNL0191 |  | Ball Screw | DFNUR6320-A1-G2000-1500-C5 | [5 empty] | 2 | Set | [6 empty] | Xhejiang Jianzhuang | China | Lishui | 2680 |  | 2026-01-09 | HMB | LC |  | 1110.14 | $ | 282 |  | 2220.28 |  | 626118.96 |  |  |  | 8483.409 | YES | CFR Karachi |  | BHUDTHI BHUM V. 034W |  | Seagull Shipping | Sea | A92GX08775B |  | Ningbo | Karachi |  | 2026-04-21 | 2026-05-12 | 2026-05-14 | 2026-05-16 | 2026-05-21 | 2026-05-21 | 30 | EFS | 2026-05-22 | KAPW-FS-205466 |  | 2026-05-25 |  | 3 | 2026-06-01 | 18.4286 | 0 | 0 |  |  |  | 2026-04-15 | 626118.96 | Paid | 2025-03-20 | 344647.1815 | Paid | 282 | 626118.96 | 632380.1496 | 0.48 | 0.065 |  |  |  | Set | [8 empty] | Arrived at Works | 50% Advance and 50% LC at Sight ( 50% TT Processed) | 54 | 1 | 1 | 22 | 3
Arrived | QEN | Capex | Capital |  | TMPNL0192 |  | Ball Screw | DFNUR6320-A1-F1600-1200-C7 | [5 empty] | 1 | Set | [6 empty] | Xhejiang Jianzhuang | China | Lishui | 2680 |  | 2026-01-09 | HMB | LC |  | 752 | $ | 282 |  | 752 |  | 212064 |  |  |  | 8483.409 | YES | CFR Karachi |  | BHUDTHI BHUM V. 034W |  | Seagull Shipping | Sea | A92GX08775B |  | Ningbo | Karachi |  | 2026-04-21 | 2026-05-12 | 2026-05-14 | 2026-05-16 | 2026-05-21 | 2026-05-21 | 30 | EFS | 2026-05-22 | KAPW-FS-205466 |  | 2026-05-25 |  | 3 | 2026-06-01 | 18.4286 | 0 | 0 |  |  |  | 2026-04-15 | 212064 | Paid | 2025-03-20 | 116730.6288 | Paid | 282 | 212064 | 214184.64 | 0.48 | 0.065 |  |  |  | Set | [8 empty] | Arrived at Works | 50% Advance and 50% LC at Sight ( 50% TT Processed) | 54 | 1 | 1 | 22 | 3
Arrived | QEN | Capex | Capital |  | TMPNL0193 |  | Ball Screw | DFNUR6320-A1-F2300-1800-C7 | [5 empty] | 2 | Set | [6 empty] | Xhejiang Jianzhuang | China | Lishui | 2680 |  | 2026-01-09 | HMB | LC |  | 847.88 | $ | 282 |  | 1695.76 |  | 478204.32 |  |  |  | 8483.409 | YES | CFR Karachi |  | BHUDTHI BHUM V. 034W |  | Seagull Shipping | Sea | A92GX08775B |  | Ningbo | Karachi |  | 2026-04-21 | 2026-05-12 | 2026-05-14 | 2026-05-16 | 2026-05-21 | 2026-05-21 | 30 | EFS | 2026-05-22 | KAPW-FS-205466 |  | 2026-05-25 |  | 3 | 2026-06-01 | 18.4286 | 0 | 0 |  |  |  | 2026-04-15 | 478204.32 | Paid | 2025-03-20 | 263227.5679 | Paid | 282 | 478204.32 | 482986.3632 | 0.48 | 0.065 |  |  |  | Set | [8 empty] | Arrived at Works | 50% Advance and 50% LC at Sight ( 50% TT Processed) | 54 | 1 | 1 | 22 | 3
Arrived | QEN | Capex | Capital |  | TMPNL0194 |  | Ball Screw | DFNUR6320-A1-F3500-3000-C7 | [5 empty] | 3 | Set | [6 empty] | Xhejiang Jianzhuang | China | Lishui | 2680 |  | 2026-01-09 | HMB | LC |  | 1015.2 | $ | 282 |  | 3045.6 |  | 858859.2 |  |  |  | 8483.409 | YES | CFR Karachi |  | BHUDTHI BHUM V. 034W |  | Seagull Shipping | Sea | A92GX08775B |  | Ningbo | Karachi |  | 2026-04-21 | 2026-05-12 | 2026-05-14 | 2026-05-16 | 2026-05-21 | 2026-05-21 | 30 | EFS | 2026-05-22 | KAPW-FS-205466 |  | 2026-05-25 |  | 3 | 2026-06-01 | 18.4286 | 0 | 0 |  |  |  | 2026-04-15 | 858859.2 | Paid | 2025-03-20 | 472759.0466 | Paid | 282 | 858859.2 | 867447.792 | 0.48 | 0.065 |  |  |  | Set | [8 empty] | Arrived at Works | 50% Advance and 50% LC at Sight ( 50% TT Processed) | 54 | 1 | 1 | 22 | 3
Arrived | QEN | Capex | Capital |  | TMPNL0195 |  | Ball Screw | DFNUR8020-A1-F3500-3000-C7 | [5 empty] | 3 | Set | [6 empty] | Xhejiang Jianzhuang | China | Lishui | 2680 |  | 2026-01-09 | HMB | LC |  | 1494.6 | $ | 282 |  | 4483.8 |  | 1264431.6 |  |  |  | 8483.409 | YES | CFR Karachi |  | BHUDTHI BHUM V. 034W |  | Seagull Shipping | Sea | A92GX08775B |  | Ningbo | Karachi |  | 2026-04-21 | 2026-05-12 | 2026-05-14 | 2026-05-16 | 2026-05-21 | 2026-05-21 | 30 | EFS | 2026-05-22 | KAPW-FS-205466 |  | 2026-05-25 |  | 3 | 2026-06-01 | 18.4286 | 0 | 0 |  |  |  | 2026-04-15 | 1264431.6 | Paid | 2025-03-20 | 696006.3742 | Paid | 282 | 1264431.6 | 1277075.916 | 0.48 | 0.065 |  |  |  | Set | [8 empty] | Arrived at Works | 50% Advance and 50% LC at Sight ( 50% TT Processed) | 54 | 1 | 1 | 22 | 3
Arrived | QBL-II |  | Store |  | 26287-60 |  | Resin | APR-103D | [5 empty] | 21.6 | Ton |  | 21.6 |  |  |  |  | SQ | China | Jinancity | 2666 |  | 2025-12-23 | HMB | LC |  | 770 | $ | 280 | 16632 | 16632 | 4656960 | 4656960 |  |  |  | 3824.1 | YES | CFR Karachi |  | MSC EMANUELA | MSC |  | Sea | MEDUWA412271 |  | QINGDAO | Karachi | 2026-01-13 | 2026-01-22 | 2026-02-22 | 2026-02-26 |  |  | 2026-02-26 |  | EFS | 2026-02-27 | KAPS-FS-150490 |  | 2026-03-04 |  | 5 | 2026-03-09 | 18.4286 | 0 | 0 |  |  |  | 2026-02-11 | 4656960 | Paid | 2026-02-26 | 1387541.232 | Paid | 280 | 4656960 | 4703529.6 | 0.23 | 0.065 |  |  | 245 | Kg | 239 |  | 2026-06-12 | 70 |  |  |  |  | Arrived at Works | 15.2 Ton for QCL and 6.4 Ton from QBL-2 | 3 | 1 | 1 | 7 | 4
Arrived | QEN |  | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 1045 | 383 | 4570 | SL25-SWSM-0115 |  | SW Sugar | 1 | Pcs | 4.134 | 4.134 | 2025-12-01 |  | 2026-02-23 | 12 | Qilu | China |  | 2660 | B1 | 2025-12-05 | HMB | LC |  | 7700 | ¥ | 40 | 276476.2 | 31831.8 | 11059048 | 1273272 |  |  |  | 7214.109 |  | FOB |  | Zhong GU XI AN |  | Broco | Sea | SW25E017886 |  | Shanghai | Karachi |  | 2026-02-20 | 2026-03-14 |  |  |  | 2026-03-14 | 22 | EFS | 2026-03-17 | KAPS-FS-159477 |  | 2026-03-19 |  | 2 | 2026-03-30 | 17 | 0 | -35 |  |  |  | 2026-02-05 | 1273272 | Paid | 2026-03-14 | 109310.4012 | Paid | 40 | 1273272 | 1286004.72 | 0.02 | 0.065 |  |  | 370 | Kg | 372 | [7 empty] | Arrived at Works | Vessel Rollover from ETD: 25-01-26 to 09-02-2026 & 17-02-26 due to shipper export license issue and vessel rollover. | 5 | 1 | 1 | 4 | 3
Arrived | QEN |  | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 1045 | 663 | 5860 | SL25-SWSM-0115 |  | SW Sugar | 2 | Pcs | 15.886 | 31.772 | 2025-12-01 |  | 2026-02-23 | 12 | Qilu | China |  | 2660 | B1 | 2025-12-05 | HMB | LC |  | 7700 | ¥ | 40 |  | 244644.4 |  | 9785776 |  |  |  | 7214.109 |  | FOB |  | Zhong GU XI AN |  | Broco | Sea | SW25E017886 |  | Shanghai | Karachi |  | 2026-02-20 | 2026-03-14 |  |  |  | 2026-03-14 | 22 | EFS | 2026-03-17 | KAPS-FS-159477 |  | 2026-03-19 |  | 2 | 2026-03-30 | 17 | 0 | -35 |  |  |  | 2026-02-05 | 9785776 | Paid | 2026-03-14 | 840108.8696 | Paid | 40 | 9785776 | 9883633.76 | 0.02 | 0.065 |  |  | 370 | Kg | 372 | [7 empty] | Arrived at Works | Vessel Rollover from ETD: 25-01-26 to 09-02-2026 & 17-02-26 due to shipper export license issue and vessel rollover. | 5 | 1 | 1 | 4 | 3
Arrived | QEN |  | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 1045 | 663 | 5860 | SL25-SWSM-0115 |  | SW Sugar | 1 | Pcs | 15.88 | 15.88 | 2025-12-01 |  | 2026-02-23 | 12 | Qilu | China |  | 2660 | B2 | 2025-12-05 | HMB | LC |  | 7700 | ¥ | 40 | 122276 | 122276 | 4891040 | 4891040 |  |  |  | 7214.109 |  | FOB |  | Ever Smart |  | Broco | Sea | SW26E001046 |  | Shanghai | Karachi |  | 2026-02-22 | 2026-03-17 | 2026-03-19 | 2026-03-21 |  | 2026-03-21 | 27 |  | 2026-03-24 | KAPS-FS-152510 |  | 2026-03-24 |  | 0 | 2026-04-02 | 17.4286 | 0 | -38 |  |  |  | 2026-02-05 | 4891040 | Paid | 2026-03-21 | 419895.784 | Paid | 40 | 4891040 | 4939950.4 | 0.02 | 0.065 |  |  | 370 | Kg | 372 | [7 empty] | Arrived at Works | Vessel Rollover from ETD: 25-01-26 to 09-02-2026 & 17-02-26 due to shipper export license issue and vessel rollover. | 5 |  | 1 | 4 | 3
Arrived | QCL |  | Store |  | 2825-156 |  | Ferro Manganese H. Carbon | Mn 70-75%, C 6-8%, Si 2%, P 0.35%, S0.04% | [5 empty] | 25 | Ton |  |  | 2025-11-21 |  | 2026-02-21 | 13.1429 | JEIL | Korea |  | 2659 |  | 2025-12-05 | HMB | LC |  | 1045 | $ | 282 | 26125 | 26125 | 7367250 | 7367250 |  |  |  | 7202.11 | NO | CFR Karachi |  | OOCL JAKARTA |  |  | Sea | YMJAS491311547 |  | HAIPHONG PORT | Karachi | 2025-11-20 | 2025-12-17 | 2026-01-04 |  |  |  | 2026-01-04 | 18 |  | 2026-01-06 | KAPW-HC-123901 |  | 2026-01-08 |  | 2 | 2026-01-14 |  | 0 | 38 |  |  |  | 2026-01-10 | 7367250 | Paid | 2026-01-07 | 2195072.1375 | Paid | 280.35 | 7367250 | 7440922.5 | 0.23 | 0.065 |  |  | 327 | Kg | [8 empty] | Arrived at Works |  | 28 |  | 1 | 24 | 2
Arrived | QEN |  | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 1045 | 586 | 5010 | SE25-LAGL-0022 |  | LA Gloria | 1 | Pcs | 10.62 | 10.62 | 2025-11-20 |  | 2026-02-15 | 12.4286 | Dajin | China | Laiwu | 2658 |  | 2025-12-03 | HMB | LC |  | 7700 | ¥ | 40 | 155771 | 81774 | 6230840 | 3270960 |  |  |  | 7214.109 | YES | FOB Shanghai |  | HEMMA BHUM |  | Broco | Sea | SW25E017873 |  | Shanghai | Karachi |  | 2026-01-11 | 2026-02-01 | 2026-02-02 | 2026-02-03 |  | 2026-02-03 | 23 | EFS | 2026-02-03 | KAPS-FS-133648 |  | 2026-02-04 |  | 1 | 2026-02-10 | 11.7143 | 0 | 5 |  |  |  | 2026-02-02 | 3270960 | Paid |  | 346885.308 | Paid | 40.75 | 3270960 | 3303669.6 | 0.04 | 0.065 |  |  | 372 | Kg | 359 | [7 empty] | Arrived at Works |  | 10 | 1 | 1 | 4 | 3
Arrived | QEN |  | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 1045 | 575 | 4705 | SE25-LAGL-0023 |  | LA Gloria | 1 | Pcs | 9.61 | 9.61 | 2025-11-20 |  | 2026-02-15 | 12.4286 | Dajin | China | Laiwu | 2658 |  | 2025-12-03 | HMB | LC |  | 7700 | ¥ | 40 |  | 73997 |  | 2959880 |  |  |  | 7214.109 | YES | FOB Shanghai |  | HEMMA BHUM |  | Broco | Sea | SW25E017873 |  | Shanghai | Karachi |  | 2026-01-11 | 2026-02-01 | 2026-02-02 | 2026-02-03 |  | 2026-02-03 | 23 | EFS | 2026-02-03 | KAPS-FS-133648 |  | 2026-02-04 |  | 1 | 2026-02-10 | 11.7143 | 0 | 5 |  |  |  | 2026-02-02 | 2959880 | Paid |  | 313895.274 | Paid | 40.75 | 2959880 | 2989478.8 | 0.04 | 0.065 |  |  | 372 | Kg | 359 | [7 empty] | Arrived at Works |  | 10 | 1 | 1 | 4 | 3
Arrived | QCL |  | Store |  | 26287-60 |  | Resin | APR-103D | [5 empty] | 9.6 | Ton |  |  | 2025-10-23 |  | 2026-01-23 | 13.1429 | SQ | China |  | 2656 |  | 2025-12-03 | HMB | LC |  | 790 | $ | 279.8 | 21042.57 | 7584 | 5887711.086 | 2122003.2 |  |  |  | 3824.1 |  | CFR Karachi |  |  | CMA CGM | CMA CGM - KHI | Sea | QGD2560214 |  | QINGDAO | Karachi |  | 2026-01-24 | 2026-02-18 | 2026-02-21 |  |  | 2026-02-21 | 28 | EFS | 2026-02-23 | KAPS-HC-146575 |  | 2026-02-24 |  | 1 | 2026-02-27 |  | 0 | -35 |  |  |  | 2026-02-12 | 2122003.2 | Paid | 2026-02-21 | 632250.8534 | Paid | 279.8 | 2122003.2 | 2143223.232 | 0.23 | 0.065 |  |  | 254 | Kg | 247 | [7 empty] | Arrived at Works |  | 3 | 1 | 1 | 7 | 2
Arrived | QCL |  | Store |  | 26486-60 |  | Intensifier | RISA5107 | [5 empty] | 5.061 | Ton |  |  | 2025-11-21 |  | 2026-02-21 | 13.1429 | SQ | China |  | 2656 |  | 2025-12-03 | HMB | LC |  | 770 | $ | 279.8 |  | 3896.97 |  | 1090372.206 |  |  |  | 3824.1 |  | CFR Karachi |  |  | CMA CGM | CMA CGM - KHI | Sea | QGD2560214 |  | QINGDAO | Karachi |  | 2026-01-24 | 2026-02-18 | 2026-02-21 |  |  | 2026-02-21 | 28 | EFS | 2026-02-23 | KAPS-HC-146575 |  | 2026-02-24 |  | 1 | 2026-02-27 |  | 0 | -6 |  |  |  | 2026-02-12 | 1090372.206 | Paid | 2026-02-21 | 324876.3988 | Paid | 279.8 | 1090372.206 | 1101275.9281 | 0.23 | 0.065 |  |  | 582 | Kg | 570 | [7 empty] | Arrived at Works |  | 3 | 1 | 1 | 7 | 2
Arrived | QCL |  | Store |  | 26487-60 |  | Intensifier | RISA5100 | [5 empty] | 4.98 | Ton |  |  | 2025-11-21 |  | 2026-02-21 | 13.1429 | SQ | China |  | 2656 |  | 2025-12-03 | HMB | LC |  | 1920 | $ | 279.8 |  | 9561.6 |  | 2675335.68 |  |  |  | 3824.1 |  | CFR Karachi |  |  | CMA CGM | CMA CGM - KHI | Sea | QGD2560214 |  | QINGDAO | Karachi |  | 2026-01-24 | 2026-02-18 | 2026-02-21 |  |  | 2026-02-21 | 28 | EFS | 2026-02-23 | KAPS-HC-146575 |  | 2026-02-24 |  | 1 | 2026-02-27 |  | 0 | -6 |  |  |  | 2026-02-12 | 2675335.68 | Paid | 2026-02-21 | 797116.2659 | Paid | 279.8 | 2675335.68 | 2702089.0368 | 0.23 | 0.065 |  |  | 250 | Kg | 241 | [7 empty] | Arrived at Works |  | 3 | 1 | 1 | 7 | 2
Arrived | QCL |  | Store |  | 19969-60 |  | Cast Iron Scrap | [6 empty] | 163.603 | Ton | [5 empty] | 0 | KE Metal | Canada |  | 2655 |  | 2025-12-04 | HMB | LC |  | 370 | $ | 280.3 | 60533.11 | 60533.11 | 16967430.733 | 16967430.733 |  |  |  | 7204.109 | NO | CFR Karachi |  | MSC CAROLINA | MSC | MSC Pakistan | By Sea | MEDUOQ016133 |  | NEW YORK,USA | Karachi | 2025-12-10 | 2025-12-17 | 2026-02-22 | 2026-02-25 | 2026-03-08 |  | 2026-03-08 | 81 | MHQ | 2026-03-10 | KAPPI-HC-53662 |  | 2026-03-12 |  | 2 | 2026-03-24 |  | 0 | 0 |  |  |  | 2026-01-08 | 16967430.733 | Paid | 2026-03-08 | 5912301.2389 | Paid | 280.3 | 16967430.733 | 17137105.0403 | 0.28 | 0.065 |  |  | 131 | Kg | 132 | [7 empty] | Arrived at Works |  | 8 | 3 | 1 | 25 | 2
Arrived | QCL |  | Store |  | 26287-60 |  | Resin | A85 | [5 empty] | 7200 | Kg |  |  | 2025-10-23 |  | 2026-01-23 |  | Cukurova | Turkey | Manisa | 2652 |  | 2025-11-21 | HMB | LC | 2026-01-14 | 0.69721 | £ | 326 | 16862 | 5019.9363 | 5497012 | 1636499.2497 |  |  |  | 3824.1 |  | CFR-FCL |  | CMA CGM OSAKA | CMA CGM |  | By Sea | ISB1875771 |  | Aliaga | Karachi | 2025-12-20 | 2025-12-26 | 2026-02-05 |  |  |  | 2026-02-05 | 41 | EFS | 2026-02-06 | KAPE-HC-53015 |  | 2026-02-12 |  | 6 | 2026-02-15 |  | 0 | -23 |  |  |  | 2026-01-14 | 1636499.2497 | Paid |  | 487594.9515 | Paid | 326 | 1636499.2497 | 1652864.2422 | 0.23 | 0.065 |  |  |  | Kg | 264 | [7 empty] | Arrived at Works | Vessel booking received from Cukurova ETD:17-12-2025, Vessel rollover ETD:30-12-25 | 11 | 1 | 1 | 9 | 2
Arrived | QCL |  | Hammad Cukurova |  | TMPNL0201 |  | Foundry Binder | HB 21 | [5 empty] | 500 | Kg | [6 empty] | Cukurova | Turkey | Manisa | 2652 |  | 2025-11-21 | HMB | LC | 2026-01-14 | 1.2043 | £ | 326 |  | 602.1388 |  | 196297.2585 |  |  |  | 3824.1 |  | CFR-FCL |  | CMA CGM OSAKA | CMA CGM |  | By Sea | ISB1875771 |  | Aliaga | Karachi | 2025-12-20 | 2025-12-26 | 2026-02-05 |  |  |  | 2026-02-05 | 41 | EFS | 2026-02-06 | KAPE-HC-53015 |  | 2026-02-12 |  | 6 | 2026-02-15 |  | 0 | 0 |  |  |  | 2026-01-14 | 196297.2585 | Paid |  | 58486.7682 | Paid | 326 | 196297.2585 | 198260.2311 | 0.23 | 0.065 |  |  |  | Kg | 424 | [7 empty] | Arrived at Works | Trading Mtaerial for Hammad Cukurova/Vessel booking received from Cukurova ETD:17-12-2025 | 11 | 1 | 1 | 9 | 2
Arrived | QCL |  | Hammad Cukurova |  | TMPNL0202 |  | Foundry Binder | OA1 | [5 empty] | 100 | Kg | [6 empty] | Cukurova | Turkey | Manisa | 2652 |  | 2025-11-21 | HMB | LC | 2026-01-14 | 0.89793 | £ | 326 |  | 89.7926 |  | 29272.3982 |  |  |  | 3824.1 |  | CFR-FCL |  | CMA CGM OSAKA | CMA CGM |  | By Sea | ISB1875771 |  | Aliaga | Karachi | 2025-12-20 | 2025-12-26 | 2026-02-05 |  |  |  | 2026-02-05 | 41 | EFS | 2026-02-06 | KAPE-HC-53015 |  | 2026-02-12 |  | 6 | 2026-02-15 |  | 0 | 0 |  |  |  | 2026-01-14 | 29272.3982 | Paid |  | 8721.711 | Paid | 326 | 29272.3982 | 29565.1222 | 0.23 | 0.065 |  |  |  | Kg | 327 | [7 empty] | Arrived at Works | Trading Mtaerial for Hammad Cukurova/Vessel booking received from Cukurova ETD:17-12-2025 | 11 | 1 | 1 | 9 | 2
Arrived | QCL |  | Store |  | 23557-60 |  | Foundry Binder | CK021SM | [5 empty] | 2700 | Kg |  |  | 2025-11-11 |  | 2026-02-11 |  | Cukurova | Turkey | Manisa | 2652 |  | 2025-11-21 | HMB | LC | 2026-01-14 | 1.6374 | £ | 326 |  | 4420.9667 |  | 1441235.1347 |  |  |  | 3824.1 |  | CFR-FCL |  | CMA CGM OSAKA | CMA CGM |  | By Sea | ISB1875771 |  | Aliaga | Karachi | 2025-12-20 | 2025-12-26 | 2026-02-05 |  |  |  | 2026-02-05 | 41 | EFS | 2026-02-06 | KAPE-HC-53015 |  | 2026-02-12 |  | 6 | 2026-02-15 |  | 0 | -4 |  |  |  | 2026-01-14 | 1441235.1347 | Paid |  | 429416.0084 | Paid | 326 | 1441235.1347 | 1455647.486 | 0.23 | 0.065 |  |  |  | Kg | 561 | [7 empty] | Arrived at Works | Vessel booking received from Cukurova ETD:17-12-2025, Vessel rollover ETD:30-12-25 | 11 | 1 | 1 | 9 | 2
Arrived | QCL |  | Hammad Cukurova |  | TMPNL0203 |  | Foundry Binder | L5060 | [5 empty] | 100 | Kg | [6 empty] | Cukurova | Turkey | Manisa | 2652 |  | 2025-11-21 | HMB | LC | 2026-01-14 | 1.2677 | £ | 326 |  | 126.7661 |  | 41325.7386 |  |  |  | 3824.1 |  | CFR-FCL |  | CMA CGM OSAKA | CMA CGM |  | By Sea | ISB1875771 |  | Aliaga | Karachi | 2025-12-20 | 2025-12-26 | 2026-02-05 |  |  |  | 2026-02-05 | 41 | EFS | 2026-02-06 | KAPE-HC-53015 |  | 2026-02-12 |  | 6 | 2026-02-15 |  | 0 | 0 |  |  |  | 2026-01-14 | 41325.7386 | Paid |  | 12313.0038 | Paid | 326 | 41325.7386 | 41738.996 | 0.23 | 0.065 |  |  |  | Kg | 444 | [7 empty] | Arrived at Works | Trading Mtaerial for Hammad Cukurova/Vessel booking received from Cukurova ETD:17-12-2025 | 11 | 1 | 1 | 9 | 2
Arrived | QCL |  | Store |  | 18988-60 |  | Exothermic Pads | 550*300*22 | [5 empty] | 1250 | Pcs |  |  | 2025-10-23 |  | 2026-01-23 |  | Cukurova | Turkey | Manisa | 2652 |  | 2025-11-21 | HMB | LC | 2026-01-14 | 4.6481 | £ | 326 |  | 5810.1115 |  | 1894096.3538 |  |  |  | 6903.901 |  | CFR-FCL |  | CMA CGM OSAKA | CMA CGM |  | By Sea | ISB1875771 |  | Aliaga | Karachi | 2025-12-20 | 2025-12-26 | 2026-02-05 |  |  |  | 2026-02-05 | 41 | EFS | 2026-02-06 | KAPE-HC-53015 |  | 2026-02-12 |  | 6 | 2026-02-15 |  | 0 | -23 |  |  |  | 2026-01-14 | 1894096.3538 | Paid |  | 621737.1281 | Paid | 326 | 1894096.3538 | 1913037.3174 | 0.26 | 0.065 |  |  |  | Pcs | 1558 | [7 empty] | Arrived at Works | Vessel booking received from Cukurova ETD:17-12-2025, Vessel rollover ETD:30-12-25 | 11 | 1 | 1 | 9 | 2
Arrived | QCL |  | Store |  | 21199-127 |  | Cast Perlite(Slag Remover) | 0.6-1.2mm | [5 empty] | 5000 | Kg |  |  | 2025-10-23 |  | 2026-01-23 |  | Cukurova | Turkey | Manisa | 2652 |  | 2025-11-21 | HMB | LC | 2026-01-14 | 0.15846 | £ | 326 |  | 792.2879 |  | 258285.8664 |  |  |  | 2530.1 |  | CFR-FCL |  | CMA CGM OSAKA | CMA CGM |  | By Sea | ISB1875771 |  | Aliaga | Karachi | 2025-12-20 | 2025-12-26 | 2026-02-05 |  |  |  | 2026-02-05 | 41 | EFS | 2026-02-06 | KAPE-HC-53015 |  | 2026-02-12 |  | 6 | 2026-02-15 |  | 0 | -23 |  |  |  | 2026-01-14 | 258285.8664 | Paid |  | 76956.2739 | Paid | 326 | 258285.8664 | 260868.7251 | 0.23 | 0.065 |  |  |  | Kg | 94 | [7 empty] | Arrived at Works | Vessel booking received from Cukurova ETD:17-12-2025, Vessel rollover ETD:30-12-25 - DHL number received - Dox retiremnet request proceeded - 06-01-26 - Clearance request pending | 11 | 1 | 1 | 9 | 2
Arrived | QEN | SR25-36 | Engg. |  | TMPNL0204 |  | Forged Alloy Steel Round Bar | 4140 | 456 | 2000 | CE25-MPTS-0008 |  | Mechprotech | 1 | Pcs | 2.56 | 2.56 | 2025-10-23 | 2025-10-24 | 2026-01-14 | 11.8571 | Qilu | China |  | 2645 |  | 2025-10-29 | HMB | LC |  | 10000 | ¥ | 39.5 |  | 25600 |  | 1011200 |  |  |  | 7228.4 |  | FOB-LCL |  |  |  | FREIGHT HUB | By Sea | JHN25120209 |  | Shanghai | Karachi |  | 2025-12-24 | 2026-01-09 | 2026-01-11 |  |  | 2026-01-11 | 18 | EFS | 2026-01-12 | KAPE-FS-46679 |  | 2026-01-19 |  | 7 | 2026-01-24 | 13.2857 | -0.14286 | -10 |  |  |  | 2026-01-08 | 1011200 | Paid | 2026-01-16 | 86811.52 | Paid | 39.5 | 1011200 | 1021312 | 0.02 | 0.065 |  |  |  | Pcs | [8 empty] | Arrived at Works | On time delivery/Docs retirement Awaited. | 5 | 1 | 1 | 4 | 3
Arrived | QEN | SR25-36 | Engg. |  | TMPNL0204 |  | Forged Alloy Steel Round Bar | 30CrNiMo8 | 385 | 5650 | CL25-DCLH-0055 |  | DEWAN © | 1 | Pcs | 5.16 | 5.16 |  | 2025-10-24 |  | 0 | Qilu | China |  | 2645 |  | 2025-10-29 | HMB | LC |  | 13400 | ¥ | 39.5 |  | 69144 |  | 2731188 |  |  |  | 7228.4 |  | FOB-LCL |  |  |  | FREIGHT HUB | By Sea | JHN25120209 |  | Shanghai | Karachi |  | 2025-12-24 | 2026-01-09 | 2026-01-11 |  |  | 2026-01-11 | 18 | EFS | [5 empty] | 0 | 2026-01-24 | 0 | 0 | 0 |  |  |  | 2026-01-08 | 2731188 | Paid | 2026-01-16 | 234472.4898 | Paid | 39.5 | 2731188 | 2758499.88 | 0.02 | 0.065 |  |  |  | Pcs | [8 empty] | Arrived at Works | On time delivery/Docs retirement Awaited. | 5 | 1 | 1 | 4 | 3
Arrived | QEN | SR25-33 | Store |  | TMPNL0012 |  | Forged Steel Round Bar | 1045 | 638 | 5520 | Stock |  | Stock | 1 | Pcs | 13.86 | 13.86 | Stock | 2025-10-02 |  | 0 | Qilu | China | Jining | 2633 |  | 2025-10-06 | HMB | LC |  | 8350 | ¥ | 40 |  | 115731 |  | 4629240 |  |  |  | 7214.109 |  | CFR Karachi |  | Hema Bhum | Interasia | Rahmat Shipping | By Sea | A56FX32273 | 21 | Shnaghai | Karachi | 2025-11-17 | 2025-11-20 | 2025-12-11 | 2025-12-18 |  |  | 2025-12-18 | 28 | EFS | 2025-12-19 | KAPS-FS-105408 | Green | 2025-12-20 |  | 1 | 2025-12-28 |  |  | 0 |  |  |  | 2025-12-10 | 4629240 | Paid | 2025-12-19 | 397420.254 | Paid | 40 | 4629240 | 4675532.4 | 0.02 | 0.065 |  |  |  | Pcs | 366 | [7 empty] | Arrived at Works | Vessel rollover ETA from 11-12-2025 to 18-12-2025. | 5 | 1 | 1 | 10 | 3
Arrived | QEN | SR25-33 | Store |  | TMPNL0012 |  | Forged Steel Round Bar | 1045 | 415 | 418 | SE25-STMA-0029 |  | SKOR'TSF | 1 | Pcs | 3.95 | 3.95 | 2025-10-16 | 2025-10-16 | 2026-01-06 | 11.7143 | Qilu | China | Jining | 2633 |  | 2025-10-06 | HMB | LC |  | 8350 | ¥ | 40 |  | 32982.5 |  | 1319300 |  |  |  | 7214.109 |  | CFR Karachi |  | Hema Bhum | Interasia | Rahmat Shipping | By Sea | A56FX32273 | 21 | Shnaghai | Karachi | 2025-11-17 | 2025-11-20 | 2025-12-11 | 2025-12-18 |  |  | 2025-12-18 | 28 | EFS | 2025-12-19 | KAPS-FS-105408 | Green | 2025-12-20 |  | 1 | 2025-12-28 | 10.4286 | 0 | 9 |  |  |  | 2025-12-10 | 1319300 | Paid | 2025-12-19 | 113261.905 | Paid | 40 | 1319300 | 1332493 | 0.02 | 0.065 |  |  |  | Pcs | 366 | [7 empty] | Arrived at Works | Vessel rollover ETA from 11-12-2025 to 18-12-2025. | 5 | 1 | 1 | 10 | 3
Arrived | QEN | SR25-33 | Store |  | TMPNL0012 |  | Forged Steel Round Bar | 1045 | 415 | 418 | SE25-STMA-0030 |  | SKOR'TSF | 1 | Pcs | 3.95 | 3.95 | 2025-10-16 | 2025-10-16 | 2026-01-06 | 11.7143 | Qilu | China | Jining | 2633 |  | 2025-10-06 | HMB | LC |  | 8350 | ¥ | 40 |  | 32982.5 |  | 1319300 |  |  |  | 7214.109 |  | CFR Karachi |  | Hema Bhum | Interasia | Rahmat Shipping | By Sea | A56FX32273 | 21 | Shnaghai | Karachi | 2025-11-17 | 2025-11-20 | 2025-12-11 | 2025-12-18 |  |  | 2025-12-18 | 28 | EFS | 2025-12-19 | KAPS-FS-105408 | Green | 2025-12-20 |  | 1 | 2025-12-28 | 10.4286 | 0 | 9 |  |  |  | 2025-12-10 | 1319300 | Paid | 2025-12-19 | 113261.905 | Paid | 40 | 1319300 | 1332493 | 0.02 | 0.065 |  |  |  | Pcs | 366 | [7 empty] | Arrived at Works | Vessel rollover ETA from 11-12-2025 to 18-12-2025. | 5 | 1 | 1 | 10 | 3
Arrived | QCL |  | Store |  | TMPNL0209 |  | Foundary Binder | T10 | [5 empty] | 250 | Kg | [6 empty] | Cukurova | Turkey | Manisa | 2628 |  | 2025-09-25 | HMB | LC |  | 1.4 | € | 330 |  | 350 |  | 115500 |  |  |  | 3824.1 | NO | CFR-FCL |  | HONG LI YUAN YANG | AKKON Lines | Freight Connection | By Sea | AKKALI25027204 | 0 | Aliaga | Karachi | 2025-10-15 | 2025-11-04 | 2025-11-18 | 2025-11-20 |  |  | 2025-11-20 | 16 | EFS | 2025-11-21 | KAPE-HC-35633 | Green | 2025-11-24 |  | 3 | 2025-11-28 | 0 | 0 | 0 |  |  |  | 2025-11-13 | 115500 | Paid | 2025-11-20 | 36746.325 | Paid | 330 | 115500 | 116655 | 0.25 | 0.065 |  |  |  | Kg | 537 | [7 empty] | Arrived at Works | Additional QTY added for Hammad CUKUROVA/Vessel Booking received on Dt: 20-10-2025, ETD: 03-11-2025 | 11 | 1 | 1 | 9 | 2
Arrived | QCL |  | Store |  | TMPNL0210 |  | Foundary Binder | FL69000 | [5 empty] | 120 | Kg | [6 empty] | Cukurova | Turkey | Manisa | 2628 |  | 2025-09-25 | HMB | LC |  | 1.6 | € | 330 |  | 192 |  | 63360 |  |  |  | 3824.1 | NO | CFR-FCL |  | HONG LI YUAN YANG | AKKON Lines | Freight Connection | By Sea | AKKALI25027204 | 0 | Aliaga | Karachi | 2025-10-15 | 2025-11-04 | 2025-11-18 | 2025-11-20 |  |  | 2025-11-20 | 16 | EFS | 2025-11-21 | KAPE-HC-35633 | Green | 2025-11-24 |  | 3 | 2025-11-28 | 0 | 0 | 0 |  |  |  | 2025-11-13 | 63360 | Paid | 2025-11-20 | 20157.984 | Paid | 330 | 63360 | 63993.6 | 0.25 | 0.065 |  |  |  | Kg | 604 | [7 empty] | Arrived at Works | Additional QTY added for Hammad CUKUROVA/Vessel Booking received on Dt: 20-10-2025, ETD: 03-11-2025 | 11 | 1 | 1 | 9 | 2
Arrived | QCL |  | Store |  | TMPNL0211 |  | Foundary Binder | Reflak 655 SD | [5 empty] | 25 | Kg | [6 empty] | Cukurova | Turkey | Manisa | 2628 |  | 2025-09-25 | HMB | LC |  | 1.15 | € | 330 |  | 28.75 |  | 9487.5 |  |  |  | 3824.1 | NO | CFR-FCL |  | HONG LI YUAN YANG | AKKON Lines | Freight Connection | By Sea | AKKALI25027204 | 0 | Aliaga | Karachi | 2025-10-15 | 2025-11-04 | 2025-11-18 | 2025-11-20 |  |  | 2025-11-20 | 16 | EFS | 2025-11-21 | KAPE-HC-35633 | Green | 2025-11-24 |  | 3 | 2025-11-28 | 0 | 0 | 0 |  |  |  | 2025-11-13 | 9487.5 | Paid | 2025-11-20 | 3018.4481 | Paid | 330 | 9487.5 | 9582.375 | 0.25 | 0.065 |  |  |  | Kg | 454 | [7 empty] | Arrived at Works | QBL-II Sample/Vessel Booking received on Dt: 20-10-2025, ETD: 03-11-2025 | 11 | 1 | 1 | 9 | 2
Arrived | QCL |  | Store |  | TMPNL0212 |  | Exothermic Riser Sleeves | BGK-0 | [5 empty] | 1950 | Pcs | [6 empty] | Cukurova | Turkey | Manisa | 2628 |  | 2025-09-25 | HMB | LC |  | 0.54 | € | 330 |  | 1053 |  | 347490 |  |  |  | 6903.901 | NO | CFR-FCL |  | HONG LI YUAN YANG | AKKON Lines | Freight Connection | By Sea | AKKALI25027204 | 0 | Aliaga | Karachi | 2025-10-15 | 2025-11-04 | 2025-11-18 | 2025-11-20 |  |  | 2025-11-20 | 16 | EFS | 2025-11-21 | KAPE-HC-35633 | Green | 2025-11-24 |  | 3 | 2025-11-28 | 0 | 0 | 0 |  |  |  | 2025-11-13 | 347490 | Paid | 2025-11-20 | 110553.9435 | Paid | 330 | 347490 | 350964.9 | 0.25 | 0.065 |  |  | 196 | Pcs | 189 | [7 empty] | Arrived at Works | Additional QTY added for Hammad CUKUROVA/Vessel Booking received on Dt: 20-10-2025, ETD: 03-11-2025 | 11 | 1 | 1 | 9 | 2
Arrived | QCL |  | Store |  | TMPNL0213 |  | Exothermic Riser Sleeves | BGK-2 | [5 empty] | 750 | Pcs | [6 empty] | Cukurova | Turkey | Manisa | 2628 |  | 2025-09-25 | HMB | LC |  | 0.82 | € | 330 |  | 615 |  | 202950 |  |  |  | 6903.901 | NO | CFR-FCL |  | HONG LI YUAN YANG | AKKON Lines | Freight Connection | By Sea | AKKALI25027204 | 0 | Aliaga | Karachi | 2025-10-15 | 2025-11-04 | 2025-11-18 | 2025-11-20 |  |  | 2025-11-20 | 16 | EFS | 2025-11-21 | KAPE-HC-35633 | Green | 2025-11-24 |  | 3 | 2025-11-28 | 0 | 0 | 0 |  |  |  | 2025-11-13 | 202950 | Paid | 2025-11-20 | 64568.5425 | Paid | 330 | 202950 | 204979.5 | 0.25 | 0.065 |  |  |  | Pcs | 290 | [7 empty] | Arrived at Works | Additional QTY added for Hammad CUKUROVA/Vessel Booking received on Dt: 20-10-2025, ETD: 03-11-2025 | 11 | 1 | 1 | 9 | 2
Arrived | QCL |  | Store |  | TMPNL0214 |  | Exothermic Riser Sleeves | BGK-3 | [5 empty] | 720 | Pcs | [6 empty] | Cukurova | Turkey | Manisa | 2628 |  | 2025-09-25 | HMB | LC |  | 1.5 | € | 330 |  | 1080 |  | 356400 |  |  |  | 6903.901 | NO | CFR-FCL |  | HONG LI YUAN YANG | AKKON Lines | Freight Connection | By Sea | AKKALI25027204 | 0 | Aliaga | Karachi | 2025-10-15 | 2025-11-04 | 2025-11-18 | 2025-11-20 |  |  | 2025-11-20 | 16 | EFS | 2025-11-21 | KAPE-HC-35633 | Green | 2025-11-24 |  | 3 | 2025-11-28 | 0 | 0 | 0 |  |  |  | 2025-11-13 | 356400 | Paid | 2025-11-20 | 113388.66 | Paid | 330 | 356400 | 359964 | 0.25 | 0.065 |  |  | 548 | Pcs | 533 | [7 empty] | Arrived at Works | Additional QTY added for Hammad CUKUROVA/Vessel Booking received on Dt: 20-10-2025, ETD: 03-11-2025 | 11 | 1 | 1 | 9 | 2
Arrived | QEN | MS25-25 | Store |  | TMPNL0215 |  | IGBT for I. H. | 300 KW | [5 empty] | 1 | Set |  |  |  | 2025-07-08 |  | 0 | Kotron | China | Zhenzhou | 2596 |  | 2025-07-18 | HMB | LC |  | 58000 | $ | 281.15 |  | 58000 |  | 16306700 |  |  |  | 8514.4 | NO | FOB-FCL | PNSC | WAN HAI 622 |  | PNSC | By Sea | HWKHI2501053 | 21 | Shanghai | Karachi | 2025-10-15 | 2025-10-27 | 2025-11-18 |  |  |  | 2025-11-18 | 22 | EFS | 2025-11-20 | KAPW-HC-91255 | Green | 2025-11-22 |  | 2 | 2025-11-28 | 0 | 0 | 0 |  |  | Unpaid | 2025-11-13 | 16306700 | Paid | 2025-11-20 | 4858581.265 | Paid | 281.15 | 16306700 | 16469767 | 0.23 | 0.065 |  |  | 17800000 | Set | 17002542 | [7 empty] | Arrived at Works | Awaited demand from QEN./Material is ready, paxcking list sent to logistics for forwarder arrangements. | 19 | 1 | 1 | 4 | 3
Arrived | QCL |  |  |  | 19969-60 |  | SCRAP OF CAST IRON | [6 empty] | 169.425 | Ton | [5 empty] | 0 |  |  |  | 2582 |  | 2025-06-23 | [5 empty] | 283.8 |  | 66075.75 |  | 18752297.85 | [11 empty] | MEDUJV905701 | [12 empty] | 2025-08-15 | KPPI-HC-8860 |  | 2025-08-17 |  |  | 2025-08-19 | 0 | 0 | 0 | [17 empty] | Ton | [8 empty] | Arrived at Works | On time |  |  |  |  | 2
Arrived | QCL |  | Store |  | 19969-60 |  | Cast Iron Scrap | Oversized | [5 empty] | 169.425 | Ton | [5 empty] | 0 | KE Metal | USA |  | 2582 |  | 2025-06-23 | HMB | LC | 2025-07-28 | 390 | $ | 283.8 |  | 66075.75 |  | 18752297.85 |  |  |  | 7204.109 | NO | CFR - FCL |  | MSC Bremen | MSC | MSC Pakistan | By Sea | MEDUJV905701 | FCL | Houston | Karachi |  | 2025-06-30 | 2025-08-12 |  |  |  | 2025-08-12 | 43 | MHQ | 2025-08-15 | KPPI-HC-8860 |  | 2025-08-15 |  | 0 | 2025-08-31 | 0 | 0 | 0 |  |  | Unpaid | 2025-07-28 | 18752297.85 | Paid | 2025-08-15 | 6723636.3941 | Paid | 283.8 | 18752297.85 | 18939820.8285 | 0.29 | 0.065 |  |  |  | Ton | [8 empty] | Arrived at Works | On-time ( ETA changed from 02-Sep to 09-Sep, 13 Sep & 20 Sep) | 8 | 3 | 1 | 26 | 2
Arrived | QH |  | Store |  | TMPNL0216 |  | UT Failed Shafts | [6 empty] | 50.39 | Ton | 50.39 | 50.39 |  |  |  | 0 | Dajin | China |  | 2540 |  | 2025-05-16 | HMB | LC |  |  |  | 282.25 |  | 40376 |  | 11396126 |  |  |  | 7204.491 | No | CFR |  |  | MSC |  | 2 x 20' STD | MEDUQV182520 | 14 | Qingdao | Port Qasim |  | 2025-04-21 | 2025-06-30 |  |  |  |  | 10 | MHQ | 2025-07-24 | KPPI-HC-4645 | Yellow | 2025-07-29 |  | 29 | 2025-08-02 | 0 | 0 | 0 | [17 empty] | Ton | [8 empty] | Arrived at Works | On time | 10 | 3 | 4 | 7 | 5
Arrived | QCL |  | Scraps |  | 19984-60 |  | SS Scrap | 25% Cr | [5 empty] | 77 | Tons | [5 empty] | 0 | Dhatu | Singapore | Singapore | 2505 |  | 2024-12-23 | HMB | LC |  |  |  | 278.8 |  | 63148 |  | 17605662.4 |  |  |  | 7204.21 | Yes | CFR |  | 2024-12-31 | Maersk | Maersk - KHI | 3 x 20' Std. | MAEU247948385 | 14 | Fremantle | Port Qasim | Pending | 2024-12-31 | 2025-02-22 |  |  |  |  | 7.5714 | Muzammil | 2025-02-24 | KPPI-FS-46617 | Green | 2025-03-03 | 2025-03-07 | 9 | 2025-03-06 | 0 | 0 | 0 | [17 empty] | Tons | [8 empty] | Arrived at Works | On time | 55 | 5 | 4 | 27 | 2
Arrived | QCL |  | Scraps |  | 23562-60 |  | Manganese Steel Scrap | 16% Mn | [5 empty] | 65.5 | Tons | [5 empty] | 0 | KE Metal | Canada | Markham | 2501 |  | 2024-12-13 | HMB | LC |  |  |  | 279.4 |  | 31383 |  | 8768410.2 |  |  |  | 7204.29 | Yes | CFR |  | 2024-12-22 | Hapag-Lloyd | Hapag-Lloyd - KHI | 3 x 20' Std. | HLCUBSC2412BIWc2 | 14 | Norfolk | Port Qasim | Pending | 2025-01-08 | 2025-02-13 |  |  |  |  | 5.1429 | Muzammil | 2025-02-14 | KPPI-FS-44902 | Green | 2025-02-18 | 2025-02-27 | 4 | 2025-02-21 | 0 | 0 | 0 | [17 empty] | Tons | [8 empty] | Arrived at Works | On time | 8 | 5 | 4 | 28 | 2
Arrived | QH |  | Store |  | TMPNL0217 |  | UT Failed Shafts | [6 empty] | 25.96 | Ton | 25.96 | 25.96 |  |  |  | 0 | Dajin | China |  | 2488 |  | 2024-12-12 | HMB | LC | [5 empty] | 214717 |  | 0 |  |  |  | 7204.491 | No | CFR |  |  | MSC |  | 1 x 20' STD | NEDUFD529311 | 14 | Qingdao | Port Qasim |  | 2024-11-27 | 2024-12-22 |  |  |  |  | 3.5714 | MHQ | 2025-01-13 | KPPI-HC-38366 | Green | 2025-01-14 | 2025-01-05 | 23 | 2025-01-17 | 0 | 0 | 0 | [17 empty] | Ton | [8 empty] | Arrived at Works | On time | 10 | 3 | 4 | 7 | 5
Arrived | QCL |  | Scraps |  | 19969-60 |  | SCRAP OF CAST IRON | Oversized | [5 empty] | 109 | Tons | [5 empty] | 0 | KE Metal | Canada | Markham | 2473 |  | 2024-09-02 | HMB | LC |  |  |  | 278.85 |  | 42385 |  | 11819057.25 |  |  |  | 7204.109 | No | CFR |  | 2024-11-25 | MSC | MSC - KHI | 4 x 20' Std. | MEDUOF257945 | 14 | Montreal | Port Qasim | 2024-11-22 | 2024-11-25 | 2025-01-25 |  |  |  |  | 8.7143 | Muzammil | 2025-01-28 | KPPI-HC-41475 | Green | 2025-01-31 | 2025-02-07 | 6 | 2025-02-02 | 0 | 0 | 0 | [17 empty] | Tons | [8 empty] | Arrived at Works | On time | 8 | 5 | 4 | 29 | 2
Arrived | QE | Temporray Import | Refurb. |  | TMPNL0218 |  | Old Roll | [6 empty] | 1 | Pcs | [6 empty] | Sonkor | South Africa |  | 2418 | [8 empty] | 0 |  | 0 | [6 empty] | CFR Karachi |  |  |  |  | Sea | DBA0401097 |  |  | Karachi |  | 2026-03-06 | 2026-05-06 | 2026-05-14 | 2026-05-17 |  | 2026-05-17 | 72 |  | 2026-05-18 | KAPS-TI-195947 |  | 2026-05-22 |  | 4 | 2026-06-01 |  | 0 | 0 | [6 empty] | 2026-06-10 | 600000 | Paid | 0 | 0 | 0 | 0.23 | 0.065 |  |  |  | Pcs | [8 empty] | Arrived at Works |  | 2 |  | 1 |  | 1
Arrived | QE | Temporray Import | Refurb. |  | TMPNL0219 |  | Old Roll | [6 empty] | 2 | Pcs | [6 empty] | CASA | Phillpines |  | 2410 | B1 |  | HMB | [5 empty] | 0 |  | 0 | [6 empty] | CFR Karachi |  |  |  |  | Sea | CEB002603 |  |  | Karachi |  | 2026-04-25 | 2026-05-13 |  |  |  | 2026-05-13 | 18 | EFS | 2026-05-20 | KAPS-TI-197712 |  | 2026-05-23 |  | 3 | 2026-06-04 |  | 0 | 0 | [6 empty] | 2026-06-10 | 600000 | Paid | 0 | 0 | 0 | 0.23 | 0.065 |  |  |  | Pcs | [8 empty] | Arrived at Works |  | 56 | 1 | 1 |  | 1
Arrived | QE |  | Refurb. |  | TMPNL0220 |  | Old Rolls- 3 Pcs |  |  |  | EXP 2409 |  |  | 3 | Pcs | [6 empty] | Sonkor | South Africa |  | 2409 |  |  | BAH | CAD |  |  |  |  | 0 |  | 0 | [6 empty] | CFR Karachi |  |  | Hapag Lloyd | CEVA | Sea | HLCUDUR260132743 |  | Durban | Karachi |  | 2026-02-06 | 2026-03-05 | 2026-03-07 |  |  | 2026-03-07 | 29 | EFS | 2026-03-09 | KAPW-TI-165812 |  | 2026-03-12 |  | 3 | 2026-03-18 |  | 0 | 0 | [6 empty] | 2026-02-25 | 750000 | Paid | 0 | 0 | 0 | 0.22 | 0.065 |  |  |  | Pcs | [8 empty] | Arrived at Works |  | 2 | 1 | 1 | 1 | 1
Arrived | QE |  | Refurb. |  | TMPNL0221 |  | Old Rolls |  |  |  | Exp 2372 |  | Bais | 2 | Pcs | 18.75 | 56.25 |  |  |  |  | Bais | Tanzania | Dumaguete | 2372 |  |  | HMB | Exp |  |  | $ |  | 0 |  | 0 |  |  |  |  | 8438.901 |  | CFR Karachi |  | ARIONAS | CMA CGM | Broco | By Sea | GHC0327461 | FCL | Cebu | Karachi |  | 2026-01-15 | 2026-03-14 | 2026-03-15 |  |  | 2026-03-15 | 59 | EFS | 2026-03-18 | KAPS-TI-160636 |  | 2026-03-27 |  | 9 | 2026-04-02 | 0 | 0 | 0 |  | 0 | Unpaid |  |  |  | 2026-03-15 | 200000 | Paid | 0 | 0 | 0 | [5 empty] | Pcs | [8 empty] | Arrived at Works |  | 57 | 1 | 1 | 30 | 1
Arrived | QE |  | Refurb. |  | TMPNL0222 |  | Old Rolls |  |  |  | Exp 2372 |  | Bais | 1 | Pcs | 18.75 | 56.25 |  |  |  |  | Bais | Tanzania | Dumaguete | 2372 |  |  | HMB | Exp |  |  | $ |  |  |  | 0 |  |  |  |  | 8438.901 |  | CFR Karachi |  | ARIONAS | CMA CGM | Broco | By Sea | GHC0327450 | FCL | Cebu | Karachi |  | 2026-01-15 | 2026-03-14 | 2026-03-15 |  |  | 2026-03-15 | 59 | EFS | 2026-03-18 | KAPS-TI-162508 |  | 2026-03-27 |  | 9 | 2026-04-02 | 0 | 0 | 0 |  | 0 | Unpaid |  |  |  | 2026-03-15 | 400000 | Paid | 0 | 0 | 0 | [5 empty] | Pcs | [8 empty] | Arrived at Works | Partial Shipment F.I Issue Pending | 57 | 1 | 1 | 30 | 1
Arrived | QE |  |  |  | TMPNL0223 |  | Old Rolls - Busco 02 Pcs | [6 empty] | 2 | Pcs | [5 empty] | 0 | Busco | Philipine |  | 2306 |  |  |  | Exp |  |  | $ | 284 | 10760 | 10760 | 3055840 | 3055840 |  |  |  |  | NO | OLB |  |  |  |  | By Sea |  | FCL |  | Karachi |  | 2025-10-14 | 2025-11-23 |  |  |  | 2025-11-23 | 40 | EFS | 2025-11-24 | KAPW-TI-93845 |  | 2025-12-01 |  | 7 | 2025-12-03 | 0 | 0 | 0 | [5 empty] | Unpaid | 2025-11-24 | 400000 | Paid | 284 | 3055840 | 3086398.4 | [5 empty] | Pcs | [8 empty] | Arrived at Works |  | 58 | 1 | 1 |  | 1
Arrived | QE |  |  |  | TMPNL0224 |  | Old Rolls - Damoisea v 10 Pcs | [6 empty] | 10 | Pcs | [5 empty] | 0 | Sonkor | SA |  | 2275 |  |  |  | Exp |  |  | $ | 284 |  |  |  | 0 |  |  |  |  | NO | OLB Pointe A Pitre |  |  | CMA CGM |  | By Sea | LHV3759939 | FCL | Pointe A Pitre | 0 |  | 2025-08-02 | 2025-10-01 |  |  |  | 2025-10-01 | 60 | EFS | 2025-10-02 | KAPS-TI-56395 | Green | 2025-10-11 |  | 9 | 2025-10-16 | 0 | 0 | 0 |  | 0 |  |  |  | Unpaid | 2025-09-30 | 475000 | Paid | 284 | 0 | 0 |  | 0.065 |  |  |  | Pcs | [8 empty] | Arrived at Works |  | 2 | 1 |  | 31 | 1
Arrived | QE |  |  |  | TMPNL0225 |  | Old Rolls - (S) Transmara | [6 empty] | 2 | Pcs | [5 empty] | 0 | Sonkor | SA |  | 2255 |  |  |  | Exp |  |  | $ | 284 |  | 9848 |  | 2796832 |  |  |  |  | NO | OLB |  |  | One Line |  | By Sea | MBAF00962900 | FCL |  | 0 |  | 2025-07-09 | 2025-09-05 |  |  |  | 2025-09-05 | 58 | EFS | 2025-09-04 | KAPS-TI-38421 | Green | 2025-09-05 |  | 1 | 2025-09-13 | 0 | 0 | 0 |  | 2796832 | Paid |  |  | Paid | 2025-09-05 | 183612.0208 | Paid | 284 | 2796832 | 2824800.32 |  | 0.065 |  |  |  | Pcs | [8 empty] | Arrived at Works |  | 2 | 1 |  |  | 1
Shafts/Ongoing/Import Status/Import Rem | QCL | Foundry Material | Trading |  | TMPNL0226 |  | Anode Butt | [6 empty] | 200 | Ton | [5 empty] | 0 | Daicel International | UAE |  | 952 |  | 2026-02-10 | HMB | Contract |  | 150 | $ | 282 | 30000 | 30000 | 8460000 | 8460000 |  |  |  | 3801.9 |  | CFR Karachi |  |  |  |  | By Sea |  |  |  | Karachi | [14 empty] | 0 |  |  | 0 | 0 |  |  |  | 2026-02-02 | 8460000 | Paid | 2026-02-28 | 2776995 | Unpaid | 282 | 8460000 | 8544600 | 0.26 | 0.065 |  |  |  | Ton | [8 empty] | Under Production | Trading Purpose only. | 59 |  | 1 |  | 2
Arrived | QCL |  | Scraps |  | 24940-60 |  | SS Scrap | 409 | [5 empty] | 21 | Tons | [5 empty] | 0 | KE Metal | Canada | Markham | 675 |  | 2024-12-17 | HMB | CAD |  |  |  | 278.4 |  | 11613 | 3233059.2 | 3233059.2 |  |  |  | 7204.21 | No | CFR |  | 2024-11-27 | MSC | MSC - KHI | 1 x 40' HC | MEDUHE971500 | 14 | Houston | Port Qasim | 2024-11-27 | 2024-11-28 | 2025-01-21 |  |  |  |  | 7.7143 | Muzammil | 2025-01-22 | KPPI-FS-40444 | Green | 2025-01-25 | 2025-02-02 | 4 | 2025-09-13 | 0 | 0 | 0 | [17 empty] | Tons | [8 empty] | Arrived at Works | On time | 8 | 5 | 4 | 26 | 2
Arrived | QCL |  | Store |  | TMPNL0227 |  | Bohler UTP Electrodes | 3.2mm | [5 empty] | 100 | Kgs |  |  | 2026-02-20 |  | 2026-03-06 |  | W.T Fasteners | China |  |  |  |  | BAH | Advance |  | 97.5 | ¥ | 40 | 0 | 9750 | 0 | 390000 |  |  |  | 8311.1 |  | FCA |  |  |  |  | Air |  |  |  | Lahore | [14 empty] | 0 | 2025-09-13 |  | 0 | 174 | 2026-03-05 | 390000 | Unpaid |  |  |  | 2026-03-15 | 750000 | Unpaid | 40 | 390000 | 393900 | 0.6 | 0.065 |  |  | 8744 | Kgs | [8 empty] | Order Cancelled |  | 60 |  | 3 |  | 2
Arrived | QCL |  | Store |  | TMPNL0228 |  | Bohler UTP Electrodes | 3.2mm | [5 empty] | 50 | Kgs |  |  | 2026-02-20 |  | 2026-03-06 |  | W.T Fasteners | China |  |  |  |  | BAH | Advance |  | 123.5 | ¥ | 40 |  | 6175 |  | 247000 |  |  |  | 8311.1 |  | FCA |  |  |  |  | Air |  |  |  | Lahore | [14 empty] | 0 | 2025-09-13 |  | 0 | 174 | 2026-03-05 | 247000 | Unpaid |  |  |  | 2026-03-15 | 750000 | Unpaid | 40 | 247000 | 249470 | 0.6 | 0.065 |  |  | 10177 | Kgs | [8 empty] | Order Cancelled |  | 60 |  | 3 |  | 2
Shafts/Ongoing/Import Status/Import Rem | QBl-II | Ferro Alloys | Store |  | 2825-156 |  | Ferro Manganese H/C | [6 empty] | 23 | MT |  |  | 2026-04-28 |  | 2026-07-28 | 13 | JC Resources | China |  | 42034 |  | 2026-06-30 | BAH | CAD |  | 1065 | $ | 278.7 | 24495 | 24495 | 6826756.5 | 6826756.5 |  |  |  | 7202.11 | NO | CFR |  |  |  |  | Sea |  |  |  | Karachi | 2026-06-01 | 2026-06-03 | 2026-06-27 | 2026-07-05 |  |  | 2026-07-05 | 32 | EFS | [5 empty] | 0 | 2026-07-15 |  | 0 | 13 |  |  |  | 2026-06-30 | 6826756.5 | Paid | 2026-05-25 | 2034032.0992 | Unpaid | 278.7 | 6826756.5 | 6895024.065 | 0.23 | 0.065 |  |  | 330 | Kgs | [8 empty] | In Transit |  | 13 | 1 | 1 |  | 4
Shafts/Ongoing/Import Status/Import Rem | QBL-II |  | Store |  | 2819-156 |  | Copper Phosphorus | [6 empty] | 2 | MT |  |  | 2026-05-20 |  | 2026-08-20 |  | JC Resources | South Africa |  |  |  |  | BAH | CAD |  | 15170 | $ | 281 |  | 30340 |  | 8525540 |  |  |  | 7405 | NO | CFR |  |  |  |  | Sea | ESSASEL26060265 |  | Busan Port | Karachi |  | 2026-06-13 | 2026-07-13 | 2026-07-19 |  |  | 2026-07-19 | 36 | EFS | [5 empty] | 0 | 2026-07-29 |  | 0 | 22 | [6 empty] | 2026-06-10 | 600000 | Unpaid | 281 | 8525540 | 8610795.4 | 0.24 | 0.065 |  |  | 4376 | Kgs | [8 empty] | In Transit |  | 13 | 1 | 1 | 32 | 4
Shafts/Ongoing/Import Status/Import Rem | QCL | Foundry Material | Store |  | 12328-60 |  | Criterion | 80E | [5 empty] | 2000 | Kgs |  |  | 2026-04-28 |  | 2026-07-28 |  | Foseco | UAE |  | 44882 |  | 2026-06-05 | BAH | Advance |  | 1.498 | € | 323.65 | 2996 | 2996 | 969655.4 | 969655.4 |  |  |  | 3816 |  | CFR Karachi |  | MV’OOCL Spain’ |  |  | Sea |  |  |  | Karachi |  | 2026-07-10 | 2026-08-20 |  |  |  | 2026-08-20 | 41 | EFS | [5 empty] | 0 | 2026-08-30 |  | 0 | -33 | 2026-06-05 | 969655.4 | Paid |  |  |  | 2026-06-10 | 288908.8264 | Unpaid | 323.65 | 969655.4 | 979351.954 | 0.23 | 0.065 |  |  | 591 | Kgs | [8 empty] | Ready Awaiting Sailing | Vessel Booking Reeceived ETD: 10-07-2026. ETD: 20-08-26 | 31 | 1 | 1 |  | 2
Arrived | QCL | Capex | Engg. |  | 27392-60 |  | CNC Spindle Motor | ES330A,4.5kW 240000-RPM | [5 empty] | 1 | Set |  |  | 2026-05-11 |  | 2026-06-01 | 3 | Jinan BCAMCNC | China |  | 44368 |  | 2026-05-19 | BAH | Advance |  | 3890 | $ | 281 | 3890 | 3890 | 1093090 | 1093090 |  |  |  | 8466.92 |  | FOB |  |  |  |  | Air |  |  |  | Lahore |  | 2026-06-12 | 2026-06-13 |  |  |  | 2026-06-13 | 1 | EFS | [5 empty] | 0 | 2026-06-15 |  | 0 | -14 | 2026-05-20 | 1093090 | Paid |  |  |  | 2026-06-15 | 325686.1655 | Paid | 281 | 1093090 | 1104020.9 | 0.23 | 0.065 |  |  | 1286222 | Set | [8 empty] | Arrived at Works |  | 61 | 1 | 3 |  | 2
Arrived | QE | Engineering Item | Store |  | 17924-60 |  | Hardnes Tester | Time 5300 | [5 empty] | 1 | Pcs |  |  | 2026-04-02 |  | 2026-04-18 | 2.2857 | Time Group Inc | China |  | 44796 |  | 2026-06-03 | BAH | Advance |  | 690 | $ | 278.8 | 690 | 690 | 192372 | 192372 |  |  |  | 9024.1 |  | CPT |  |  |  |  | Air |  |  |  | Lahore |  | 2026-06-11 | 2026-06-13 |  |  |  | 2026-06-13 | 2 | EFS | [5 empty] | 0 | 2026-06-23 |  | 0 | -66 | 2026-06-03 | 192372 | Paid |  |  |  | 2026-06-17 | 600000 | Paid | 278.8 | 192372 | 194295.72 | 0.28 | 0.065 |  |  | 234125 | Pcs | [8 empty] | Arrived at Works |  | 23 | 1 | 3 |  | 1
Shafts/Ongoing/Import Status/Import Rem | QBl-II | Foundry Material | Store |  | 26287-60 |  | Resin | APR-103D | [5 empty] | 64.8 | MT |  |  | 2026-04-27 |  | 2026-07-27 | 13 | SQ | China |  | 42622 |  | 2026-06-30 | BAH | CAD |  | 870 | $ | 278.8 | 56376 | 56376 | 15717628.8 | 15717628.8 |  |  |  | 3824.1 | NO | CFR |  |  | TS Lines |  | Sea | 799610294304 |  | Qingdao | Karachi |  | 2026-06-03 | 2026-07-01 | 2026-07-05 |  |  | 2026-07-05 | 32 | EFS | [5 empty] | 0 | 2026-07-15 |  | 0 | 12 |  |  |  | 2026-06-30 | 15717628.8 | Paid | 2026-05-25 | 4683067.501 | Unpaid | 278.8 | 15717628.8 | 15874805.088 | 0.23 | 0.065 |  |  | 273 | Kg | [8 empty] | In Transit | Prodcution will be completed on 22-05-2026 and Vessel booking applied by Shipper, booking date awaited. 20MT for QBL & 44.8MT for QCL | 3 | 1 | 1 | 7 | 4
Shafts/Ongoing/Import Status/Import Rem | QEN | Shafts | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 1045 | 513 | 4550 | SL26-MEHS-0350 |  | Mehran | 2 | Pcs | 7.3849 | 14.7698 | 2026-06-02 |  | 2026-08-25 | 12 | Dajin | China |  | 68320 |  | 2026-06-04 | BAH | LC |  | 7100 | ¥ | 41 | 343827.39 | 104865.58 | 14096922.99 | 4299488.78 |  |  |  | 7214.109 |  | FOB |  |  |  |  | Sea |  |  |  | Karachi | 2026-07-07 | 2026-07-22 | 2026-08-19 |  |  |  | 2026-08-19 | 28 | EFS | [5 empty] | 0 | 2026-08-24 |  | 0 | 1 |  |  |  | 2026-08-01 | 4299488.78 | Unpaid | 2026-08-05 | 200000 | Unpaid | 41 | 4299488.78 | 4342483.6678 | 0.02 | 0.065 |  |  |  | Pcs | [8 empty] | Under Production | Production is about to complete. Forwarder nomination is awaited from Logistics. | 10 | 1 | 1 |  | 3
Shafts/Ongoing/Import Status/Import Rem | QEN | Shafts | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 1045 | 336 | 3525 | SL26-MEHS-0352 |  | Mehran | 1 | Pcs | 2.4543 | 2.4543 | 2026-06-02 |  | 2026-08-25 | 12 | Dajin | China |  | 68320 |  | 2026-06-04 | BAH | LC |  | 7100 | ¥ | 41 |  | 17425.53 |  | 714446.73 |  |  |  | 7214.109 |  | FOB |  |  |  |  | Sea |  |  |  | Karachi | 2026-07-07 | 2026-07-22 | 2026-08-19 |  |  |  | 2026-08-19 | 28 | EFS | [5 empty] | 0 | 2026-08-24 |  | 0 | 1 |  |  |  | 2026-08-01 | 714446.73 | Unpaid | 2026-08-05 | 200000 | Unpaid | 41 | 714446.73 | 721591.1973 | 0.02 | 0.065 |  |  |  | Pcs | [8 empty] | Under Production | Production is about to complete. Forwarder nomination is awaited from Logistics. | 10 | 1 | 1 |  | 3
Shafts/Ongoing/Import Status/Import Rem | QEN | Shafts | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 1045 | 526 | 4380 | SL26-MEHS-0351 |  | Mehran | 1 | Pcs | 7.4738 | 7.4738 | 2026-06-02 |  | 2026-08-25 | 12 | Dajin | China |  | 68320 |  | 2026-06-04 | BAH | LC |  | 7100 | ¥ | 41 |  | 53063.98 |  | 2175623.18 |  |  |  | 7214.109 |  | FOB |  |  |  |  | Sea |  |  |  | Karachi | 2026-07-07 | 2026-07-22 | 2026-08-19 |  |  |  | 2026-08-19 | 28 | EFS | [5 empty] | 0 | 2026-08-24 |  | 0 | 1 |  |  |  | 2026-08-01 | 2175623.18 | Unpaid | 2026-08-05 | 200000 | Unpaid | 41 | 2175623.18 | 2197379.4118 | 0.02 | 0.065 |  |  |  | Pcs | [8 empty] | Under Production | Production is about to complete. Forwarder nomination is awaited from Logistics. | 10 | 1 | 1 |  | 3
Shafts/Ongoing/Import Status/Import Rem | QEN | Shafts | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 1045 | 303 | 3470 | SL26-JKS1-0296 |  | JK-1 | 3 | Pcs | 1.9648 | 5.894 | 2026-06-03 |  | 2026-08-26 | 12 | Dajin | China |  | 68320 |  | 2026-06-04 | BAH | LC |  | 7100 | ¥ | 41 |  | 41847.4 |  | 1715743.4 |  |  |  | 7214.109 |  | FOB |  |  |  |  | Sea |  |  |  | Karachi | 2026-07-08 | 2026-07-23 | 2026-08-20 |  |  |  | 2026-08-20 | 28 | EFS | [5 empty] | 0 | 2026-08-25 |  | 0 | 1 |  |  |  | 2026-08-01 | 1715743.4 | Unpaid | 2026-08-05 | 200000 | Unpaid | 41 | 1715743.4 | 1732900.834 | 0.02 | 0.065 |  |  |  | Pcs | [8 empty] | Under Production | Production is about to complete. Forwarder nomination is awaited from Logistics. | 10 | 1 | 1 |  | 3
Shafts/Ongoing/Import Status/Import Rem | QEN | Shafts | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 4140 | 498 | 4520 | SE26-ADKG-0001 |  | PT.ADIKARYA | 1 | Pcs | 6.916 | 6.916 | 2026-06-08 |  | 2026-08-31 | 12 | Dajin | China |  | 68320 |  | 2026-06-04 | BAH | LC |  | 8200 | ¥ | 41 |  | 56711.2 |  | 2325159.2 |  |  |  | 7228.4 |  | FOB |  |  |  |  | Sea |  |  |  | Karachi | 2026-07-13 | 2026-07-23 | 2026-08-20 |  |  |  | 2026-08-20 | 28 | EFS | [5 empty] | 0 | 2026-08-25 |  | 0 | 6 |  |  |  | 2026-08-01 | 2325159.2 | Unpaid | 2026-08-05 | 200000 | Unpaid | 41 | 2325159.2 | 2348410.792 | 0.02 | 0.065 |  |  |  | Pcs | [8 empty] | Under Production | Production is about to complete. Forwarder nomination is awaited from Logistics. | 10 | 1 | 1 |  | 3
Shafts/Ongoing/Import Status/Import Rem | QEN | Shafts | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 1045 | 463 | 3740 | SE26-SCHD-0001 |  | TCCHAD-SOMDIAA | 1 | Pcs | 4.967 | 4.967 | 2026-06-08 |  | 2026-08-31 | 12 | Dajin | China |  | 68320 |  | 2026-06-04 | BAH | LC |  | 7100 | ¥ | 41 |  | 35265.7 |  | 1445893.7 |  |  |  | 7214.109 |  | FOB |  |  |  |  | Sea |  |  |  | Karachi | 2026-07-13 | 2026-07-23 | 2026-08-20 |  |  |  | 2026-08-20 | 28 | EFS | [5 empty] | 0 | 2026-08-25 |  | 0 | 6 |  |  |  | 2026-08-01 | 1445893.7 | Unpaid | 2026-08-05 | 200000 | Unpaid | 41 | 1445893.7 | 1460352.637 | 0.02 | 0.065 |  |  |  | Pcs | [8 empty] | Under Production | Production is about to complete. Forwarder nomination is awaited from Logistics. | 10 | 1 | 1 |  | 3
Shafts/Ongoing/Import Status/Import Rem | QEN | Shafts | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 1045 | 463 | 3690 | SE26-SCHD-0002 |  | TCCHAD-SOMDIAA | 1 | Pcs | 4.88 | 4.88 | 2026-06-08 |  | 2026-08-31 | 12 | Dajin | China |  | 68320 |  | 2026-06-04 | BAH | LC |  | 7100 | ¥ | 41 |  | 34648 |  | 1420568 |  |  |  | 7214.109 |  | FOB |  |  |  |  | Sea |  |  |  | Karachi | 2026-07-13 | 2026-07-23 | 2026-08-20 |  |  |  | 2026-08-20 | 28 | EFS | [5 empty] | 0 | 2026-08-25 |  | 0 | 6 |  |  |  | 2026-08-01 | 1420568 | Unpaid | 2026-08-05 | 200000 | Unpaid | 41 | 1420568 | 1434773.68 | 0.02 | 0.065 |  |  |  | Pcs | [8 empty] | Under Production | Production is about to complete. Forwarder nomination is awaited from Logistics. | 10 | 1 | 1 |  | 3
Shafts/Ongoing/Import Status/Import Rem | QEN | Shafts | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 1045 | 538 | 4680 | SL26-THAS-0085 |  | Tharparkar | 1 | Pcs | 8.358 | 8.358 | 2026-06-10 |  | 2026-09-02 | 12 | Qilu | China |  | 69578 |  | 2026-06-24 | BAH | LC |  | 7150 | ¥ | 41 | 373619.23 | 59759.7 | 15318388.43 | 2450147.7 |  |  |  | 7214.109 |  | FOB |  |  |  |  | Sea |  |  |  | Karachi | 2026-07-15 | 2026-07-29 | 2026-08-20 |  |  |  | 2026-08-20 | 22 | EFS | [5 empty] | 0 | 2026-08-30 |  | 0 | 3 |  |  |  | 2026-07-30 | 2450147.7 | Unpaid | 2026-08-05 | 200000 | Unpaid | 41 | 2450147.7 | 2474649.177 | 0.02 | 0.065 |  |  |  | Pcs | [8 empty] | Under Production |  | 5 | 1 | 1 |  | 3
Shafts/Ongoing/Import Status/Import Rem | QEN | Shafts | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | EN14B | 482 | 4323 | SE26-SMHE-0085 |  | Sonkor-MHLUME | 2 | Pcs | 6.197 | 12.394 | 2026-06-09 |  | 2026-09-01 | 12 | Qilu | China |  | 69578 |  | 2026-06-24 | BAH | LC |  | 8300 | ¥ | 41 |  | 102870.2 |  | 4217678.2 |  |  |  | 7214.109 |  | FOB |  |  |  |  | Sea |  |  |  | Karachi | 2026-07-14 | 2026-07-29 | 2026-08-20 |  |  |  | 2026-08-20 | 22 | EFS | [5 empty] | 0 | 2026-08-30 |  | 0 | 2 |  |  |  | 2026-07-30 | 4217678.2 | Unpaid | 2026-08-05 | 200000 | Unpaid | 41 | 4217678.2 | 4259854.982 | 0.02 | 0.065 |  |  |  | Pcs | [8 empty] | Under Production |  | 5 | 1 | 1 |  | 3
Shafts/Ongoing/Import Status/Import Rem | QEN | Shafts | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | EN14B | 482 | 4323 | SE26-SMHE-0084 |  | Sonkor-MHLUME | 1 | Pcs | 6.197 | 6.197 | 2026-06-09 |  | 2026-09-01 | 12 | Qilu | China |  | 69578 |  | 2026-06-24 | BAH | LC |  | 8300 | ¥ | 41 |  | 51435.1 |  | 2108839.1 |  |  |  | 7214.109 |  | FOB |  |  |  |  | Sea |  |  |  | Karachi | 2026-07-14 | 2026-07-29 | 2026-08-20 |  |  |  | 2026-08-20 | 22 | EFS | [5 empty] | 0 | 2026-08-30 |  | 0 | 2 |  |  |  | 2026-07-30 | 2108839.1 | Unpaid | 2026-08-05 | 200000 | Unpaid | 41 | 2108839.1 | 2129927.491 | 0.02 | 0.065 |  |  |  | Pcs | [8 empty] | Under Production |  | 5 | 1 | 1 |  | 3
Shafts/Ongoing/Import Status/Import Rem | QEN | Shafts | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 4140 Stepped QT | 283*386*283 | 735*460*895 | SL26-ASML-0047 |  | Ansari | 1 | Pcs | 1.239 | 1.239 | 2026-06-10 |  | 2026-09-02 | 12 | Qilu | China |  | 69578 |  | 2026-06-24 | BAH | LC |  | 11000 | ¥ | 41 |  | 13629 |  | 558789 |  |  |  | 7228.4 |  | FOB |  |  |  |  | Sea |  |  |  | Karachi | 2026-07-15 | 2026-07-29 | 2026-08-20 |  |  |  | 2026-08-20 | 22 | EFS | [5 empty] | 0 | 2026-08-30 |  | 0 | 3 |  |  |  | 2026-07-30 | 558789 | Unpaid | 2026-08-05 | 200000 | Unpaid | 41 | 558789 | 564376.89 | 0.02 | 0.065 |  |  |  | Pcs | [8 empty] | Under Production |  | 5 | 1 | 1 |  | 3
Shafts/Ongoing/Import Status/Import Rem | QEN | Shafts | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 1045 | 558 | 4870 | SL26-SAKS-0111 |  | Sakrand | 1 | Pcs | 9.364 | 9.364 | 2026-06-16 |  | 2026-09-08 | 12 | Qilu | China |  | 69578 |  | 2026-06-24 | BAH | LC |  | 7150 | ¥ | 41 |  | 66952.6 |  | 2745056.6 |  |  |  | 7228.4 |  | FOB |  |  |  |  | Sea |  |  |  | Karachi | 2026-07-21 | 2026-07-29 | 2026-08-20 |  |  |  | 2026-08-20 | 22 | EFS | [5 empty] | 0 | 2026-08-30 |  | 0 | 9 |  |  |  | 2026-07-30 | 2745056.6 | Unpaid | 2026-08-05 | 200000 | Unpaid | 41 | 2745056.6 | 2772507.166 | 0.02 | 0.065 |  |  |  | Pcs | [8 empty] | Under Production |  | 5 | 1 | 1 |  | 3
Shafts/Ongoing/Import Status/Import Rem | QEN | Shafts | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 4140 | 583 | 2467 | SL26-TAMS-0029 |  | Tando Allayar | 1 | Pcs | 5.1778 | 5.1778 | 2026-06-12 |  | 2026-09-04 | 12 | Qilu | China |  | 69578 |  | 2026-06-24 | BAH | LC |  | 8350 | ¥ | 41 |  | 43234.63 |  | 1772619.83 |  |  |  | 7228.4 |  | FOB |  |  |  |  | Sea |  |  |  | Karachi | 2026-07-17 | 2026-07-29 | 2026-08-20 |  |  |  | 2026-08-20 | 22 | EFS | [5 empty] | 0 | 2026-08-30 |  | 0 | 5 |  |  |  | 2026-07-30 | 1772619.83 | Unpaid | 2026-08-05 | 200000 | Unpaid | 41 |  | 0 | [5 empty] | Pcs | [8 empty] | Under Production |  | 5 | 1 | 1 |  | 3
Shafts/Ongoing/Import Status/Import Rem | QEN | Shafts | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 4140 | 553 | 2270 | SL26-SAKS-0112 |  | Sakrand | 1 | Pcs | 4.28 | 4.28 | 2026-06-19 |  | 2026-09-11 | 12 | Qilu | China |  | 69578 |  | 2026-06-24 | BAH | LC |  | 8350 | ¥ | 41 |  | 35738 |  | 1465258 |  |  |  | 7228.4 |  | FOB |  |  |  |  | Sea |  |  |  | Karachi | 2026-07-24 | 2026-07-29 | 2026-08-20 |  |  |  | 2026-08-20 | 22 | EFS | [5 empty] | 0 | 2026-08-30 |  | 0 | 12 |  |  |  | 2026-07-30 | 1465258 | Unpaid | 2026-08-05 | 200000 | Unpaid | 41 | 1465258 | 1479910.58 | 0.02 | 0.065 |  |  |  | Pcs | [8 empty] | Under Production |  | 5 | 1 | 1 |  | 3
Shafts/Ongoing/Import Status/Import Rem | QEN | Shafts | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 1045 | 513 | 4490 | SE26-GFUL-0145,0146,0147 |  | GREEN FUEL | 18 | Pcs | 7.287 | 131.166 | 2026-06-17 |  | 2026-09-09 | 12 | Dajin | China |  | 69677 |  | 2026-06-24 | BAH | LC |  | 6712.3 | ¥ | 41 | 880425.5418 | 880425.5418 | 36097447.2138 | 36097447.2138 |  |  |  | 7214.109 |  | FOB |  |  |  |  | Sea |  |  |  | Karachi | 2026-07-22 | 2026-08-01 | 2026-08-23 |  |  |  | 2026-08-23 | 22 | EFS | [5 empty] | 0 | 2026-09-02 |  | 0 | 7 |  |  |  | 2026-07-30 | 36097447.2138 | Unpaid | 2026-08-05 | 200000 | Unpaid | 41 | 36097447.2138 | 36458421.6859 | 0.02 | 0.065 |  |  |  | Pcs | [8 empty] | Under Production |  | 10 | 1 | 1 |  | 3
Shafts/Ongoing/Import Status/Import Rem | QEN | Shafts | Engg. |  | TMPNL0012 |  | Forged Steel Round Bar | 1045 | 558 | 4930 | SL26-ASHS-0176 |  | Ashraf Sugar | 3 | Pcs | 9.467 | 28.401 | 2026-06-30 |  | 2026-09-22 | 12 | Qilu | China |  |  |  |  | BAH | LC |  | 7150 | ¥ | 41 | 0 | 203067.15 | 0 | 8325753.15 |  |  |  | 7214.109 |  | FOB |  |  |  |  | Sea |  |  |  | Karachi | 2026-08-04 | 2026-08-14 | 2026-09-05 |  |  |  | 2026-09-05 | 22 | EFS | [5 empty] | 0 | 2026-09-15 |  | 0 | 7 |  |  |  | 2026-08-10 | 8325753.15 | Unpaid | 2026-07-10 | 200000 | Unpaid | 41 | 8325753.15 | 8409010.6815 | 0.02 | 0.065 |  |  |  | Pcs | [8 empty] | LC in Process |  | 5 | 1 | 1 |  | 3
Shafts/Ongoing/Import Status/Import Rem | QBL-II | Scrap | Store |  | TMPNL0245 |  | Manganese Steel Scrap | [6 empty] | 18.806 | Ton | [6 empty] | KE Metal | USA |  | 2739 | B1 | 2026-06-19 | HMB | LC |  | 527.39 | $ | 281 | 9918.0963 | 9918.0963 | 2786985.0715 | 2786985.0715 |  |  |  | 7204.29 | NO | CFR |  |  |  |  | Sea |  |  |  | Karachi |  | 2026-05-24 | 2026-07-12 | 2026-07-19 |  |  | 2026-07-19 | 56 | MHQ | [5 empty] | 0 | 2026-07-24 | 0 | 0 | 0 | [6 empty] | 2026-06-10 | 600000 | Unpaid | 281 | 2786985.0715 | 2814854.9223 | 0.28 | 0.065 |  |  | 177 | Kgs | [8 empty] | In Transit |  | 8 | 3 | 1 |  | 4
Shafts/Ongoing/Import Status/Import Rem | QBL-II | Scrap | Store |  | TMPNL0246 |  | Manganese Steel Scrap | [6 empty] | 105.23 | Ton | [6 empty] | KE Metal | USA |  | 2739 | B2 | 2026-06-19 | HMB | LC |  | 527.39 | $ | 281 | 55497.2497 | 55497.2497 | 15594727.1657 | 15594727.1657 |  |  |  | 7204.29 | NO | CFR |  |  |  |  | Sea |  |  |  | Karachi |  | 2026-05-28 | 2026-08-07 |  |  |  | 2026-08-07 | 71 | MHQ | [5 empty] | 0 | 2026-08-17 | 0 | 0 | 0 | [6 empty] | 2026-06-10 | 600000 | Unpaid | 281 | 15594727.1657 | 15750674.4374 | 0.28 | 0.065 |  |  | 177 | Kgs | [8 empty] | In Transit |  | 8 | 3 | 1 |  | 4
Shafts/Ongoing/Import Status/Import Rem | QBL-II | Scrap | Store |  | TMPNL0247 |  | SS 409 Scrap | [6 empty] | 20.681 | Ton | [6 empty] | KE Metal | USA |  | 68955 | B1 | 2026-06-17 | BAH | LC |  | 550 | $ | 281 | 11374.55 | 11374.55 | 3196248.55 | 3196248.55 |  |  |  | 7204.21 | NO | CFR |  |  |  |  | Sea |  |  |  | Karachi |  | 2026-06-11 | 2026-08-03 |  |  |  | 2026-08-03 | 53 | MHQ | [5 empty] | 0 | 2026-08-13 | 0 | 0 | 0 | [6 empty] | 2026-06-10 | 600000 | Unpaid | 281 | 3196248.55 | 3228211.0355 | 0.28 | 0.065 |  |  | 177 | Kgs | [8 empty] | In Transit |  | 8 | 3 | 1 |  | 4
Shafts/Ongoing/Import Status/Import Rem | QBL-II | Scrap | Store |  | TMPNL0248 |  | SS 409 Scrap | [6 empty] | 39.011 | Ton | [6 empty] | KE Metal | USA |  | 68955 | B2 | 2026-06-17 | BAH | LC |  | 550 | $ | 281 | 21456.05 | 21456.05 | 6029150.05 | 6029150.05 |  |  |  | 7204.21 | NO | CFR |  |  |  |  | Sea |  |  |  | Karachi |  | 2026-06-26 | 2026-08-10 |  |  |  | 2026-08-10 | 45 | MHQ | [5 empty] | 0 | 2026-08-20 | 0 | 0 | 0 | [6 empty] | 2026-06-10 | 600000 | Unpaid | 281 | 6029150.05 | 6089441.5505 | 0.28 | 0.065 |  |  | 177 | Kgs | [8 empty] | In Transit |  | 8 | 3 | 1 |  | 4
Shafts/Ongoing/Import Status/Import Rem | QCL | Scrap | Store |  | 19969-60 |  | Cast Iron Scrap | [6 empty] | 500 | Ton | [6 empty] | Prime Commodities Fze | UAE |  | 68000 |  | 2026-06-10 | BAH | LC |  | 440 | $ | 281 | 220000 | 220000 | 61820000 | 61820000 |  |  |  | 7204.109 |  | CFR |  |  |  |  | Sea |  |  |  | Karachi |  | 2026-06-02 | 2026-08-28 |  |  |  | 2026-08-28 | 87 | MHQ | [5 empty] | 0 | 2026-09-07 | 0 | 0 | 0 | [6 empty] | 2026-06-10 | 600000 | Unpaid | 281 | 61820000 | 62438200 | 0.28 | 0.065 |  |  | 152 | Kgs | [8 empty] | In Transit |  | 7 | 3 | 1 |  | 2
Shafts/Ongoing/Import Status/Import Rem | QBl-II | Foundry Material | Store |  | 26382-60 |  | Hardner | HQG60 / AKS-1075 | [5 empty] | 5 | MT |  |  | 2026-04-28 |  | 2026-07-28 | 13 | SQ | China |  | 41932 |  |  | BAH | CAD |  | 1990 | $ | 281 | 37120 | 9950 | 10430720 | 2795950 |  |  |  | 3824.1 | YES | CFR |  |  | TS Lines |  | Sea | 799610302269 |  | Qingdao | Karachi |  | 2026-06-03 | 2026-07-01 | 2026-07-05 |  |  | 2026-07-05 | 32 | EFS | [5 empty] | 0 | 2026-07-15 |  | 0 | 13 |  |  |  | 2026-06-10 | 2795950 | Unpaid | 2026-05-25 | 833053.3025 | Unpaid | 281 | 2795950 | 2823909.5 | 0.23 | 0.065 |  |  | 597 | Kg | [8 empty] | In Transit | Prodcution will be completed on 22-05-2026 and Vessel booking applied by Shipper, booking date awaited.. | 3 | 1 | 1 | 7 | 4
Shafts/Ongoing/Import Status/Import Rem | QCL | Foundry Material | Store |  | 26838-60 |  | Hardner | HQG20 / AS-09 | [5 empty] | 13 | MT |  |  | 2026-04-27 |  | 2026-07-27 | 13 | SQ | China |  | 41932 |  |  | BAH | CAD |  | 2090 | $ | 281 |  | 27170 |  | 7634770 |  |  |  | 3824.1 | YES | CFR |  |  | TS Lines |  | Sea | 799610302269 |  | Qingdao | Karachi |  | 2026-06-03 | 2026-07-01 | 2026-07-05 |  |  | 2026-07-05 | 32 | EFS | [5 empty] | 0 | 2026-07-15 |  | 0 | 12 |  |  |  | 2026-06-10 | 7634770 | Unpaid | 2026-05-25 | 2274779.7215 | Unpaid | 281 | 7634770 | 7711117.7 | 0.23 | 0.065 |  |  | 625 | Kg | [8 empty] | In Transit | Prodcution will be completed on 22-05-2026 and Vessel booking applied by Shipper, booking date awaited.. | 3 | 1 | 1 | 7 | 2
Arrived | QE | Engineering Item | Engg. |  | 2724-60 |  | Go-No Go Gauge | R-3259 | [5 empty] | 1 | Pcs |  |  | 2026-04-15 |  | 2026-04-30 | 2.1429 | NCS | China | [7 empty] | 7350 | ¥ | 41 | 0 | 7350 | 0 | 301350 |  |  |  | 3822.9 |  | EX-WORK |  |  |  |  | Air |  |  |  | Lahore | [14 empty] | 0 |  |  | 0 | 0 | 2026-05-05 | 301350 | Paid |  |  |  | 2026-06-30 | 95874.5025 | Paid | 41 | 301350 | 304363.5 | 0.25 | 0.065 |  |  | 439897 | Pcs | [8 empty] | Arrived at Works |  | 62 |  | 3 |  | 1
Arrived | QE | Engineering Item | Engg. |  | TMPNL0249 |  | Hardfacing Wire | TWD743-O | [5 empty] | 15 | Kg | [5 empty] | 0 | Qingdao Tendileweld | China |  | 44795 |  | 2026-06-04 | BAH | Advance |  | 11.19 | $ | 278.7 | 167.85 | 167.85 | 46779.795 | 46779.795 |  |  |  | 8311.2 |  | EX-WORK |  |  |  |  | Air |  |  |  | Lahore |  | 2026-06-12 | 2026-06-13 |  |  |  | 2026-06-13 | 1 | EFS | [5 empty] | 0 | 2026-06-15 |  | 0 | 0 | 2026-06-03 | 46779.795 | Paid |  |  |  | 2026-06-15 | 33782.029 | Paid | 278.7 | 46779.795 | 47247.5929 | 0.65 | 0.065 |  |  | 17819 | Kg | [8 empty] | Arrived at Works |  | 63 | 1 | 3 |  | 1
Shafts/Ongoing/Import Status/Import Rem | QE | Temporray Import | Refurb. |  | TMPNL0250 |  | Old Roll | [6 empty] | 1 | Pc | [5 empty] | 0 | CASA | Phillpines |  | 2410 | B2 |  | HMB | [5 empty] | 0 | 0 | 0 | 0 |  |  |  |  | NO | CFR Karachi |  |  |  |  | Sea | CEB002604 |  |  | Karachi |  | 2026-05-27 | 2026-06-16 | 2026-06-19 |  |  | 2026-06-19 | 23 | EFS | [5 empty] | 0 | 2026-07-08 |  | 0 | 0 | [6 empty] | 2026-06-19 | 200000 | Paid | 0 | 0 | 0 | 0.23 | 0.065 |  |  |  | Pc | [8 empty] | Arrived at QFL |  | 56 | 1 | 1 |  | 1
Arrived | QCL | Refractory Material | Store |  | 18988-60 |  | Exothermic Pads | Izoprelevha P(550*300*22) | [5 empty] | 1250 | Pcs |  |  | 2026-03-10 |  | 2026-06-10 | 13.1429 | Cukurova | Turkey |  | 62845 |  | 2026-03-31 | BAH | LC |  | 4.6025 | € | 320.48 | 17049.6 | 5753.0737 | 5464055.808 | 1843745.0578 |  |  |  | 6903.901 |  | CFR Karachi |  | SEASPAN BRILLIANCE 101E | One Line | One Line Pakistan | Sea | ONEYISTG06274300 |  | Aliaga | Karachi |  | 2026-05-02 | 2026-06-05 | 2026-06-14 | 2026-06-20 |  | 2026-06-20 | 49 | EFS | [5 empty] | 0 | 2026-06-29 |  | 0 | -19 |  |  |  | 2026-05-25 | 1843745.0578 | Paid | 2026-06-22 | 586587.4901 | Paid | 320.48 | 1843745.0578 | 1862182.5084 | 0.25 | 0.065 |  |  | 1356 | Pcs | [8 empty] | Arrived at Works | Vessel Booking received. ETD: 22-04-26, Vessel rollover ETD:02-05-2026. ( For QCL) | 11 | 1 | 1 | 9 | 2
Shafts/Ongoing/Import Status/Import Rem | QBL-II | Foundry Material | Store |  | 26287-60 |  | Resin | A-85 | [5 empty] | 24000 | Kgs |  |  | 2026-02-25 |  | 2026-05-25 | 12.7143 | Cukurova | Turkey |  | 63909 |  | 2026-04-14 | BAH | LC |  | 0.645 | € | 322 | 15480 | 15480 | 4984560 | 4984560 |  |  |  | 3824.1 |  | CFR Karachi |  | NAVIOS AZURE | CMA CGM | CMA CGM | Sea | ISB1976103 |  | Aliaga | Karachi |  | 2026-05-09 | 2026-07-15 | 2026-07-27 | 2026-07-29 |  | 2026-07-29 | 81 | EFS | [5 empty] | 0 | 2026-08-08 |  | 0 | -75 |  |  |  | 2026-05-30 | 4984560 | Unpaid | 2026-04-30 | 1485149.652 | Unpaid | 322 | 4984560 | 5034405.6 | 0.23 | 0.065 |  |  | 235 | Kgs | [8 empty] | In Transit | Shipment booking has been received with ETD 09-05-26. However, the shipment has been unexpectedly delayed due to the current Red Sea issue, which has increased the transit time from 45 days to approximately 70 days. Additionally, the booking was received by the supplier from the shipping line after a delay of 18 days. | 11 | 1 | 1 | 9 | 4
Shafts/Ongoing/Import Status/Import Rem | QCL | Foundry Material | Store |  | 26487-60 |  | Zircon Coating | CK-780/RISA-5100 | [5 empty] | 5400 | Kg |  |  | 2026-04-27 |  | 2026-07-27 |  | Cukurova | Turkey |  | 68756 |  | 2026-06-09 | BAH | LC |  | 2.005 | € | 325 |  | 10827 |  | 3518775 |  |  |  | 3824.1 |  | CFR Karachi |  |  | Akkon |  | Sea | AKKNEM26035883 |  | Aliaga | Karachi |  | 2026-07-02 | 2026-07-30 |  |  |  | 2026-07-30 | 28 | EFS | [5 empty] | 0 | 2026-08-09 |  | 0 | -13 |  |  |  | 2026-07-15 | 3518775 | Unpaid | 2026-07-30 | 200000 | Unpaid | 325 | 3518775 | 3553962.75 | 0.23 | 0.065 |  |  |  | Kg | [8 empty] | Ready Awaiting Sailing | Vessel Booking Received ETD: 26-06-26, New ETD: 02-07-26 ETA: 30-07-26 | 11 | 1 | 1 | 9 | 2
Shafts/Ongoing/Import Status/Import Rem | QCL | Foundry Material | Store |  | 19677-60 |  | Release Agent | HS-10 | [5 empty] | 360 | Kg |  |  | 2026-05-12 |  | 2026-08-12 |  | Cukurova | Turkey |  | 68756 |  | 2026-06-09 | BAH | LC |  | 13.82 | € | 325 |  | 4975.2 |  | 1616940 |  |  |  | 3824.1 |  | CFR Karachi |  |  | Akkon |  | Sea | AKKNEM26035883 |  | Aliaga | Karachi |  | 2026-07-02 | 2026-07-30 |  |  |  | 2026-07-30 | 28 | EFS | [5 empty] | 0 | 2026-08-09 |  | 0 | 3 |  |  |  | 2026-07-15 | 1616940 | Unpaid | 2026-07-30 | 200000 | Unpaid | 325 | 1616940 | 1633109.4 | 0.23 | 0.065 |  |  |  | Kg | [8 empty] | Ready Awaiting Sailing | For QCL 260 Kg & For QBL-II 100 Kg.//Vessel Booking Received ETD: 26-06-26, New ETD: 02-07-26 ETA: 30-07-26 | 11 | 1 | 1 | 9 | 2
Shafts/Ongoing/Import Status/Import Rem | QCL | Foundry Material | Store |  | 26486-60 |  | Intensifier | Reflak-212A/RISA-5107 | [5 empty] | 5400 | Kg |  |  | 2026-04-27 |  | 2026-07-27 |  | Cukurova | Turkey |  | 68756 |  | 2026-06-09 | BAH | LC |  | 0.93 | € | 325 |  | 5022 |  | 1632150 |  |  |  | 3824.1 |  | CFR Karachi |  |  | Akkon |  | Sea | AKKNEM26035883 |  | Aliaga | Karachi |  | 2026-07-02 | 2026-07-30 |  |  |  | 2026-07-30 | 28 | EFS | [5 empty] | 0 | 2026-08-09 |  | 0 | -13 |  |  |  | 2026-07-15 | 1632150 | Unpaid | 2026-07-30 | 200000 | Unpaid | 325 | 1632150 | 1648471.5 | 0.23 | 0.065 |  |  |  | Kg | [8 empty] | Ready Awaiting Sailing | Vessel Booking Received ETD: 26-06-26, New ETD: 02-07-26 ETA: 30-07-26 | 11 | 1 | 1 | 9 | 2
Shafts/Ongoing/Import Status/Import Rem | QBL-II | Refactory | Store |  | 26558-60 |  | Exothermic Riser Sleeves | OBG-9/300 | [5 empty] | 117 | Pcs |  |  | 2026-04-28 |  | 2026-07-28 | 13 | Cukurova | Turkey |  | 68756 |  | 2026-06-09 | BAH | LC |  | 10.6 | € | 325 |  | 1240.2 |  | 403065 |  |  |  | 6903.901 |  | CFR Karachi |  |  | Akkon |  | Sea | AKKNEM26035883 |  | Aliaga | Karachi |  | 2026-07-02 | 2026-07-30 |  |  |  | 2026-07-30 | 28 | EFS | [5 empty] | 0 | 2026-08-09 |  | 0 | -12 |  |  |  | 2026-07-15 | 403065 | Unpaid | 2026-07-30 | 200000 | Unpaid | 325 | 403065 | 407095.65 | 0.23 | 0.065 |  |  |  | Pcs | [8 empty] | Ready Awaiting Sailing | Vessel Booking Received ETD: 26-06-26, New ETD: 02-07-26 ETA: 30-07-26 | 11 | 1 | 1 | 9 | 4
Shafts/Ongoing/Import Status/Import Rem | QBL-II | Refactory | Store |  | 15598-60 |  | Exothermic Riser Sleeves | BGK-6 | [5 empty] | 368 | Pcs |  |  | 2026-05-12 |  | 2026-08-12 | 13.1429 | Cukurova | Turkey |  | 68756 |  | 2026-06-09 | BAH | LC |  | 4.86 | € | 325 |  | 1788.48 |  | 581256 |  |  |  | 6903.901 |  | CFR Karachi |  |  | Akkon |  | Sea | AKKNEM26035883 |  | Aliaga | Karachi |  | 2026-07-02 | 2026-07-30 |  |  |  | 2026-07-30 | 28 | EFS | [5 empty] | 0 | 2026-08-09 |  | 0 | 3 |  |  |  | 2026-07-15 | 581256 | Unpaid | 2026-07-30 | 200000 | Unpaid | 325 | 581256 | 587068.56 | 0.23 | 0.065 |  |  |  | Pcs | [8 empty] | Ready Awaiting Sailing | Vessel Booking Received ETD: 26-06-26, New ETD: 02-07-26 ETA: 30-07-26 | 11 | 1 | 1 | 9 | 4
Shafts/Ongoing/Import Status/Import Rem | QEN | Engineering Item | Engg. |  | 25014-60 |  | Tip Mechanical | APMT16408PDER/YBG205 | [5 empty] | 2500 | Pcs |  |  | 2026-05-22 |  | 2026-07-10 | 7 | ZCCCT | China |  | 4057 |  | 2026-06-22 | HMB | Advance |  | 2.458 | $ | 278.6 |  | 6145 |  | 1711997 |  |  |  | 8207.8 |  | FCA |  |  |  |  | Air |  |  |  | Lahore | [14 empty] | 0 |  |  | 0 | 0 | 2026-06-22 | 1711997 | Paid |  |  |  | 2026-07-30 | 200000 | Unpaid | 278.6 | 1711997 | 1729116.97 | 0.29 | 0.065 |  |  | 780 | Pcs | [8 empty] | Under Production |  | 64 |  | 3 |  | 3
Shafts/Ongoing/Import Status/Import Rem | QCL | Refactory | Store |  | 24927-60 |  | Ceramic Foam Filter | Dia125x22/10 PPI | [5 empty] | 504 | Pcs |  |  | 2026-05-20 |  | 2026-08-20 | 13.1429 | Shanxi Fuqian | China |  | 4065 |  | 2026-06-22 | BAH | Advance |  | 6.02 | $ | 278.6 | 3034.08 | 3034.08 | 845294.688 | 845294.688 |  |  |  | 6903.901 |  | CPT |  |  |  |  | Air |  |  |  | Lahore | [14 empty] | 0 |  |  | 0 | 0 | 2026-06-22 | 845294.688 | Paid |  |  |  | 2026-07-30 | 200000 | Unpaid | 278.6 | 845294.688 | 853747.6349 | 0.25 | 0.065 |  |  | 2399 | Pcs | [8 empty] | Under Production |  | 26 |  | 3 |  | 2
Shafts/Ongoing/Import Status/Import Rem | QCL | Refactory | Store |  | 13940-60 |  | Stelex Pro filter | D125x30/10 | [5 empty] | 1000 | Pcs |  |  | 2026-05-12 |  | 2026-08-12 | 13.1429 | E-Born | China |  | 4063 |  | 2026-06-22 | HMB | Advance |  | 6.94 | $ | 278.6 | 6940 | 6940 | 1933484 | 1933484 |  |  |  | 6903.901 |  | CPT |  |  |  |  | Air |  |  |  | Lahore | [14 empty] | 0 |  |  | 0 | 0 | 2026-06-22 | 1933484 | Paid |  |  |  | 2026-07-30 | 200000 | Unpaid | 278.6 | 1933484 | 1952818.84 | 0.25 | 0.065 |  |  | 2054 | Pcs | [8 empty] | Under Production |  | 35 |  | 3 |  | 2
Shafts/Ongoing/Import Status/Import Rem | QEN |  | Samples |  | TMPNL0251 |  | Welding Wire | ER312 SS SAW | [5 empty] | 50 | Kg | [5 empty] | 0 | Dayang | China |  |  |  |  | BAH | Advance |  | 7.41 | $ | 280 | 0 | 370.5 | 0 | 103740 |  |  |  | 7223 |  | FCA |  |  |  |  | Air |  |  |  | Lahore | [14 empty] | 0 |  |  | 0 | 0 | 2026-06-15 | 103740 | Unpaid |  |  |  | 2026-07-30 | 200000 | Unpaid | 280 | 103740 | 104777.4 | 0.29 | 0.065 |  |  | 5536 | Kg | [8 empty] | T/T in Process |  | 65 |  | 3 |  | 3
Shafts/Ongoing/Import Status/Import Rem | QEN |  | Samples |  | TMPNL0252 |  | Welding Flux | SJ601 | [5 empty] | 15 | Kg | [5 empty] | 0 | Dayang | China |  |  |  |  | BAH | Advance |  | 1.26 | $ | 280 |  | 18.9 |  | 5292 |  |  |  | 7223 |  | FCA |  |  |  |  | Air |  |  |  | Lahore | [14 empty] | 0 |  |  | 0 | 0 | 2026-06-15 | 5292 | Unpaid |  |  |  | 2026-07-30 | 200000 | Unpaid | 280 | 5292 | 5344.92 | 0.29 | 0.065 |  |  | 6767 | Kg | [8 empty] | T/T in Process |  | 65 |  | 3 |  | 3
Shafts/Ongoing/Import Status/Import Rem | QEN |  | Samples |  | TMPNL0253 |  | Welding Electrodes-DIN8555 E10-UM-60-Z | 3.2mm | [5 empty] | 10 | Kg | [6 empty] | Dayang | China |  | 4061 |  | 2026-06-22 | HMB | Advance |  | 10.85 | $ | 278.6 | 466.01 | 108.5 | 129830.386 | 30228.1 |  |  |  | 7223 |  | FOB |  |  |  |  | Air |  |  |  | Lahore | [14 empty] | 0 |  |  | 0 | 0 | 2026-06-22 | 30228.1 | Paid |  |  |  | 2026-07-30 | 200000 | Unpaid | 278.6 | 30228.1 | 30530.381 | 0.29 | 0.065 |  |  |  | Kg | [8 empty] | Under Production |  | 65 |  | 3 |  | 3
Shafts/Ongoing/Import Status/Import Rem | QEN |  | Samples |  | TMPNL0254 |  | Welding Electrodes-DIN8555 E7-UM-250-K | 3.2mm | [5 empty] | 5 | Kg | [6 empty] | Dayang | China |  | 4061 |  | 2026-06-22 | HMB | Advance |  | 3.14 | $ | 278.6 |  | 15.7 |  | 4374.02 |  |  |  | 7223 |  | FOB |  |  |  |  | Air |  |  |  | Lahore | [14 empty] | 0 |  |  | 0 | 0 | 2026-06-22 | 4374.02 | Paid |  |  |  | 2026-07-30 | 200000 | Unpaid | 278.6 | 4374.02 | 4417.7602 | 0.29 | 0.065 |  |  |  | Kg | [8 empty] | Under Production |  | 65 |  | 3 |  | 3
Shafts/Ongoing/Import Status/Import Rem | QEN |  | Samples |  | TMPNL0255 |  | Welding Electrodes-E309-16 | 3.2mm | [5 empty] | 2 | Kg | [6 empty] | Dayang | China |  | 4061 |  | 2026-06-22 | HMB | Advance |  | 3.92 | $ | 278.6 |  | 7.84 |  | 2184.224 |  |  |  | 7223 |  | FOB |  |  |  |  | Air |  |  |  | Lahore | [14 empty] | 0 |  |  | 0 | 0 | 2026-06-22 | 2184.224 | Paid |  |  |  | 2026-07-30 | 200000 | Unpaid | 278.6 | 2184.224 | 2206.0662 | 0.29 | 0.065 |  |  |  | Kg | [8 empty] | Under Production |  | 65 |  | 3 |  | 3
Shafts/Ongoing/Import Status/Import Rem | QEN |  | Samples |  | TMPNL0256 |  | Welding Electrodes-E307-16 | 3.2mm | [5 empty] | 2 | Kg | [6 empty] | Dayang | China |  | 4061 |  | 2026-06-22 | HMB | Advance |  | 4.84 | $ | 278.6 |  | 9.68 |  | 2696.848 |  |  |  | 7223 |  | FOB |  |  |  |  | Air |  |  |  | Lahore | [14 empty] | 0 |  |  | 0 | 0 | 2026-06-22 | 2696.848 | Paid |  |  |  | 2026-07-30 | 200000 | Unpaid | 278.6 | 2696.848 | 2723.8165 | 0.29 | 0.065 |  |  |  | Kg | [8 empty] | Under Production |  | 65 |  | 3 |  | 3
Shafts/Ongoing/Import Status/Import Rem | QEN |  | Samples |  | TMPNL0257 |  | Welding Electrodes-EFeCr-A8 | 3.2mm | [5 empty] | 2 | Kg | [6 empty] | Dayang | China |  | 4061 |  | 2026-06-22 | HMB | Advance |  | 5.23 | $ | 278.6 |  | 10.46 |  | 2914.156 |  |  |  | 7223 |  | FOB |  |  |  |  | Air |  |  |  | Lahore | [14 empty] | 0 |  |  | 0 | 0 | 2026-06-22 | 2914.156 | Paid |  |  |  | 2026-07-30 | 200000 | Unpaid | 278.6 | 2914.156 | 2943.2976 | 0.29 | 0.065 |  |  |  | Kg | [8 empty] | Under Production |  | 65 |  | 3 |  | 3
Shafts/Ongoing/Import Status/Import Rem | QEN |  | Samples |  | TMPNL0258 |  | Welding Electrodes-ECuSn-C | 3.2mm | [5 empty] | 2 | Kg | [6 empty] | Dayang | China |  | 4061 |  | 2026-06-22 | HMB | Advance |  | 19.48 | $ | 278.6 |  | 38.96 |  | 10854.256 |  |  |  | 7223 |  | FOB |  |  |  |  | Air |  |  |  | Lahore | [14 empty] | 0 |  |  | 0 | 0 | 2026-06-22 | 10854.256 | Paid |  |  |  | 2026-07-30 | 200000 | Unpaid | 278.6 | 10854.256 | 10962.7986 | 0.29 | 0.065 |  |  |  | Kg | [8 empty] | Under Production |  | 65 |  | 3 |  | 3
Shafts/Ongoing/Import Status/Import Rem | QEN |  | Samples |  | TMPNL0259 |  | Welding Electrodes-E310-16 | 3.2mm | [5 empty] | 2 | Kg | [6 empty] | Dayang | China |  | 4061 |  | 2026-06-22 | HMB | Advance |  | 6.01 | $ | 278.6 |  | 12.02 |  | 3348.772 |  |  |  | 7223 |  | FOB |  |  |  |  | Air |  |  |  | Lahore | [14 empty] | 0 |  |  | 0 | 0 | 2026-06-22 | 3348.772 | Paid |  |  |  | 2026-07-30 | 200000 | Unpaid | 278.6 | 3348.772 | 3382.2597 | 0.29 | 0.065 |  |  |  | Kg | [8 empty] | Under Production |  | 65 |  | 3 |  | 3
Shafts/Ongoing/Import Status/Import Rem | QEN |  | Samples |  | TMPNL0260 |  | Welding Electrodes-ENIFE-CI | 3.2mm | [5 empty] | 2 | Kg | [6 empty] | Dayang | China |  | 4061 |  | 2026-06-22 | HMB | Advance |  | 14.38 | $ | 278.6 |  | 28.76 |  | 8012.536 |  |  |  | 7223 |  | FOB |  |  |  |  | Air |  |  |  | Lahore | [14 empty] | 0 |  |  | 0 | 0 | 2026-06-22 | 8012.536 | Paid |  |  |  | 2026-07-30 | 200000 | Unpaid | 278.6 | 8012.536 | 8092.6614 | 0.29 | 0.065 |  |  |  | Kg | [8 empty] | Under Production |  | 65 |  | 3 |  | 3
Shafts/Ongoing/Import Status/Import Rem | QEN |  | Samples |  | TMPNL0261 |  | Welding Electrodes-E312-16 | 3.2mm | [5 empty] | 2 | Kg | [6 empty] | Dayang | China |  | 4061 |  | 2026-06-22 | HMB | Advance |  | 5.88 | $ | 278.6 |  | 11.76 |  | 3276.336 |  |  |  | 7223 |  | FOB |  |  |  |  | Air |  |  |  | Lahore | [14 empty] | 0 |  |  | 0 | 0 | 2026-06-22 | 3276.336 | Paid |  |  |  | 2026-07-30 | 200000 | Unpaid | 278.6 | 3276.336 | 3309.0994 | 0.29 | 0.065 |  |  |  | Kg | [8 empty] | Under Production |  | 65 |  | 3 |  | 3
Shafts/Ongoing/Import Status/Import Rem | QEN |  | Samples |  | TMPNL0262 |  | Welding Electrodes-E7018 | 3.2mm | [5 empty] | 2 | Kg | [6 empty] | Dayang | China |  | 4061 |  | 2026-06-22 | HMB | Advance |  | 0.89 | $ | 278.6 |  | 1.78 |  | 495.908 |  |  |  | 7223 |  | FOB |  |  |  |  | Air |  |  |  | Lahore | [14 empty] | 0 |  |  | 0 | 0 | 2026-06-22 | 495.908 | Paid |  |  |  | 2026-07-30 | 200000 | Unpaid | 278.6 | 495.908 | 500.8671 | 0.29 | 0.065 |  |  |  | Kg | [8 empty] | Under Production |  | 65 |  | 3 |  | 3
Shafts/Ongoing/Import Status/Import Rem | QEN |  | Samples |  | TMPNL0263 |  | Welding Wire-E71T-1C | 1.2mm | [5 empty] | 15 | Kg | [6 empty] | Dayang | China |  | 4061 |  | 2026-06-22 | HMB | Advance |  | 1.05 | $ | 278.6 |  | 15.75 |  | 4387.95 |  |  |  | 7223 |  | FOB |  |  |  |  | Air |  |  |  | Lahore | [14 empty] | 0 |  |  | 0 | 0 | 2026-06-22 | 4387.95 | Paid |  |  |  | 2026-07-30 | 200000 | Unpaid | 278.6 | 4387.95 | 4431.8295 | 0.29 | 0.065 |  |  |  | Kg | [8 empty] | Under Production |  | 65 |  | 3 |  | 3
Shafts/Ongoing/Import Status/Import Rem | QEN |  | Samples |  | TMPNL0264 |  | Welding Wire-ER80S-B2 | 1.2mm | [5 empty] | 50 | Kg | [6 empty] | Dayang | China |  | 4061 |  | 2026-06-22 | HMB | Advance |  | 2 | $ | 278.6 |  | 100 |  | 27860 |  |  |  | 7223 |  | FOB |  |  |  |  | Air |  |  |  | Lahore | [14 empty] | 0 |  |  | 0 | 0 | 2026-06-22 | 27860 | Paid |  |  |  | 2026-07-30 | 200000 | Unpaid | 278.6 | 27860 | 28138.6 | 0.29 | 0.065 |  |  |  | Kg | [8 empty] | Under Production |  | 65 |  | 3 |  | 3
Shafts/Ongoing/Import Status/Import Rem | QEN |  | Samples |  | TMPNL0265 |  | Welding Flux-SJ101 | 3.2mm | [5 empty] | 20 | Kg | [6 empty] | Dayang | China |  | 4061 |  | 2026-06-22 | HMB | Advance |  | 0.52 | $ | 278.6 |  | 10.4 |  | 2897.44 |  |  |  | 7223 |  | FOB |  |  |  |  | Air |  |  |  | Lahore | [14 empty] | 0 |  |  | 0 | 0 | 2026-06-22 | 2897.44 | Paid |  |  |  | 2026-07-30 | 200000 | Unpaid | 278.6 | 2897.44 | 2926.4144 | 0.29 | 0.065 |  |  |  | Kg | [8 empty] | Under Production |  | 65 |  | 3 |  | 3
Shafts/Ongoing/Import Status/Import Rem | QEN |  | Samples |  | TMPNL0266 |  | Welding Wire-EM12K | 3.2mm | [5 empty] | 100 | Kg | [6 empty] | Dayang | China |  | 4061 |  | 2026-06-22 | HMB | Advance |  | 0.84 | $ | 278.6 |  | 84 |  | 23402.4 |  |  |  | 7223 |  | FOB |  |  |  |  | Air |  |  |  | Lahore | [14 empty] | 0 |  |  | 0 | 0 | 2026-06-22 | 23402.4 | Paid |  |  |  | 2026-07-30 | 200000 | Unpaid | 278.6 | 23402.4 | 23636.424 | 0.29 | 0.065 |  |  |  | Kg | [8 empty] | Under Production |  | 65 |  | 3 |  | 3
Shafts/Ongoing/Import Status/Import Rem | QEN |  | Samples |  | TMPNL0267 |  | Welding Flux-SJ101 | [6 empty] | 20 | Kg | [6 empty] | Dayang | China |  | 4061 |  | 2026-06-22 | HMB | Advance |  | 0.52 | $ | 278.6 |  | 10.4 |  | 2897.44 |  |  |  | 7223 |  | FOB |  |  |  |  | Air |  |  |  | Lahore | [14 empty] | 0 |  |  | 0 | 0 | 2026-06-22 | 2897.44 | Paid |  |  |  | 2026-07-30 | 200000 | Unpaid | 278.6 | 2897.44 | 2926.4144 | 0.29 | 0.065 |  |  |  | Kg | [8 empty] | Under Production |  | 65 |  | 3 |  | 3
Shafts/Ongoing/Import Status/Import Rem | QCL | Cutting Tools | Store |  | 14846-60 |  | Swing Frame Grinding Wheel | 50x50x500(NK16Q58) | [5 empty] | 50 | Pcs |  |  | 2026-05-12 |  | 2026-08-12 |  | Aten | Turkey |  | 4045 |  | 2026-06-22 | HMB | Advance |  | 125 | $ | 278.6 |  | 6250 |  | 1741250 |  |  |  | 6804.1 |  | CFR |  |  |  |  | Sea |  |  |  | Karachi | 2026-07-06 | 2026-07-21 | 2026-09-14 |  |  |  | 2026-09-14 | [7 empty] | 0 | 2026-09-24 |  | 0 | -43 | 2026-06-16 | 1741250 | Paid |  |  |  | 2026-07-30 | 200000 | Unpaid | 278.6 | 1741250 | 1758662.5 | 0.29 | 0.065 |  |  | 38367 | Pcs | [8 empty] | Under Production |  | 38 |  | 1 |  | 2
Shafts/Ongoing/Import Status/Import Rem | QCL | Foundry Material | Store |  | 23558-60 |  | Neutral Lining | CXNRM | [5 empty] | 6 | Ton |  |  | 2026-05-20 |  | 2026-08-20 |  | HK Jinyuen | China |  | 4059 |  | 2026-06-22 | HMB | Advance |  | 1300 | $ | 278.6 | 7800 | 7800 | 2173080 | 2173080 |  |  |  | 3816 |  | FOB |  |  |  |  | Sea |  |  |  | Karachi | [14 empty] | 0 |  |  | 0 | 0 | 2026-06-22 | 2173080 | Paid |  |  |  | 2026-07-30 | 200000 | Unpaid | 278.6 | 2173080 | 2194810.8 | 0.24 | 0.065 |  |  | 455 | Kg | [8 empty] | Under Production |  | 44 |  | 1 |  | 2
Shafts/Ongoing/Import Status/Import Rem | QCL | Foundry Material | Store |  | TMPNL0268 |  | Foundry Coke | 80-140mm | [5 empty] | 150 | Ton |  |  | 2026-05-12 |  | 2026-08-12 | 13.1429 | Italiana Coke | Italy |  |  |  |  | HMB | LC |  | 507 | $ | 282 | 0 | 76050 | 0 | 21446100 |  |  |  | 2704.001 | YES | CFR Karachi |  |  |  |  | Sea |  |  |  | Karachi | [7 empty] | 0 | [6 empty] | 0 |  | 0 | 0 | 0 |  |  |  | 2026-07-15 | 21446100 | Unpaid | 2026-07-30 | 6389865.495 | Unpaid | 282 | 21446100 | 21660561 | 0.23 | 0.065 |  |  | 166 | Kgs | [8 empty] | LC in Process |  | 53 |  | 1 |  | 2
Shafts/Ongoing/Import Status/Import Rem | QBL-II | Refactory | Store |  | 2823-60 |  | Exothermic Powder | [6 empty] | 3 | Ton |  |  | 2026-04-28 |  | 2026-07-28 | 13 | SQ | China |  | 4067 |  | 2026-06-22 | BAH | Advance |  | 770 | $ | 278.6 | 3704.4 | 2310 | 1032045.84 | 643566 |  |  |  | 3824.1 |  | FOB |  |  |  |  | Sea |  |  |  | Karachi | [14 empty] | 0 |  |  | 0 | 0 | 2026-06-22 | 643566 | Paid |  |  |  | 2026-07-30 | 211250.5395 | Unpaid | 278.6 | 643566 | 650001.66 | 0.26 | 0.065 |  |  | 302 | Kg | [8 empty] | Under Production |  | 3 |  | 1 |  | 4
Shafts/Ongoing/Import Status/Import Rem | QBL-II | Refactory | Store |  | 12571-60 |  | Exothermic Riser Sleeves | [6 empty] | 120 | Pcs |  |  | 2026-04-28 |  | 2026-07-28 | 13 | SQ | China |  | 4067 |  | 2026-06-22 | BAH | Advance |  | 11.62 | $ | 278.6 |  | 1394.4 |  | 388479.84 |  |  |  | 6903.901 |  | FOB |  |  |  |  | Sea |  |  |  | Karachi | [14 empty] | 0 |  |  | 0 | 0 | 2026-06-22 | 388479.84 | Paid |  |  |  | 2026-07-30 | 115747.5683 | Unpaid | 278.6 | 388479.84 | 392364.6384 | 0.23 | 0.065 |  |  | 4230 | Pcs | [8 empty] | Under Production |  | 3 |  | 1 |  | 4
Shafts/Ongoing/Import Status/Import Rem | QBL-II | Refactory | Store |  | 16781-60 |  | Straight Pipe/Ceramic Tube | Dia60,L300 | [5 empty] | 3045 | Pcs |  |  | 2026-04-28 |  | 2026-07-28 |  | One Piece | China |  |  |  |  | BAH | CAD |  | 6.5 | ¥ | 41 | 0 | 19792.5 | 0 | 811492.5 |  |  |  | 6903.901 |  | CFR Karachi |  |  |  |  | Sea |  |  |  | Karachi | 2026-06-20 | 2026-06-30 | 2026-07-22 |  |  |  | 2026-07-22 | [7 empty] | 0 | 2026-08-01 |  | 0 | -4 |  |  |  | 2026-07-15 | 811492.5 | Unpaid | 2026-07-30 | 241784.1904 | Unpaid | 41 | 811492.5 | 819607.425 | 0.23 | 0.065 |  |  |  | Pcs | [8 empty] | Under Production |  | 9 |  | 1 |  | 4
Shafts/Ongoing/Import Status/Import Rem | QBL-II | Refactory | Store |  | 16772-60 |  | T Pipe brick | Dia40 | [5 empty] | 500 | Pcs |  |  | 2026-05-12 |  | 2026-08-12 |  | One Piece | China |  |  |  |  | BAH | CAD |  | 3.28 | ¥ | 41 |  | 1640 |  | 67240 |  |  |  | 6903.901 |  | CFR Karachi |  |  |  |  | Sea |  |  |  | Karachi | 2026-06-20 | 2026-06-30 | 2026-07-22 |  |  |  | 2026-07-22 | [7 empty] | 0 | 2026-08-01 |  | 0 | 11 |  |  |  | 2026-07-15 | 67240 | Unpaid | 2026-07-30 | 20034.158 | Unpaid | 41 | 67240 | 67912.4 | 0.23 | 0.065 |  |  |  | Pcs | [8 empty] | Under Production |  | 9 |  | 1 |  | 4
Shafts/Ongoing/Import Status/Import Rem | QBL-II | Refactory | Store |  | TMPNL0269 |  | T Pipe brick | Dia60 | [5 empty] | 700 | Pcs | [6 empty] | One Piece | China |  |  |  |  | BAH | CAD |  | 5.35 | ¥ | 41 |  | 3745 |  | 153545 |  |  |  | 6903.901 |  | CFR Karachi |  |  |  |  | Sea |  |  |  | Karachi | 2026-06-20 | 2026-06-30 | 2026-07-22 |  |  |  | 2026-07-22 | [7 empty] | 0 | 2026-08-01 |  | 0 | 0 |  |  |  | 2026-07-15 | 153545 | Unpaid | 2026-07-30 | 45748.7328 | Unpaid | 41 | 153545 | 155080.45 | 0.23 | 0.065 |  |  |  | Pcs | [8 empty] | Under Production |  | 9 |  | 1 |  | 4
Shafts/Ongoing/Import Status/Import Rem | QBL-II | Refactory | Store |  | TMPNL0270 |  | Pouring Basin | Dia200-80 | [5 empty] | 402 | Pcs | [6 empty] | One Piece | China |  |  |  |  | BAH | CAD |  | 22.46 | ¥ | 41 |  | 9028.92 |  | 370185.72 |  |  |  | 6903.901 |  | CFR Karachi |  |  |  |  | Sea |  |  |  | Karachi | 2026-06-20 | 2026-06-30 | 2026-07-22 |  |  |  | 2026-07-22 | [7 empty] | 0 | 2026-08-01 |  | 0 | 0 |  |  |  | 2026-07-15 | 370185.72 | Unpaid | 2026-07-30 | 110296.8353 | Unpaid | 41 | 370185.72 | 373887.5772 | 0.23 | 0.065 |  |  |  | Pcs | [8 empty] | Under Production |  | 9 |  | 1 |  | 4
Shafts/Ongoing/Import Status/Import Rem | QBL-II | Refactory | Store |  | TMPNL0271 |  | Fire Slab-Straight | 250*250*20-dia80 | [5 empty] | 500 | Pcs |  |  | 2026-04-28 |  | 2026-07-28 |  | One Piece | China |  |  |  |  | BAH | CAD |  | 12.56 | ¥ | 41 |  | 6280 |  | 257480 |  |  |  | 6903.901 |  | CFR Karachi |  |  |  |  | Sea |  |  |  | Karachi | 2026-06-20 | 2026-06-30 | 2026-07-22 |  |  |  | 2026-07-22 | [7 empty] | 0 | 2026-08-01 |  | 0 | -4 |  |  |  | 2026-07-15 | 257480 | Unpaid | 2026-07-30 | 76716.166 | Unpaid | 41 | 257480 | 260054.8 | 0.23 | 0.065 |  |  |  | Pcs | [8 empty] | Under Production |  | 9 |  | 1 |  | 4
Shafts/Ongoing/Import Status/Import Rem | QBL-II | Refactory | Store |  | TMPNL0272 |  | Fire Slab-Straight | 250*250*20-dia60 | [5 empty] | 500 | Pcs |  |  | 2026-04-28 |  | 2026-07-28 |  | One Piece | China |  |  |  |  | BAH | CAD |  | 12.56 | ¥ | 41 |  | 6280 |  | 257480 |  |  |  | 6903.901 |  | CFR Karachi |  |  |  |  | Sea |  |  |  | Karachi | 2026-06-20 | 2026-06-30 | 2026-07-22 |  |  |  | 2026-07-22 | [7 empty] | 0 | 2026-08-01 |  | 0 | -4 |  |  |  | 2026-07-15 | 257480 | Unpaid | 2026-07-30 | 76716.166 | Unpaid | 41 | 257480 | 260054.8 | 0.23 | 0.065 |  |  |  | Pcs | [8 empty] | Under Production |  | 9 |  | 1 |  | 4
Shafts/Ongoing/Import Status/Import Rem | QBL-II | Refactory | Store |  | 25655-60 |  | Fire Slab-Straight | 250*250*20 | [5 empty] | 4000 | Pcs |  |  | 2026-04-28 |  | 2026-07-28 |  | One Piece | China |  |  |  |  | BAH | CAD |  | 12.56 | ¥ | 41 |  | 50240 |  | 2059840 |  |  |  | 6903.901 |  | CFR Karachi |  |  |  |  | Sea |  |  |  | Karachi | 2026-06-20 | 2026-06-30 | 2026-07-22 |  |  |  | 2026-07-22 | [7 empty] | 0 | 2026-08-01 |  | 0 | -4 |  |  |  | 2026-07-15 | 2059840 | Unpaid | 2026-07-30 | 613729.328 | Unpaid | 41 | 2059840 | 2080438.4 | 0.23 | 0.065 |  |  |  | Pcs | [8 empty] | Under Production |  | 9 |  | 1 |  | 4
Shafts/Ongoing/Import Status/Import Rem | QBL-II | Refactory | Store |  | TMPNL0273 |  | Exothermic Riser Sleeves | S80/BGK-1 | [5 empty] | 10 | Pcs | [6 empty] | One Piece | China |  |  |  |  | BAH | CAD |  | 5.74 | ¥ | 41 |  | 57.4 |  | 2353.4 |  |  |  | 6903.901 |  | CFR Karachi |  |  |  |  | Sea |  |  |  | Karachi | 2026-06-20 | 2026-06-30 | 2026-07-22 |  |  |  | 2026-07-22 | [7 empty] | 0 | 2026-08-01 |  | 0 | 0 |  |  |  | 2026-07-15 | 2353.4 | Unpaid | 2026-07-30 | 701.1955 | Unpaid | 41 | 2353.4 | 2376.934 | 0.23 | 0.065 |  |  |  | Pcs | [8 empty] | Under Production |  | 9 |  | 1 |  | 4
Shafts/Ongoing/Import Status/Import Rem | QBL-II | Refactory | Store |  | TMPNL0274 |  | Exothermic Riser Sleeves | S90/BGK-2 | [5 empty] | 10 | Pcs | [6 empty] | One Piece | China |  |  |  |  | BAH | CAD |  | 6.86 | ¥ | 41 |  | 68.6 |  | 2812.6 |  |  |  | 6903.901 |  | CFR Karachi |  |  |  |  | Sea |  |  |  | Karachi | 2026-06-20 | 2026-06-30 | 2026-07-22 |  |  |  | 2026-07-22 | [7 empty] | 0 | 2026-08-01 |  | 0 | 0 |  |  |  | 2026-07-15 | 2812.6 | Unpaid | 2026-07-30 | 838.0142 | Unpaid | 41 | 2812.6 | 2840.726 | 0.23 | 0.065 |  |  |  | Pcs | [8 empty] | Under Production |  | 9 |  | 1 |  | 4
Shafts/Ongoing/Import Status/Import Rem | QBL-II | Refactory | Store |  | TMPNL0275 |  | Exothermic Riser Sleeves | S100/BGK-3 | [5 empty] | 10 | Pcs | [6 empty] | One Piece | China |  |  |  |  | BAH | CAD |  | 9.72 | ¥ | 41 |  | 97.2 |  | 3985.2 |  |  |  | 6903.901 |  | CFR Karachi |  |  |  |  | Sea |  |  |  | Karachi | 2026-06-20 | 2026-06-30 | 2026-07-22 |  |  |  | 2026-07-22 | [7 empty] | 0 | 2026-08-01 |  | 0 | 0 |  |  |  | 2026-07-15 | 3985.2 | Unpaid | 2026-07-30 | 1187.3903 | Unpaid | 41 | 3985.2 | 4025.052 | 0.23 | 0.065 |  |  |  | Pcs | [8 empty] | Under Production |  | 9 |  | 1 |  | 4
Shafts/Ongoing/Import Status/Import Rem | QBL-II | Refactory | Store |  | TMPNL0276 |  | Exothermic Riser Sleeves | S120/BGK-4 | [5 empty] | 10 | Pcs | [6 empty] | One Piece | China |  |  |  |  | BAH | CAD |  | 16.27 | ¥ | 41 |  | 162.7 |  | 6670.7 |  |  |  | 6903.901 |  | CFR Karachi |  |  |  |  | Sea |  |  |  | Karachi | 2026-06-20 | 2026-06-30 | 2026-07-22 |  |  |  | 2026-07-22 | [7 empty] | 0 | 2026-08-01 |  | 0 | 0 |  |  |  | 2026-07-15 | 6670.7 | Unpaid | 2026-07-30 | 1987.5351 | Unpaid | 41 | 6670.7 | 6737.407 | 0.23 | 0.065 |  |  |  | Pcs | [8 empty] | Under Production |  | 9 |  | 1 |  | 4
Shafts/Ongoing/Import Status/Import Rem | QBL-II | Refactory | Store |  | TMPNL0277 |  | Exothermic Riser Sleeves | S150/BGK-5 | [5 empty] | 10 | Pcs | [6 empty] | One Piece | China |  |  |  |  | BAH | CAD |  | 39.85 | ¥ | 41 |  | 398.5 |  | 16338.5 |  |  |  | 6903.901 |  | CFR Karachi |  |  |  |  | Sea |  |  |  | Karachi | 2026-06-20 | 2026-06-30 | 2026-07-22 |  |  |  | 2026-07-22 | [7 empty] | 0 | 2026-08-01 |  | 0 | 0 |  |  |  | 2026-07-15 | 16338.5 | Unpaid | 2026-07-30 | 4868.0561 | Unpaid | 41 | 16338.5 | 16501.885 | 0.23 | 0.065 |  |  |  | Pcs | [8 empty] | Under Production |  | 9 |  | 1 |  | 4
Shafts/Ongoing/Import Status/Import Rem | QBL-II | Refactory | Store |  | TMPNL0278 |  | Exothermic Riser Sleeves | S180/BGK-5.5 | [5 empty] | 10 | Pcs | [6 empty] | One Piece | China |  |  |  |  | BAH | CAD |  | 43.31 | ¥ | 41 |  | 433.1 |  | 17757.1 |  |  |  | 6903.901 |  | CFR Karachi |  |  |  |  | Sea |  |  |  | Karachi | 2026-06-20 | 2026-06-30 | 2026-07-22 |  |  |  | 2026-07-22 | [7 empty] | 0 | 2026-08-01 |  | 0 | 0 |  |  |  | 2026-07-15 | 17757.1 | Unpaid | 2026-07-30 | 5290.7279 | Unpaid | 41 | 17757.1 | 17934.671 | 0.23 | 0.065 |  |  |  | Pcs | [8 empty] | Under Production |  | 9 |  | 1 |  | 4
Shafts/Ongoing/Import Status/Import Rem | QBL-II | Refactory | Store |  | TMPNL0279 |  | Exothermic Riser Sleeves | S200/BGK-7 | [5 empty] | 10 | Pcs | [6 empty] | One Piece | China |  |  |  |  | BAH | CAD |  | 57.19 | ¥ | 41 |  | 571.9 |  | 23447.9 |  |  |  | 6903.901 |  | CFR Karachi |  |  |  |  | Sea |  |  |  | Karachi | 2026-06-20 | 2026-06-30 | 2026-07-22 |  |  |  | 2026-07-22 | [7 empty] | 0 | 2026-08-01 |  | 0 | 0 |  |  |  | 2026-07-15 | 23447.9 | Unpaid | 2026-07-30 | 6986.3018 | Unpaid | 41 | 23447.9 | 23682.379 | 0.23 | 0.065 |  |  |  | Pcs | [8 empty] | Under Production |  | 9 |  | 1 |  | 4
Shafts/Ongoing/Import Status/Import Rem | QBL-II | Refactory | Store |  | TMPNL0280 |  | Exothermic Riser Sleeves | S225/BGK-8 | [5 empty] | 10 | Pcs | [6 empty] | One Piece | China |  |  |  |  | BAH | CAD |  | 71.76 | ¥ | 41 |  | 717.6 |  | 29421.6 |  |  |  | 6903.901 |  | CFR Karachi |  |  |  |  | Sea |  |  |  | Karachi | 2026-06-20 | 2026-06-30 | 2026-07-22 |  |  |  | 2026-07-22 | [7 empty] | 0 | 2026-08-01 |  | 0 | 0 |  |  |  | 2026-07-15 | 29421.6 | Unpaid | 2026-07-30 | 8766.1657 | Unpaid | 41 | 29421.6 | 29715.816 | 0.23 | 0.065 |  |  |  | Pcs | [8 empty] | Under Production |  | 9 |  | 1 |  | 4
Shafts/Ongoing/Import Status/Import Rem | QBL-II | Refactory | Store |  | TMPNL0281 |  | Exothermic Riser Sleeves | S250/BGK-9 | [5 empty] | 10 | Pcs | [6 empty] | One Piece | China |  |  |  |  | BAH | CAD |  | 98.48 | ¥ | 41 |  | 984.8 |  | 40376.8 |  |  |  | 6903.901 |  | CFR Karachi |  |  |  |  | Sea |  |  |  | Karachi | 2026-06-20 | 2026-06-30 | 2026-07-22 |  |  |  | 2026-07-22 | [7 empty] | 0 | 2026-08-01 |  | 0 | 0 |  |  |  | 2026-07-15 | 40376.8 | Unpaid | 2026-07-30 | 12030.2676 | Unpaid | 41 | 40376.8 | 40780.568 | 0.23 | 0.065 |  |  |  | Pcs | [8 empty] | Under Production |  | 9 |  | 1 |  | 4
Shafts/Ongoing/Import Status/Import Rem | QBL-II | Refactory | Store |  | TMPNL0282 |  | Exothermic Riser Sleeves | A60/90-6/9 | [5 empty] | 10 | Pcs | [6 empty] | One Piece | China |  |  |  |  | BAH | CAD |  | 4.82 | ¥ | 41 |  | 48.2 |  | 1976.2 |  |  |  | 6903.901 |  | CFR Karachi |  |  |  |  | Sea |  |  |  | Karachi | 2026-06-20 | 2026-06-30 | 2026-07-22 |  |  |  | 2026-07-22 | [7 empty] | 0 | 2026-08-01 |  | 0 | 0 |  |  |  | 2026-07-15 | 1976.2 | Unpaid | 2026-07-30 | 588.8088 | Unpaid | 41 | 1976.2 | 1995.962 | 0.23 | 0.065 |  |  |  | Pcs | [8 empty] | Under Production |  | 9 |  | 1 |  | 4
Shafts/Ongoing/Import Status/Import Rem | QBL-II | Refactory | Store |  | TMPNL0283 |  | Exothermic Riser Sleeves | T80/120/120-OBG-4 | [5 empty] | 10 | Pcs | [6 empty] | One Piece | China |  |  |  |  | BAH | CAD |  | 11.26 | ¥ | 41 |  | 112.6 |  | 4616.6 |  |  |  | 6903.901 |  | CFR Karachi |  |  |  |  | Sea |  |  |  | Karachi | 2026-06-20 | 2026-06-30 | 2026-07-22 |  |  |  | 2026-07-22 | [7 empty] | 0 | 2026-08-01 |  | 0 | 0 |  |  |  | 2026-07-15 | 4616.6 | Unpaid | 2026-07-30 | 1375.516 | Unpaid | 41 | 4616.6 | 4662.766 | 0.23 | 0.065 |  |  |  | Pcs | [8 empty] | Under Production |  | 9 |  | 1 |  | 4
Shafts/Ongoing/Import Status/Import Rem | QBL-II | Refactory | Store |  | TMPNL0284 |  | Exothermic Riser Sleeves | T80/160/150-OBG-5 | [5 empty] | 10 | Pcs | [6 empty] | One Piece | China |  |  |  |  | BAH | CAD |  | 19.91 | ¥ | 41 |  | 199.1 |  | 8163.1 |  |  |  | 6903.901 |  | CFR Karachi |  |  |  |  | Sea |  |  |  | Karachi | 2026-06-20 | 2026-06-30 | 2026-07-22 |  |  |  | 2026-07-22 | [7 empty] | 0 | 2026-08-01 |  | 0 | 0 |  |  |  | 2026-07-15 | 8163.1 | Unpaid | 2026-07-30 | 2432.1956 | Unpaid | 41 | 8163.1 | 8244.731 | 0.23 | 0.065 |  |  |  | Pcs | [8 empty] | Under Production |  | 9 |  | 1 |  | 4
Shafts/Ongoing/Import Status/Import Rem | QBL-II | Refactory | Store |  | TMPNL0285 |  | Exothermic Riser Sleeves | T100/200/200-OBG-6 | [5 empty] | 10 | Pcs | [6 empty] | One Piece | China |  |  |  |  | BAH | CAD |  | 35.7 | ¥ | 41 |  | 357 |  | 14637 |  |  |  | 6903.901 |  | CFR Karachi |  |  |  |  | Sea |  |  |  | Karachi | 2026-06-20 | 2026-06-30 | 2026-07-22 |  |  |  | 2026-07-22 | [7 empty] | 0 | 2026-08-01 |  | 0 | 0 |  |  |  | 2026-07-15 | 14637 | Unpaid | 2026-07-30 | 4361.0942 | Unpaid | 41 | 14637 | 14783.37 | 0.23 | 0.065 |  |  |  | Pcs | [8 empty] | Under Production |  | 9 |  | 1 |  | 4
Shafts/Ongoing/Import Status/Import Rem | QBL-II | Refactory | Store |  | TMPNL0286 |  | Exothermic Riser Sleeves | T120/240/200-OBG-7 | [5 empty] | 10 | Pcs | [6 empty] | One Piece | China |  |  |  |  | BAH | CAD |  | 40.26 | ¥ | 41 |  | 402.6 |  | 16506.6 |  |  |  | 6903.901 |  | CFR Karachi |  |  |  |  | Sea |  |  |  | Karachi | 2026-06-20 | 2026-06-30 | 2026-07-22 |  |  |  | 2026-07-22 | [7 empty] | 0 | 2026-08-01 |  | 0 | 0 |  |  |  | 2026-07-15 | 16506.6 | Unpaid | 2026-07-30 | 4918.1415 | Unpaid | 41 | 16506.6 | 16671.666 | 0.23 | 0.065 |  |  |  | Pcs | [8 empty] | Under Production |  | 9 |  | 1 |  | 4
Shafts/Ongoing/Import Status/Import Rem | QBL-II | Refactory | Store |  | TMPNL0287 |  | Exothermic Riser Sleeves | T140/280/200-OBG-8 | [5 empty] | 10 | Pcs | [6 empty] | One Piece | China |  |  |  |  | BAH | CAD |  | 48.17 | ¥ | 41 |  | 481.7 |  | 19749.7 |  |  |  | 6903.901 |  | CFR Karachi |  |  |  |  | Sea |  |  |  | Karachi | 2026-06-20 | 2026-06-30 | 2026-07-22 |  |  |  | 2026-07-22 | [7 empty] | 0 | 2026-08-01 |  | 0 | 0 |  |  |  | 2026-07-15 | 19749.7 | Unpaid | 2026-07-30 | 5884.4231 | Unpaid | 41 | 19749.7 | 19947.197 | 0.23 | 0.065 |  |  |  | Pcs | [8 empty] | Under Production |  | 9 |  | 1 |  | 4
Shafts/Ongoing/Import Status/Import Rem | QBL-II | Refactory | Store |  | TMPNL0288 |  | Exothermic Riser Sleeves | T160/320/200-OBG-9 | [5 empty] | 10 | Pcs | [6 empty] | One Piece | China |  |  |  |  | BAH | CAD |  | 59.37 | ¥ | 41 |  | 593.7 |  | 24341.7 |  |  |  | 6903.901 |  | CFR Karachi |  |  |  |  | Sea |  |  |  | Karachi | 2026-06-20 | 2026-06-30 | 2026-07-22 |  |  |  | 2026-07-22 | [7 empty] | 0 | 2026-08-01 |  | 0 | 0 |  |  |  | 2026-07-15 | 24341.7 | Unpaid | 2026-07-30 | 7252.6095 | Unpaid | 41 | 24341.7 | 24585.117 | 0.23 | 0.065 |  |  |  | Pcs | [8 empty] | Under Production |  | 9 |  | 1 |  | 4
Shafts/Ongoing/Import Status/Import Rem | QBL-II | Refactory | Store |  | TMPNL0289 |  | Exothermic Riser Sleeves | T180/360/200-OBG-10 | [5 empty] | 10 | Pcs | [6 empty] | One Piece | China |  |  |  |  | BAH | CAD |  | 67.21 | ¥ | 41 |  | 672.1 |  | 27556.1 |  |  |  | 6903.901 |  | CFR Karachi |  |  |  |  | Sea |  |  |  | Karachi | 2026-06-20 | 2026-06-30 | 2026-07-22 |  |  |  | 2026-07-22 | [7 empty] | 0 | 2026-08-01 |  | 0 | 0 |  |  |  | 2026-07-15 | 27556.1 | Unpaid | 2026-07-30 | 8210.34 | Unpaid | 41 | 27556.1 | 27831.661 | 0.23 | 0.065 |  |  |  | Pcs | [8 empty] | Under Production |  | 9 |  | 1 |  | 4
Shafts/Ongoing/Import Status/Import Rem | QBL-II | Refactory | Store |  | TMPNL0290 |  | Exothermic Riser Sleeves | T200/400/200-OBG-11 | [5 empty] | 10 | Pcs | [6 empty] | One Piece | China |  |  |  |  | BAH | CAD |  | 83.66 | ¥ | 41 |  | 836.6 |  | 34300.6 |  |  |  | 6903.901 |  | CFR Karachi |  |  |  |  | Sea |  |  |  | Karachi | 2026-06-20 | 2026-06-30 | 2026-07-22 |  |  |  | 2026-07-22 | [7 empty] | 0 | 2026-08-01 |  | 0 | 0 |  |  |  | 2026-07-15 | 34300.6 | Unpaid | 2026-07-30 | 10219.8638 | Unpaid | 41 | 34300.6 | 34643.606 | 0.23 | 0.065 |  |  |  | Pcs | [8 empty] | Under Production |  | 9 |  | 1 |  | 4
Shafts/Ongoing/Import Status/Import Rem | QE | Engineering Item | Engg. |  | TMPNL0291 |  | NM 500 Plate | Hardox 500 | 75x1500 | 3000 | CE26-MO-0147 | CE26-MO-0147 | PPC Cement | 1 | Pcs | 2.649 | 2.649 | 2026-06-12 |  | 2026-07-24 |  | Henan Bebon | China |  | 4043 |  | 2026-06-16 | BAH | Advance |  | 2275.08 | $ | 278.6 | 6026.6869 | 6026.6869 | 1679034.9759 | 1679034.9759 |  |  |  | 7208.511 | NO | FOB |  |  |  |  | Sea |  |  |  | Karachi |  | 2026-07-07 | 2026-07-22 |  |  |  | 2026-07-22 | 15 | EFS | [5 empty] | 0 | 2026-08-01 |  | 0 | -8 | 2026-06-16 | 1679034.9759 | Paid |  |  |  |  | 551143.2308 | Unpaid | 278.6 | 1679034.9759 | 1695825.3257 | 0.26 | 0.065 |  |  | 717 | Kg | [8 empty] | Under Production | Cutting Inprocess ( RFD on 22-06-2026) Logistics is arranging Freight Forwarder for Shipping. | 39 | 1 | 1 |  | 1
Shafts/Ongoing/Import Status/Import Rem | QBL-II | Refactory | Store |  | 12568-60 |  | Exothermic Riser Sleeves | BGK-7/FT-100-S200 | [5 empty] | 228 | Pcs |  |  | 2026-04-28 |  | 2026-07-28 | 13 | Cukurova | Turkey |  | 68756 |  | 2026-06-09 | BAH | LC |  | 6.8 | € | 325 |  | 1550.4 |  | 503880 |  |  |  | 6903.901 |  | CFR Karachi |  |  |  |  | Sea |  |  |  | Karachi |  | 2026-06-26 | 2026-07-22 |  |  |  | 2026-07-22 | 26 | EFS | [5 empty] | 0 | 2026-08-01 |  | 0 | -4 |  |  |  | 2026-07-10 | 503880 | Unpaid | 2026-07-30 | 200000 | Unpaid | 325 | 503880 | 508918.8 | 0.23 | 0.065 |  |  |  | Pcs | [8 empty] | Under Production | Vessel Booking Received ETD: 26-06-26, ETA: 22-07-26 | 11 | 1 | 1 |  | 4
Shafts/Ongoing/Import Status/Import Rem | QCL | Refactory | Store |  | 16775-60 |  | Ceramic Tube | 40x300 | [5 empty] | 256 | Pcs |  |  | 2026-05-12 |  | 2026-08-12 |  | Selko | Turkey |  | 4069 |  | 2026-06-23 | HMB | Advance |  | 1.7 | $ | 278.55 | 1796.2 | 435.2 | 500331.51 | 121224.96 |  |  |  | 6903.901 |  | FOB |  |  |  |  | Sea |  |  |  | Karachi | [14 empty] | 0 |  |  | 0 |  | 2026-06-23 | 121224.96 | Paid |  |  |  | 2026-07-30 | 200000 | Unpaid | 278.55 | 121224.96 | 122437.2096 | 0.23 | 0.065 |  |  | 815 | Pcs | [8 empty] | Ready Awaiting Sailing | Material is ready, Packing List received from supplier.Forwarder arrnagment is in process. | 66 |  | 1 |  | 2
Shafts/Ongoing/Import Status/Import Rem | QCL | Refactory | Store |  | 16772-60 |  | Ceramic T Piece | Dia40 | [5 empty] | 720 | Pcs |  |  | 2026-05-12 |  | 2026-08-12 |  | Selko | Turkey |  | 4069 |  | 2026-06-23 | HMB | Advance |  | 1.6 | $ | 278.55 |  | 1152 |  | 320889.6 |  |  |  | 6903.901 |  | FOB |  |  |  |  | Sea |  |  |  | Karachi | [14 empty] | 0 |  |  | 0 |  | 2026-06-23 | 320889.6 | Paid |  |  |  | 2026-07-30 | 200000 | Unpaid | 278.55 | 320889.6 | 324098.496 | 0.23 | 0.065 |  |  | 617 | Pcs | [8 empty] | Ready Awaiting Sailing | Material is ready, Packing List received from supplier.Forwarder arrnagment is in process. | 66 |  | 1 |  | 2
Shafts/Ongoing/Import Status/Import Rem | QCL | Refactory | Store |  | 16784-60 |  | Ceramic T Piece | Dia60 | [5 empty] | 110 | Pcs |  |  | 2026-05-12 |  | 2026-08-12 |  | Selko | Turkey |  | 4069 |  | 2026-06-23 | HMB | Advance |  | 1.9 | $ | 278.55 |  | 209 |  | 58216.95 |  |  |  | 6903.901 |  | FOB |  |  |  |  | Sea |  |  |  | Karachi | [14 empty] | 0 |  |  | 0 |  | 2026-06-23 | 58216.95 | Paid |  |  |  | 2026-07-30 | 200000 | Unpaid | 278.55 | 58216.95 | 58799.1195 | 0.23 | 0.065 |  |  | 969 | Pcs | [8 empty] | Ready Awaiting Sailing | Material is ready, Packing List received from supplier.Forwarder arrnagment is in process. | 66 |  | 1 |  | 2
Shafts/Ongoing/Import Status/Import Rem | QCL | Ferro Alloys | Store |  | 2818-156 |  | Ferro Chrome L/C | [6 empty] | 10 | Ton |  |  | 2026-06-22 |  | 2026-09-23 | [13 empty] | 0 |  | 0 | 0 | [29 empty] | 0 |  |  | 0 |  |  |  |  | 2026-07-20 | 0 | Unpaid | 2026-07-30 | 200000 | Unpaid | 0 | 0 | 0 | 0.23 | 0.065 |  |  |  | Ton | [8 empty] | Costing in Process | [5 empty] | 2
Shafts/Ongoing/Import Status/Import Rem | QCL | Foundry Material | Store |  | 19572-60 |  | Titanium Cermet Rod | Dia14x30 | [5 empty] | 300 | Kg |  |  | 2026-07-29 |  | 2026-09-29 |  | Hunan Westion | China | [7 empty] | 85.5 | ¥ | 279 |  | 25650 |  | 7156350 |  |  |  | 8209 | [25 empty] | 0 |  |  | 0 |  | 2026-07-03 | 7156350 | Unpaid |  |  |  | 2026-07-30 | 200000 | Unpaid | 279 | 7156350 | 7227913.5 | 0.23 | 0.065 |  |  | 3664 | Kg | [8 empty] | Costing in Process |  | 67 |  |  |  | 2